| Workpackage number : | 1 |  |  | Start date or starting event: |  |  |  | Month 1 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Participant number: |  | 1 |  |  |  |  |  |  |  |  |
| Person-months per participant: |  |  |  |  |  |  |  |  |  |  |

Objectives Analysis of the State of the Art and Development of Concepts (Phase I) Work Area A: Task 1.1: Definition of content to be provided Task 1.2: Development of a documentation and digitization plan for content creation and management Work Area B: Task 1.3: Identification of standards to be used Task 1.4: Development of the System Specifications Work Area C: Task 1.5: Development of the Legal Framework and Partnership Model Task 1.6: Definition of supported Business Functions Task 1.7: Identification of Market (Segments) and User Groups

Description of work Work Area A: Task 1.1: Analysis of collections and items located in libraries, museums, archives, research centres, etc in a participating region. Task 1.2: Development of a documentation and digitization plan based on sound methods and standards, following best practice models. Work Area B: Task 1.3: Review of existing standards and methods relevant to REGNET Task 1.4: Definition of the Functional Requirements; development of the REGNET- Architectural Design; identification of Software Components; detailed System Design; definition of hardware, system, and network requirements; identification of tools. Work Area C: Task 1.5: Development of a legal framework; development of Partnership Models; (stakeholders at regional, national, and international levels, service providers); development of a "Virtual Enterprise Concept" Task 1.6: Analysis of existing and required business processes and business functions (including supply chains); development of a business modell regarding the marketing and procurement of digital goods with reference to following market segments: - Education - (Cultural) Tourism - Science and Research - Recreational Economics - Administration - (Multimedia) SMEs & Industries - Arts Task 1.7: Collection of available market information according to the requirements Outlined in task 1.6.

Deliverables D1: Report: "Content Creation and Content Management" D2: Report: "The REGNET - System: Specifications and State of the Art" D3: Report: "REGNET - Enterprise Engineering and Market Analysis".

Milestones and expected result M1: Review of the Analysis of the State of the Art and Development of Concepts. It is expected that: - the content providers have prepared their documentation plans and are ready for the preparation of contents - the service providers and system integrators are ready to start the preparation of the necessary infrastructure in their organisations to run a trial service and are in the position to develop the system and the services. - All partners agree to the legal framework which has to follow national and international laws; contacts have been established to potential partner organisations.