|  | List of Participants |
| --- | --- |

| Partic. Role* | Partic. no. | Participant name | Participant short name | Country | Date enter project | Date exit project |
| --- | --- | --- | --- | --- | --- | --- |
| C | 1 | Angewandte Informations-technik Forschungsgesellschaft mbH | AIT | A | Start of project | End of project |
| A | 2 | Österreichische Nationalbibliothek | ONB | A | Start of project | End of project |
| A | 3 | Salzburg Research Forschungsgesellschaft m.b.H. | SR | A | Start of project | End of project |
| P | 4 | IMAC Information & Management Consulting e.K. | IMAC | DE | Start of project | End of project |
| P | 5 | Stockholms universitet | SUL | SE | Start of project | End of project |
| A | 6 | Länsmuseet pa Gotland | LMG | SE | Start of project | End of project |
| A | 7 | Naturhistoriska riksmuseet | NRM | SE | Start of project | End of project |
| A | 8 | Kungl. Vetenskapsakademien | KVA | SE | Start of project | End of project |
| P | 9 | TARX nv | TARX | BE | Start of project | End of project |
| A | 10 | Stad Mechelen | MECH | BE | Start of project | End of project |
| A | 11 | Stichting Museon (Museum vorr het Onderwijs) | MUS | NL | Start of project | End of project |
| P | 12 | Motorola S.p.A. | MOT | I | Start of project | End of project |
| P | 13 | SPACE S.r.l. | SPAC | I | Start of project | End of project |
| P | 14 | Fratelli Alinari I.D.E.A. S.P.A. | ALI | I | Start of project | End of project |
| P | 15 | Consorzio Civita | CC | I | Start of project | End of project |
| P | 16 | Sistemas Expertos SA | SIE | ES | Start of project | End of project |
| A | 17 | Ajuntament de Granollers | GRAN | ES | Start of project | End of project |
| P | 18 | Instituto Andaluz de Tecnologia | IAT | ES | Start of project | End of project |
| P | 19 | Zeus Consulting SA | ZEUS | EL | Start of project | End of project |
| A | 20 | Systema Informatics S.A. | SI | EL | Start of project | End of project |
| A | 21 | Centre for Research and Technology Hellas | CERT | EL | Start of project | End of project |
| P | 22 | Institute of Computer and Communication Systems, Bulgarian Acadamy of Sciences | ICCS | BUL | Start of project | End of project |
| P | 23 | VALTECH | VALT | F | Start of project | End of project |
| A | 24 | Terra Incognita Europa Limited | TINC | UK | Start of project | End of project |

*C = Coordinator (or use C-F and C-S if financial and scientific coordinator roles are separate)

P - Principal contractor

A - Assistant contractor

9.7 Project management

The management structure, techniques and procedures to apply in the project have the following objectives:

- To manage and control the project's resources, schedules and activities.

- To ensure the integration of the business and software related tasks.

- To check the consistency between the developments and the strategic objectives of the partners.

- To ensure the overall quality of all systems results.

- To coordinate the REGNET-network on a European scale.

The management structure will be based on a small number of committees and members, with the objective of improving the overall flexibility and swiftness of the decision processes:

- Project Control Group (PCG). - Formed by the co-ordinator (AIT) and the Project Manager (SR). These two partners are responsible for the Administrative Procedures as well as for the Technical Management of the REGNET Project.

- Project Management Group (PMG).- Formed by the Project Control Group and five Work Area Managers (WA-A: Content Engineering (AIT); WA-B: Platform Engineering (ZEUS); WA-C: Enterprise Engineering (VALT); WA-D: Domain Management (IMAC); WA-E: Region Management (TARX)) plus two Technical Group Managers (Interface/End User Devices: MOT; Object/Catalogue Management (SI)). It will be responsible for the overall management (co-ordinating legal and ethical issues), technical management (major decisions regarding work contents, configuration & change control, QA & self-assessment), revision of internal documentation and dissemination, and relationship with EU officers and third-party organisations. PMG will join at least every 3 months.

- Extended Project Management Group (EPMG). - Formed by the PMG plus all other contractors of the REGNET Project (that means one management representative from each partner). This group convenes on the occasion of main project events (kick-off, milestones, contingency, etc). It is possible to delegate a voting right to another partner in advance and written form to the co-ordinator.

- Project Team Group (PTG). - Formed by partners working together on task level either within the development phase (I) or demonstration phase (II). These meetings - if necessary - are announced by the Work Area Managers on request by work package or task managers, who will be responsible for the organisation of meetings.

- Exploitation Committee.- Formed by one management or marketing representative from the commercial partners, and will be responsible for exploitation plan and approval of dissemination activities.  Other partners will occasionally participate in the meetings.

- Users Group.- Formed by partners acting as Content Providers or Regional Poles. Other partners can be nominated on request. It is intended to extend the group by partners external to the project to enable the growth of the network.

- Task Leaders.- Each Task will have a responsible of its specific actions (controlled by task briefs) and results. For each work package, one of the Task Leaders will also act as Workpackage Leader for common WP issues.

A Steering Committee composed by one senior representative of the partners could be settled for decisions in case of problems at lower levels. A Consortium Agreement will be signed by the partners not later than two months from the start of the project, detailing management, responsibility and exploitation issues, including intellectual property and commercialisation rights.

Quality assurance procedures

The following quality assurance procedures will be implemented:

- A project electronic repository will be accessible to the consortium members, where all common project information and shareable code of the project will be stored and updated.  The Coordinator, Project Manager and the Task Leaders will provide and maintain all information at the project, task and deliverables levels.  All project documentation will be prepared and stored in the Electronic Repository by the corresponding responsible in a common format.   All generic documents (deliverable, minutes, common reports, . . . ) will be normalised to maintain homogeneity in the project. The deliverables will be issued by the Task Leaders after a QA revision procedure, and released by the Project Manager.

- The meetings will be organised by the concerning group, committees or Task Leaders, according to the needs of the project, and will require pre-agenda and the meeting minutes, for comments and approval of the attendants.  All project milestones will produce a meeting with the EPMG and the involved Task Leaders.

- A collection of software engineering (Change Management, Configuration Management and application program interfaces standards) will be agreed in order to ensure the correct integration of the modules developed by the different partners.  A support responsible will be identified to provide the necessary support to the users.  The validation of the Designs, the Integration and Validation plans and the results of the tests are key issues of the QA, so there will need to be formally approved by the PMG.

- A document detailing contact data, responsibilities nomination and related information (e.g. escalation procedure for problem resolution) will be issued at the project kick-off meeting and maintained by the Coordinator (AIT).

Allocation of management responsibilities

Angewandte Informationstechnik Forschungsgesellschaft mbH (AIT) as Co-ordinator and responsible for the Administrative Management will delegate responsibility for the Project Management to Salzburg Research (SR). Both partners form the Project Control Group.

The Project Control Group will be responsible of the performance of the following tasks:

- Production & consolidation of periodic progress reports, and co-ordination of the project final ones. Cost statements consolidation, and financial co-ordination.

- Scheduling of project resources and surveillance of resources and work-content deviations.

- Interfacing with EC officers and external reviewers.  Co-ordination of the periodic progress reviews.

- Internal storage and dissemination of the information (communication strategy), plus any other common effort related to project co-ordination.

Each Deliverable and Task will have a Leader (TL), nominated by the corresponding partner (see part B). He/She will have technical responsibility for:

- Task specific actions and results and the adequate progress towards its functional and quality goals.

- Co-ordinate task level meetings and compile all required information from the Task participants and produce/review/approve the final Deliverables and reports for the Management Groups.

TL will define the structure and overall index of the Task deliverables, complying with the management guidelines and set up 'task briefs' which lay down the work to be done within a task.  TL will distribute the responsibilities required to adequately accomplish the Task between the participant partners considering their profile, experience and assigned manpower.

Each partner will also nominate a person (a member of the EPMG  or a Task Leader), responsible of recording and reporting the partners’ details regarding spent resources, changes in the key persons, . . .   Internal Reporting will include the management and exploitation reports produced by the PMC and the ExC, plus a Partner Monthly report including for each partner or cluster consortium:

- Partners and involved Tasks identifications

- Achievements & deliverables in the reported period

- Status of any conflict affecting the task

- Deviations & team changes from original plan

- Resources spent in the reported activity

- Technical and resources forecast for the next period

- Percentage of technical advance of each task

External Reports and Reviews

External reports will be produced by the Project Control Group and reviewed by the PMG according to the EC contract rules, including:

- The Bimonthly Management reports will include a brief summary of the internal monthly reports.

- The Progress reports  (6-month periods) will include more detailed summaries of the monthly reports, overall project status plus the cost-statement reports from each partner.

- The Final report will include summaries of all points above mentioned, plus summaries of technical works, achieved objectives and conclusions.

The Consortium will propose periodic Six-Months Review Meetings with the EU officers and external experts, but will be open to any other schedule proposed by the Commission.

To support management procedures MS-Project will be used. As far as graphical charts have to be produced the software package VISIO will be used.

Quality Assurance (QA) will be included in an own task (T7.2) and described in a separate deliverable (D14). One partner (MOT) will be responsible for this and has to work out at a QA-procedure at the beginning of the project.

The image of the overall management structure can be taken from the next figures:

The five Work Areas have clear responsibilities (Work Area Mangers). The practical work is carried out in Project Team Groups. During the development phase (dedicated to Area B) there will be 5 Team-Groups related to the five main components (building blocks, nodes; see Annex) . Each Team Group has a group leader (underlined short name). Three other team groups are dedicated to the other four work areas. One group consist of system implementers extended by developers. One group is dedicated to Enterprise engineering only. Finally one group consists of the content providers. The relation between groups and tasks are clearly defined in the work package/task description.