## Tabelle1
REGNET - Budget: 2.Draft (10.8.2000) in EURO
[8 empty] | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19 | P20 | P21 | P22 | P23 | P24 | P25 | P26
|  | Duration | Start | End | Phase | Funding | Lead | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S |  |  |  | Partner - TYPE
| Number productive hours/year (1year = 12 months) | [6 empty] | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 | 1620 |  |  |  | Number productive hours/year (1year = 12 months)
| Overhead percentage | [6 empty] | 80% | 20% | 80% | 80% | 20% | 80% | 20% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 20% | 80% | 80% | 80% | 80% |  |  |  | Overhead percentage
| Average increases per year | [35 empty] | Average increases per year | bar: S to S
| Base year for the rates: | [6 empty] | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 |  |  |  | Base year for the rates:
| Hourly Rate - Cat. 1 (eg.Scientist) | [6 empty] | 59.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 1 (eg.Scientist)
| Hourly Rate - Cat. 2 (eg.Academic) | [6 empty] | 48.45 | 29.63 | 44.45 | 44.45 | 29.63 | 29.63 | 29.63 | 29.63 | 37.04 | 29.63 | 29.63 | 29.63 | 44.45 | 37.04 | 37.04 | 44.45 | 29.63 | 37.04 | 44.45 | 37.04 | 37.04 | 14.82 | 14.82 | 44.45 | 37.04 | 44.45 |  |  |  | Hourly Rate - Cat. 2 (eg.Academic)
| Hourly Rate - Cat. 3 (eg.Technician) | [6 empty] | 36.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 3 (eg.Technician)
| Monthly Rate - Cat. 1 (eg.Scientist) | [6 empty] | 7986.6 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 6000 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 6000 | 0 | 6000 |  |  |  | Monthly Rate - Cat. 1 (eg.Scientist)
| Monthly Rate - Cat. 2 (eg.Academic) | [6 empty] | 6540.75 | 4000.05 | 6000.75 | 6000 | 4000.05 | 4000.05 | 4000.05 | 4000.05 | 5000.4 | 4000.05 | 4000.05 | 4000.05 | 6000 | 5000.4 | 5000.4 | 6000 | 4000.05 | 5000.4 | 6000 | 5000.4 | 5000.4 | 2000 | 2000 | 6000 | 5000.4 | 6000 |  |  |  | Monthly Rate - Cat. 2 (eg.Academic)
| Monthly Rate - Cat. 3 (eg.Technician) | [6 empty] | 4957.2 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 6000 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 6000 | 0 | 6000 |  |  |  | Monthly Rate - Cat. 3 (eg.Technician)
| Monthly Rate (Proposal/Average) | [6 empty] | 6000 | 4000 | 6000 | 6000 | 4000 | 4000 | 4000 | 4000 | 5000 | 4000 | 4000 | 4000 | 6000 | 5000 | 5000 | 6000 | 4000 | 5000 | 6000 | 5000 | 5000 | 2000 | 2000 | 6000 | 5000 | 6000 |  |  |  | Monthly Rate (Proposal)
| Hourly Rate (Proposal) | [6 empty] | 44.4444 | 29.6296 | 44.4444 | 44.4444 | 29.6296 | 29.6296 | 29.6296 | 29.6296 | 37.037 | 29.6296 | 29.6296 | 29.6296 | 44.4444 | 37.037 | 37.037 | 44.4444 | 29.6296 | 37.037 | 44.4444 | 37.037 | 37.037 | 14.8148 | 14.8148 | 44.4444 | 37.037 | 44.4444 |  |  |  | Hourly Rate (Proposal)
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL |  | Partner
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP1 | Analysis of the State of the Art and Development of Concepts | 6 | 1 | 6 | 1 |  | ZEUS | 15 | 1 | 6 | 10 | 2 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 9 | 1 | 2 | 8 | 1 | 5 | 15 | 8 | 6 | 7 | 2 | 18 | 5 | 11 | 144 | 144 | WP1 | Analysis of the State...
T1.1 | Def.of Content | 3 | 1 | 3 |  | 50% | IMAC | 1 | 1 |  | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 | 1 |  |  |  |  | 20 | T1.1 | Def.of Content
T1.2 | Doc&Dig.Plan | 3 | 4 | 6 |  | 50% | IMAC | AIT S: 1; IMAC S,C: 2; SUL C,B: 1; TARX C,S,B: 1; SPAC S: 1; CC C,B: 1; IAT S,B: 1; ZEUS S: 1; ICCS C,S: 1; SUSU C,S: 1 |  | 11 | T1.2 | Doc&Dig.Plan
T1.3 | Ident.of.Standards | 2 | 1 | 2 |  | 50% | IAT | AIT S: 1; SPAC S: 1; IAT S,B: 2; ZEUS S: 1; VALT S: 2; MOT S: 1 |  | 8 | T1.3 | Ident.of.Standards
T1.4.1 | Repository | 4 | 3 | 6 |  | 50% | TARX | AIT S: 1; IMAC S,C: 2; TARX C,S,B: 2; SIE S: 2; ITI C,S: 2; ICCS C,S: 2 |  | 11 | T1.4.1 | Repository
T1.4.2 | Reference System | 4 | 3 | 6 |  | 50% | AIT | AIT S: 4; SIE S: 2 |  | 6 | T1.4.2 | Reference System
T1.4.3 | Knowledge Base | 4 | 3 | 6 |  | 50% | ITI | AIT S: 2; ZEUS S: 1; SI SI: 2; ITI C,S: 4; VALT S: 2 |  | 11 | T1.4.3 | Knowledge Base
T1.4.4 | Data Generation | 4 | 3 | 6 |  | 50% | SPAC | AIT S: 2; TARX C,S,B: 2; SPAC S: 4; MOT S: 2 |  | 10 | T1.4.4 | Data Generation
T1.4.5 | Search System | 4 | 3 | 6 |  | 50% | SIE | AIT S: 1; SIE S: 4; SI SI: 2; MOT S: 2 |  | 9 | T1.4.5 | Search System
T1.4.6 | e-Business | 4 | 3 | 6 |  | 50% | ZEUS | ZEUS S: 4; VALT S: 4; MOT S: 2 |  | 10 | T1.4.6 | e-Business
T1.4.7 | Product Catalogue | 4 | 3 | 6 |  | 50% | ZEUS | ZEUS S: 2; VALT S: 2 |  | 4 | T1.4.7 | Product Catalogue
T1.4.8 | Production Process | 4 | 3 | 6 |  | 50% | TZ | TZ S: 4; SPAC S: 2 |  | 6 | T1.4.8 | Production Process
T1.4.9 | Products and Services | 4 | 3 | 6 |  | 50% | ZEUS | TZ S: 2; ZEUS S: 2 |  | 4 | T1.4.9 | Products and Services
T1.4.10 | GUI/Portals | 4 | 3 | 6 |  | 50% | MOT | ZEUS S: 2; ICCS C,S: 2; MOT S: 2 |  | 6 | T1.4.10 | GUI/Portals
T1.4.11 | Data Management | 4 | 3 | 6 |  | 50% | SI | SI SI: 4; MOT S: 2 |  | 6 | T1.4.11 | Data Management
T1.4.12 | Core System | 4 | 3 | 6 |  | 50% | VALT | ZEUS S: 1; VALT S: 4 |  | 5 | T1.4.12 | Core System
T1.4.13 | Implementation Platform | 4 | 3 | 6 |  | 50% | VALT | VALT S: 2 |  | 2 | T1.4.13 | Implementation Platform
T1.5 | Dev.of Legal FW | 3 | 4 | 6 |  | 50% | AIT | AIT S: 2; IAT S,B: 1; TINC S: 1 |  | 4 | T1.5 | Dev.of Legal FW
T1.6 | Def.of supp.Bus.Fct | 3 | 1 | 3 |  | 50% | VALT | IMAC S,C: 2; VALT S: 2; TINC S: 2 |  | 6 | T1.6 | Def.of supp.Bus.Fct
T1.7 | Ident.of.Market/User Gr. | 3 | 1 | 3 |  | 50% | TINC | IMAC S,C: 2; ICCS C,S: 1; TINC S: 2 |  | 5 | T1.7 | Ident.of.Market/User Gr.
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | S | C,S | C,S | C,S | S | S | S
WP2 | Implementation of the System and Preparation of Services and Product Generation | 6 | 7 | 12 | 1 |  | VALT | 22 | 2 | 9 | 10 | 2 | 2 | 2 | 2 | 8 | 2 | 2 | 2 | 11 | 2 | 4 | 12 | 4 | 3 | 17 | 9 | 9 | 12 | 2 | 22 | 8 | 15 | 195 | 195 | WP2 | Implementation of the....
T2.1 | Preparation of Content & Products | 6 | 7 | 12 |  | 50% | IMAC | 2 | 2 |  | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 |  | 4 | 2 |  |  |  | 4 | 2 |  |  |  |  | 43 | T2.1 | Preparation of Content & Products
T2.2.1 | Repository | 6 | 7 | 12 |  | 50% | TARX | AIT S: 3; 2 IMAC S,C: 3; 2 TARX C,S,B: 3; 2 SIE S: 3; 2 ITI C,S: 3; 1 ICCS C,S: 3 |  | 18 | T2.2.1 | Repository
T2.2.2 | Reference System | 6 | 7 | 12 |  | 50% | AIT | AIT S: 6; 2 SIE S: 3 |  | 9 | T2.2.2 | Reference System
T2.2.3 | Knowledge Base | 6 | 7 | 12 |  | 50% | ITI | AIT S: 3; 2 ZEUS S: 2; 2 SI S: 3; 2 ITI C,S: 6; 1 VALT S: 2 |  | 16 | T2.2.3 | Knowledge Base
T2.2.4 | Data Generation | 6 | 7 | 12 |  | 50% | SPAC | AIT S: 3; 2 TARX C,S,B: 3; 2 SPAC S: 6; 2 MOT S: 2 |  | 14 | T2.2.4 | Data Generation
T2.2.5 | Search System | 6 | 7 | 12 |  | 50% | SIE | AIT S: 3; 2 SIE S: 6; 2 SI S: 3; 2 MOT S: 2 |  | 14 | T2.2.5 | Search System
T2.2.6 | e-Business | 6 | 7 | 12 |  | 50% | ZEUS | 2 ZEUS S: 6; 1 VALT S: 6; 2 MOT S: 2 |  | 14 | T2.2.6 | e-Business
T2.2.7 | Product Catalogue | 6 | 7 | 12 |  | 50% | ZEUS | 2 ZEUS S: 3; 1 VALT S: 3 |  | 6 | T2.2.7 | Product Catalogue
T2.2.8 | Production Process | 6 | 7 | 12 |  | 50% | TZ | TZ S: 6; 2 SPAC S: 3 |  | 9 | T2.2.8 | Production Process
T2.2.9 | Products ans Services | 6 | 7 | 12 |  | 50% | ZEUS | TZ S: 3; 2 ZEUS S: 2 |  | 5 | T2.2.9 | Products ans Services
T2.2.10 | GUI/Portals | 6 | 7 | 12 |  | 50% | MOT | 2 ZEUS S: 3; 1 ICCS C,S: 3; 2 MOT S: 6 |  | 12 | T2.2.10 | GUI/Portals
T2.2.11 | Data Management | 6 | 7 | 12 |  | 50% | SI | 2 SI S: 3; 2 MOT S: 3 |  | 6 | T2.2.11 | Data Management
T2.2.12 | Core System | 2 | 7 | 8 |  | 50% | VALT | 2 ZEUS S: 1; 1 VALT S: 4 |  | 5 | T2.2.12 | Core System
T2.2.13 | System Integration | 2 | 11 | 12 |  | 50% | VALT | 1 VALT S: 4 |  | 4 | T2.2.13 | System Integration
T2.3 | Contracts&Partnerships | 6 | 7 | 12 |  | 50% | AIT | AIT S: 2; 2 IAT S,B: 1; 2 TINC S: 2 |  | 5 | T2.3 | Contracts&Partnerships
T2.4 | Business Process | 6 | 7 | 12 |  | 50% | VALT | 2 IMAC S,C: 2; 1 VALT S: 3; 2 TINC S: 3 |  | 8 | T2.4 | Business Process
T2.5 | Market Engineering | 6 | 7 | 12 |  | 50% | TINC | 2 IMAC S,C: 2; 1 ICCS C,S: 2; 2 TINC S: 3 |  | 7 | T2.5 | Market Engineering
| YEAR 1: WP1+WP2 | [35 empty] | YEAR 1: WP1+WP2
| PM: person months - all categories | [6 empty] | 37 | 3 | 15 | 20 | 4 | 3 | 3 | 3 | 14 | 3 | 3 | 3 | 20 | 3 | 6 | 20 | 5 | 8 | 32 | 17 | 15 | 19 | 4 | 40 | 13 | 26 |  |  |  | PM: person months - all categories
| equal: hours - all categories | [6 empty] | 4995 | 405 | 2025 | 2700 | 540 | 405 | 405 | 405 | 1890 | 405 | 405 | 405 | 2700 | 405 | 810 | 2700 | 675 | 1080 | 4320 | 2295 | 2025 | 2565 | 540 | 5400 | 1755 | 3510 |  |  |  | equal: hours - all categories
| Percentage - Cat. 1 | [6 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | Percentage - Cat. 1
| Percentage - Cat. 2 | [6 empty] | 41% | 50% | 100% | 100% | 50% | 100% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% |  |  |  | Percentage - Cat. 2
| Percentage - Cat. 3 | [6 empty] | 35% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | Percentage - Cat. 3
| Hours on Project - Cat. 1 | [6 empty] | 999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 1
| Hours on Project - Cat. 2 | [6 empty] | 2047.95 | 202.5 | 2025 | 2700 | 270 | 405 | 202.5 | 405 | 1890 | 405 | 405 | 405 | 2700 | 405 | 810 | 2700 | 675 | 1080 | 4320 | 2295 | 2025 | 1282.5 | 540 | 5400 | 1755 | 3510 |  |  |  | Hours on Project - Cat. 2
| Hours on Project - Cat. 3 | [6 empty] | 1748.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 3
| Hourly Rate - Cat. 1 | [6 empty] | 59.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 1
| Hourly Rate - Cat. 2 | [6 empty] | 48.45 | 29.63 | 44.45 | 44.45 | 29.63 | 29.63 | 29.63 | 29.63 | 37.04 | 29.63 | 29.63 | 29.63 | 44.45 | 37.04 | 37.04 | 44.45 | 29.63 | 37.04 | 44.45 | 37.04 | 37.04 | 14.82 | 14.82 | 44.45 | 37.04 | 44.45 |  |  |  | Hourly Rate - Cat. 2
| Hourly Rate - Cat. 3 | [6 empty] | 36.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 3
| Personnel costs - Cat. 1 | [6 empty] | 59100.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 1
| Personnel costs - Cat. 2 | [6 empty] | 99223.1775 | 6000.075 | 90011.25 | 120015 | 8000.1 | 12000.15 | 6000.075 | 12000.15 | 70005.6 | 12000.15 | 12000.15 | 12000.15 | 120015 | 15001.2 | 30002.4 | 120015 | 20000.25 | 40003.2 | 192024 | 85006.8 | 75006 | 19006.65 | 8002.8 | 240030 | 65005.2 | 156019.5 |  |  |  | Personnel costs - Cat. 2
| Personnel costs - Cat. 3 | [6 empty] | 64195.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 3
| Hourly overhead rate - Cat. 1 | [6 empty] | 47.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 1
| Hourly overhead rate - Cat. 2 | [6 empty] | 38.76 | 5.926 | 35.56 | 35.56 | 5.926 | 23.704 | 5.926 | 23.704 | 29.632 | 23.704 | 23.704 | 23.704 | 35.56 | 29.632 | 29.632 | 35.56 | 23.704 | 29.632 | 35.56 | 29.632 | 29.632 | 2.964 | 11.856 | 35.56 | 29.632 | 35.56 |  |  |  | Hourly overhead rate - Cat. 2
| Hourly overhead rate - Cat. 3 | [6 empty] | 29.376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 3
| Overhead costs - Cat. 1 | [6 empty] | 47280.672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 1
| Overhead costs - Cat. 2 | [6 empty] | 79378.542 | 1200.015 | 72009 | 96012 | 1600.02 | 9600.12 | 1200.015 | 9600.12 | 56004.48 | 9600.12 | 9600.12 | 9600.12 | 96012 | 12000.96 | 24001.92 | 96012 | 16000.2 | 32002.56 | 153619.2 | 68005.44 | 60004.8 | 3801.33 | 6402.24 | 192024 | 52004.16 | 124815.6 |  |  |  | Overhead costs - Cat. 2
| Overhead costs - Cat. 3 | [6 empty] | 51356.592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 3
| Total Personnel costs: | [6 empty] | 222519.7575 | 6000.075 | 90011.25 | 120015 | 8000.1 | 12000.15 | 6000.075 | 12000.15 | 70005.6 | 12000.15 | 12000.15 | 12000.15 | 120015 | 15001.2 | 30002.4 | 120015 | 20000.25 | 40003.2 | 192024 | 85006.8 | 75006 | 19006.65 | 8002.8 | 240030 | 65005.2 | 156019.5 |  | 1767690.6075 |  | Total Personnel costs:
| Total Overhead | [6 empty] | 178015.806 | 1200.015 | 72009 | 96012 | 1600.02 | 9600.12 | 1200.015 | 9600.12 | 56004.48 | 9600.12 | 9600.12 | 9600.12 | 96012 | 12000.96 | 24001.92 | 96012 | 16000.2 | 32002.56 | 153619.2 | 68005.44 | 60004.8 | 3801.33 | 6402.24 | 192024 | 52004.16 | 124815.6 |  | 1390748.346 |  | Total Overhead
| Total Personnel costs (proposal): | [6 empty] | 222000 | 12000 | 90000 | 120000 | 16000 | 12000 | 12000 | 12000 | 70000 | 12000 | 12000 | 12000 | 120000 | 15000 | 30000 | 120000 | 20000 | 40000 | 192000 | 85000 | 75000 | 38000 | 8000 | 240000 | 65000 | 156000 |  | 1806000 |  | Total Personnel costs (proposal):
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP3 | Validation and Preparation | 3 | 13 | 15 | 1 |  | IMAC | 4 | 1 | 0 | 4 | 2 | 2 | 2 | 2 | 4 | 2 | 2 | 2 | 4 | 2 | 2 | 0 | 2 | 4 | 4 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 52 | 52 | WP3 | Validation and Preparation
T3.1 | Validation of demonstrator | 3 | 13 | 15 |  | 50% | IMAC | [27 empty] | 19 | T3.1 | Validation of demonstrator | bar: AIT S to ONB C,B,S; IMAC S,C to CC C,B; GRAN C,B to ZEUS S; ICCS C,S to SUSU C,S
T3.2 | Preparation of demonstration | 3 | 13 | 15 |  | 50% | VALT | 3 |  |  | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 |  | 1 | 3 | 3 |  |  | 3 | 2 |  |  |  |  | 33 | T3.2 | Preparation of demonstration
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP4 | Demonstration | 8 | 16 | 23 | 2 |  | TARX | 4 | 3 | 1 | 4 | 4 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 5 | 3 | 5 | 1 | 3 | 4 | 5 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 77 | 77 | WP4 | Demonstration
T4.1 | Demonstration | 6 | 16 | 21 |  | 35% | TARX | 3 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 | 3 |  |  | 3 | 3 |  |  |  |  | 57 | T4.1 | Demonstration
T4.2 | System Modification | 6 | 16 | 21 |  | 35% | VALT | AIT S: 1; TZ S: 1; TARX C,S,B: 1; SPAC S: 1; SIE S: 1; ZEUS S: 1; SI SI: 1; ITI C,S: 1; VALT S: 2; TINC S: 1; MOT S: 1 |  | 12 | T4.2 | System Modification
T4.3 | Analysis | 2 | 22 | 23 |  | 35% | CC | IMAC S,C: 1; SUL C,B: 1; TARX C,S,B: 1; SPAC S: 1; CC C,B: 2; IAT S,B: 1; ZEUS S: 1 |  | 8 | T4.3 | Analysis
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP5 | Development of an exploitation plan | 18 | 7 | 24 | all |  | MOT | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 2 | 12 | 12 | WP5 | Development of an exploitation plan
T5.1 | Dev.of Exploitation Plan |  |  |  |  | 50% | MOT | AIT S: 1; 1 IMAC S,C: 1; 1 TARX C,S,B: 1; 1 SPAC S: 1; 2 CC C,B: 1; 1 IAT S,B: 1; 1 ZEUS S: 1; 1 ICCS C,S: 1; 1 VALT S: 1; 1 TINC S: 1; 1 MOT S: 2 |  | 12 | T5.1 | Dev.of Exploitation Plan
| YEAR 2: WP3+WP4+WP5 | [35 empty] | YEAR 2: WP3+WP4+WP5
| PM: person months - all categories | [6 empty] | 9 | 4 | 1 | 9 | 6 | 5 | 5 | 5 | 10 | 5 | 5 | 5 | 10 | 5 | 8 | 1 | 5 | 9 | 10 | 1 | 1 | 8 | 6 | 3 | 2 | 3 |  | 40 |  | PM: person months - all categories
| equal: hours - all categories | [6 empty] | 1215 | 540 | 135 | 1215 | 810 | 675 | 675 | 675 | 1350 | 675 | 675 | 675 | 1350 | 675 | 1080 | 135 | 675 | 1215 | 1350 | 135 | 135 | 1080 | 810 | 405 | 270 | 405 |  |  |  | equal: hours - all categories
| Percentage - Cat. 1 | [6 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | Percentage - Cat. 1
| Percentage - Cat. 2 | [6 empty] | 40% | 50% | 100% | 100% | 50% | 100% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% |  |  |  | Percentage - Cat. 2
| Percentage - Cat. 3 | [6 empty] | 33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | Percentage - Cat. 3
| Hours on Project - Cat. 1 | [6 empty] | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 1
| Hours on Project - Cat. 2 | [6 empty] | 486 | 270 | 135 | 1215 | 405 | 675 | 337.5 | 675 | 1350 | 675 | 675 | 675 | 1350 | 675 | 1080 | 135 | 675 | 1215 | 1350 | 135 | 135 | 540 | 810 | 405 | 270 | 405 |  |  |  | Hours on Project - Cat. 2
| Hours on Project - Cat. 3 | [6 empty] | 400.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 3
| Hourly Rate - Cat. 1 | [6 empty] | 60.3432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 1
| Hourly Rate - Cat. 2 | [6 empty] | 49.419 | 29.63 | 44.45 | 44.45 | 29.63 | 29.63 | 29.63 | 29.63 | 37.04 | 29.63 | 29.63 | 29.63 | 44.45 | 37.04 | 37.04 | 44.45 | 29.63 | 37.04 | 44.45 | 37.04 | 37.04 | 14.82 | 14.82 | 44.45 | 37.04 | 44.45 |  |  |  | Hourly Rate - Cat. 2
| Hourly Rate - Cat. 3 | [6 empty] | 37.4544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 3
| Personnel costs - Cat. 1 | [6 empty] | 14663.3976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 1
| Personnel costs - Cat. 2 | [6 empty] | 24017.634 | 8000.1 | 6000.75 | 54006.75 | 12000.15 | 20000.25 | 10000.125 | 20000.25 | 50004 | 20000.25 | 20000.25 | 20000.25 | 60007.5 | 25002 | 40003.2 | 6000.75 | 20000.25 | 45003.6 | 60007.5 | 5000.4 | 5000.4 | 8002.8 | 12004.2 | 18002.25 | 10000.8 | 18002.25 |  |  |  | Personnel costs - Cat. 2
| Personnel costs - Cat. 3 | [6 empty] | 15017.3417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 3
| Hourly overhead rate - Cat. 1 | [6 empty] | 48.2746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 1
| Hourly overhead rate - Cat. 2 | [6 empty] | 39.5352 | 5.926 | 35.56 | 35.56 | 5.926 | 23.704 | 5.926 | 23.704 | 29.632 | 23.704 | 23.704 | 23.704 | 35.56 | 29.632 | 29.632 | 35.56 | 23.704 | 29.632 | 35.56 | 29.632 | 29.632 | 2.964 | 11.856 | 35.56 | 29.632 | 35.56 |  |  |  | Hourly overhead rate - Cat. 2
| Hourly overhead rate - Cat. 3 | [6 empty] | 29.9635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 3
| Overhead costs - Cat. 1 | [6 empty] | 11730.7181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 1
| Overhead costs - Cat. 2 | [6 empty] | 19214.1072 | 1600.02 | 4800.6 | 43205.4 | 2400.03 | 16000.2 | 2000.025 | 16000.2 | 40003.2 | 16000.2 | 16000.2 | 16000.2 | 48006 | 20001.6 | 32002.56 | 4800.6 | 16000.2 | 36002.88 | 48006 | 4000.32 | 4000.32 | 1600.56 | 9603.36 | 14401.8 | 8000.64 | 14401.8 |  |  |  | Overhead costs - Cat. 2
| Overhead costs - Cat. 3 | [6 empty] | 12013.8733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 3
| Total Personnel costs: | [6 empty] | 53698.3733 | 8000.1 | 6000.75 | 54006.75 | 12000.15 | 20000.25 | 10000.125 | 20000.25 | 50004 | 20000.25 | 20000.25 | 20000.25 | 60007.5 | 25002 | 40003.2 | 6000.75 | 20000.25 | 45003.6 | 60007.5 | 5000.4 | 5000.4 | 8002.8 | 12004.2 | 18002.25 | 10000.8 | 18002.25 |  | 625749.3983 |  | Total Personnel costs:
| Total Overhead | [6 empty] | 42958.6986 | 1600.02 | 4800.6 | 43205.4 | 2400.03 | 16000.2 | 2000.025 | 16000.2 | 40003.2 | 16000.2 | 16000.2 | 16000.2 | 48006 | 20001.6 | 32002.56 | 4800.6 | 16000.2 | 36002.88 | 48006 | 4000.32 | 4000.32 | 1600.56 | 9603.36 | 14401.8 | 8000.64 | 14401.8 |  | 477797.6136 |  | Total Overhead
| Total Personnel costs (proposal): | [6 empty] | 54000 | 16000 | 6000 | 54000 | 24000 | 20000 | 20000 | 20000 | 50000 | 20000 | 20000 | 20000 | 60000 | 25000 | 40000 | 6000 | 20000 | 45000 | 60000 | 5000 | 5000 | 16000 | 12000 | 18000 | 10000 | 18000 |  | 664000 |  | Total Personnel costs (proposal):
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP6 | Information Dissemination | 24 | 1 | 24 | all |  | SPAC | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 12 | 12 | WP6 | Information Dissemination
T6.1 | Information Dissemination | 24 | 1 | 24 |  | 50% | SPAC | [27 empty] | 12 | T6.1 | Information Dissemnination | bar: AIT S; IMAC S,C to SUL C,B; TARX C,S,B; SPAC S; CC C,B; IAT S,B to ZEUS S; ICCS C,S; VALT S to MOT S
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP7 | Project Management | 24 | 1 | 24 | all |  | AIT | 12 | 0 | 12 | 6 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 0 | 4 | 5 | 2 | 2 | 4 | 0 | 6 | 2 | 12 | 80 | 80 | WP7 | Project Management
T7.1 | Management | 24 | 1 | 24 |  | 50% | AIT | 1 AIT S: 12; 1 TZ S: 12; 1 IMAC S,C: 6; 1 SUL C,B: 2; 1 TARX C,S,B: 4; 1 SPAC S: 4; 1 SIE S: 3; 1 IAT S,B: 4; 1 ZEUS S: 5; 1 SI SI: 2; 1 ITI C,S: 2; 1 ICCS C,S: 4; 1 VALT S: 6; 1 TINC S: 2; 1 MOT S: 4 |  | 72 | T7.1 | Management
T7.2 | Quality Assurance | 24 | 1 | 24 |  | 50% | MOT | 1 MOT S: 8 |  | 8 | T7.2 | Quality Assurance
| YEAR 1+2: WP6+WP7 (Total= 100%) | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  |  | YEAR 1+2: WP6+WP7 (Total= 100%)
| PM: person months - all categories | [6 empty] | 13 | 0 | 12 | 7 | 3 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 1 | 3 | 0 | 5 | 6 | 2 | 2 | 5 | 0 | 7 | 3 | 13 |  | 265 |  | PM: person months - all categories
| equal: hours - all categories | [6 empty] | 1755 | 0 | 1620 | 945 | 405 | 0 | 0 | 0 | 675 | 0 | 0 | 0 | 675 | 0 | 135 | 405 | 0 | 675 | 810 | 270 | 270 | 675 | 0 | 945 | 405 | 1755 |  |  |  | equal: hours - all categories
| YEAR 1: percentage of WP6+WP7: | [6 empty] | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% |  |  |  | YEAR 1: percentage of WP6+WP7:
| hours - all categories | [6 empty] | 877.5 | 0 | 810 | 472.5 | 202.5 | 0 | 0 | 0 | 337.5 | 0 | 0 | 0 | 337.5 | 0 | 67.5 | 202.5 | 0 | 337.5 | 405 | 135 | 135 | 337.5 | 0 | 472.5 | 202.5 | 877.5 |  |  |  | hours - all categories
| Percentage - Cat. 1 | [6 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | Percentage - Cat. 1
| Percentage - Cat. 2 | [6 empty] | 40% | 50% | 100% | 100% | 50% | 100% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% |  |  |  | Percentage - Cat. 2
| Percentage - Cat. 3 | [6 empty] | 35% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | Percentage - Cat. 3
| Hours on Project - Cat. 1 | [6 empty] | 175.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 1
| Hours on Project - Cat. 2 | [6 empty] | 351 | 0 | 810 | 472.5 | 101.25 | 0 | 0 | 0 | 337.5 | 0 | 0 | 0 | 337.5 | 0 | 67.5 | 202.5 | 0 | 337.5 | 405 | 135 | 135 | 168.75 | 0 | 472.5 | 202.5 | 877.5 |  |  |  | Hours on Project - Cat. 2
| Hours on Project - Cat. 3 | [6 empty] | 307.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 3
| Hourly Rate - Cat. 1 | [6 empty] | 59.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 1
| Hourly Rate - Cat. 2 | [6 empty] | 48.45 | 29.63 | 44.45 | 44.45 | 29.63 | 29.63 | 29.63 | 29.63 | 37.04 | 29.63 | 29.63 | 29.63 | 44.45 | 37.04 | 37.04 | 44.45 | 29.63 | 37.04 | 44.45 | 37.04 | 37.04 | 14.82 | 14.82 | 44.45 | 37.04 | 44.45 |  |  |  | Hourly Rate - Cat. 2
| Hourly Rate - Cat. 3 | [6 empty] | 36.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 3
| Personnel costs - Cat. 1 | [6 empty] | 10382.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 1
| Personnel costs - Cat. 2 | [6 empty] | 17005.95 | 0 | 36004.5 | 21002.625 | 3000.0375 | 0 | 0 | 0 | 12501 | 0 | 0 | 0 | 15001.875 | 0 | 2500.2 | 9001.125 | 0 | 12501 | 18002.25 | 5000.4 | 5000.4 | 2500.875 | 0 | 21002.625 | 7500.6 | 39004.875 |  |  |  | Personnel costs - Cat. 2
| Personnel costs - Cat. 3 | [6 empty] | 11277.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 3
| Hourly overhead rate - Cat. 1 | [6 empty] | 47.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 1
| Hourly overhead rate - Cat. 2 | [6 empty] | 38.76 | 5.926 | 35.56 | 35.56 | 5.926 | 23.704 | 5.926 | 23.704 | 29.632 | 23.704 | 23.704 | 23.704 | 35.56 | 29.632 | 29.632 | 35.56 | 23.704 | 29.632 | 35.56 | 29.632 | 29.632 | 2.964 | 11.856 | 35.56 | 29.632 | 35.56 |  |  |  | Hourly overhead rate - Cat. 2
| Hourly overhead rate - Cat. 3 | [6 empty] | 29.376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 3
| Overhead costs - Cat. 1 | [6 empty] | 8306.064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 1
| Overhead costs - Cat. 2 | [6 empty] | 13604.76 | 0 | 28803.6 | 16802.1 | 600.0075 | 0 | 0 | 0 | 10000.8 | 0 | 0 | 0 | 12001.5 | 0 | 2000.16 | 7200.9 | 0 | 10000.8 | 14401.8 | 4000.32 | 4000.32 | 500.175 | 0 | 16802.1 | 6000.48 | 31203.9 |  |  |  | Overhead costs - Cat. 2
| Overhead costs - Cat. 3 | [6 empty] | 9022.104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 3
| Total Personnel costs: | [6 empty] | 38666.16 | 0 | 36004.5 | 21002.625 | 3000.0375 | 0 | 0 | 0 | 12501 | 0 | 0 | 0 | 15001.875 | 0 | 2500.2 | 9001.125 | 0 | 12501 | 18002.25 | 5000.4 | 5000.4 | 2500.875 | 0 | 21002.625 | 7500.6 | 39004.875 |  | 248190.5475 |  | Total Personnel costs:
| Total Overhead | [6 empty] | 30932.928 | 0 | 28803.6 | 16802.1 | 600.0075 | 0 | 0 | 0 | 10000.8 | 0 | 0 | 0 | 12001.5 | 0 | 2000.16 | 7200.9 | 0 | 10000.8 | 14401.8 | 4000.32 | 4000.32 | 500.175 | 0 | 16802.1 | 6000.48 | 31203.9 |  | 195251.8905 |  | Total Overhead
| Total Personnel costs (proposal): | [6 empty] | 39000 | 0 | 36000 | 21000 | 6000 | 0 | 0 | 0 | 12500 | 0 | 0 | 0 | 15000 | 0 | 2500 | 9000 | 0 | 12500 | 18000 | 5000 | 5000 | 5000 | 0 | 21000 | 7500 | 39000 |  | 254000 |  | Total Personnel costs (proposal):
| YEAR 2: percentage of WP6+WP7: | [6 empty] | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% |  |  |  | YEAR 2: percentage of WP6+WP7:
| hours - all categories | [6 empty] | 877.5 | 0 | 810 | 472.5 | 202.5 | 0 | 0 | 0 | 337.5 | 0 | 0 | 0 | 337.5 | 0 | 67.5 | 202.5 | 0 | 337.5 | 405 | 135 | 135 | 337.5 | 0 | 472.5 | 202.5 | 877.5 |  |  |  | hours - all categories
| Percentage - Cat. 1 | [6 empty] | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | Percentage - Cat. 1
| Percentage - Cat. 2 | [6 empty] | 40% | 50% | 100% | 100% | 25% | 100% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% |  |  |  | Percentage - Cat. 2
| Percentage - Cat. 3 | [6 empty] | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | Percentage - Cat. 3
| Hours on Project - Cat. 1 | [6 empty] | 175.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 1
| Hours on Project - Cat. 2 | [6 empty] | 351 | 0 | 810 | 472.5 | 50.625 | 0 | 0 | 0 | 337.5 | 0 | 0 | 0 | 337.5 | 0 | 67.5 | 202.5 | 0 | 337.5 | 405 | 135 | 135 | 168.75 | 0 | 472.5 | 202.5 | 877.5 |  |  |  | Hours on Project - Cat. 2
| Hours on Project - Cat. 3 | [6 empty] | 298.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 3
| Hourly Rate - Cat. 1 | [6 empty] | 60.3432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 1
| Hourly Rate - Cat. 2 | [6 empty] | 49.419 | 29.63 | 44.45 | 44.45 | 29.63 | 29.63 | 29.63 | 29.63 | 37.04 | 29.63 | 29.63 | 29.63 | 44.45 | 37.04 | 37.04 | 44.45 | 29.63 | 37.04 | 44.45 | 37.04 | 37.04 | 14.82 | 14.82 | 44.45 | 37.04 | 44.45 |  |  |  | Hourly Rate - Cat. 2
| Hourly Rate - Cat. 3 | [6 empty] | 37.4544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 3
| Personnel costs - Cat. 1 | [6 empty] | 10590.2316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 1
| Personnel costs - Cat. 2 | [6 empty] | 17346.069 | 0 | 36004.5 | 21002.625 | 1500.0187 | 0 | 0 | 0 | 12501 | 0 | 0 | 0 | 15001.875 | 0 | 2500.2 | 9001.125 | 0 | 12501 | 18002.25 | 5000.4 | 5000.4 | 2500.875 | 0 | 21002.625 | 7500.6 | 39004.875 |  |  |  | Personnel costs - Cat. 2
| Personnel costs - Cat. 3 | [6 empty] | 11174.5202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 3
| Hourly overhead rate - Cat. 1 | [6 empty] | 48.2746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 1
| Hourly overhead rate - Cat. 2 | [6 empty] | 39.5352 | 5.926 | 35.56 | 35.56 | 5.926 | 23.704 | 5.926 | 23.704 | 29.632 | 23.704 | 23.704 | 23.704 | 35.56 | 29.632 | 29.632 | 35.56 | 23.704 | 29.632 | 35.56 | 29.632 | 29.632 | 2.964 | 11.856 | 35.56 | 29.632 | 35.56 |  |  |  | Hourly overhead rate - Cat. 2
| Hourly overhead rate - Cat. 3 | [6 empty] | 29.9635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 3
| Overhead costs - Cat. 1 | [6 empty] | 8472.1853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 1
| Overhead costs - Cat. 2 | [6 empty] | 13876.8552 | 0 | 28803.6 | 16802.1 | 300.0038 | 0 | 0 | 0 | 10000.8 | 0 | 0 | 0 | 12001.5 | 0 | 2000.16 | 7200.9 | 0 | 10000.8 | 14401.8 | 4000.32 | 4000.32 | 500.175 | 0 | 16802.1 | 6000.48 | 31203.9 |  |  |  | Overhead costs - Cat. 2
| Overhead costs - Cat. 3 | [6 empty] | 8939.6162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 3
| Total Personnel costs: | [6 empty] | 39110.8208 | 0 | 36004.5 | 21002.625 | 1500.0187 | 0 | 0 | 0 | 12501 | 0 | 0 | 0 | 15001.875 | 0 | 2500.2 | 9001.125 | 0 | 12501 | 18002.25 | 5000.4 | 5000.4 | 2500.875 | 0 | 21002.625 | 7500.6 | 39004.875 |  | 247135.1896 |  | Total Personnel costs:
| Total Overhead | [6 empty] | 31288.6567 | 0 | 28803.6 | 16802.1 | 300.0038 | 0 | 0 | 0 | 10000.8 | 0 | 0 | 0 | 12001.5 | 0 | 2000.16 | 7200.9 | 0 | 10000.8 | 14401.8 | 4000.32 | 4000.32 | 500.175 | 0 | 16802.1 | 6000.48 | 31203.9 |  | 195307.6154 |  | Total Overhead
| Total Personnel costs (proposal): | [6 empty] | 39000 | 0 | 36000 | 21000 | 6000 | 0 | 0 | 0 | 12500 | 0 | 0 | 0 | 15000 | 0 | 2500 | 9000 | 0 | 12500 | 18000 | 5000 | 5000 | 5000 | 0 | 21000 | 7500 | 39000 |  | 254000 |  | Total Personnel costs (proposal):
A8.2 Participant Profile/Information - Personnel costs/overhead
| Personnel Costs Year 1 | [35 empty] | Personnel Costs Year 1
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
| Hours on Project - Cat. 1 | [6 empty] | 1174.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 1
| Hours on Project - Cat. 2 | [6 empty] | 2398.95 | 202.5 | 2835 | 3172.5 | 371.25 | 405 | 202.5 | 405 | 2227.5 | 405 | 405 | 405 | 3037.5 | 405 | 877.5 | 2902.5 | 675 | 1417.5 | 4725 | 2430 | 2160 | 1451.25 | 540 | 5872.5 | 1957.5 | 4387.5 |  |  |  | Hours on Project - Cat. 2
| Hours on Project - Cat. 3 | [6 empty] | 2055.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 3
| Hourly Rate - Cat. 1 | [6 empty] | 59.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 1
| Hourly Rate - Cat. 2 | [6 empty] | 48.45 | 29.63 | 44.45 | 44.45 | 29.63 | 29.63 | 29.63 | 29.63 | 37.04 | 29.63 | 29.63 | 29.63 | 44.45 | 37.04 | 37.04 | 44.45 | 29.63 | 37.04 | 44.45 | 37.04 | 37.04 | 14.82 | 14.82 | 44.45 | 37.04 | 44.45 |  |  |  | Hourly Rate - Cat. 2
| Hourly Rate - Cat. 3 | [6 empty] | 36.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 3
| Personnel costs - Cat. 1 | [6 empty] | 69483.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 1
| Personnel costs - Cat. 2 | [6 empty] | 116229.1275 | 6000.075 | 126015.75 | 141017.625 | 11000.1375 | 12000.15 | 6000.075 | 12000.15 | 82506.6 | 12000.15 | 12000.15 | 12000.15 | 135016.875 | 15001.2 | 32502.6 | 129016.125 | 20000.25 | 52504.2 | 210026.25 | 90007.2 | 80006.4 | 21507.525 | 8002.8 | 261032.625 | 72505.8 | 195024.375 |  |  |  | Personnel costs - Cat. 2
| Personnel costs - Cat. 3 | [6 empty] | 75473.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 3
| Hourly overhead rate - Cat. 1 | [6 empty] | 47.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 1
| Hourly overhead rate - Cat. 2 | [6 empty] | 38.76 | 5.926 | 35.56 | 35.56 | 5.926 | 23.704 | 5.926 | 23.704 | 29.632 | 23.704 | 23.704 | 23.704 | 35.56 | 29.632 | 29.632 | 35.56 | 23.704 | 29.632 | 35.56 | 29.632 | 29.632 | 2.964 | 11.856 | 35.56 | 29.632 | 35.56 |  |  |  | Hourly overhead rate - Cat. 2
| Hourly overhead rate - Cat. 3 | [6 empty] | 29.376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 3
| Overhead costs - Cat. 1 | [6 empty] | 55586.736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 1
| Overhead costs - Cat. 2 | [6 empty] | 92983.302 | 1200.015 | 100812.6 | 112814.1 | 2200.0275 | 9600.12 | 1200.015 | 9600.12 | 66005.28 | 9600.12 | 9600.12 | 9600.12 | 108013.5 | 12000.96 | 26002.08 | 103212.9 | 16000.2 | 42003.36 | 168021 | 72005.76 | 64005.12 | 4301.505 | 6402.24 | 208826.1 | 58004.64 | 156019.5 |  |  |  | Overhead costs - Cat. 2
| Overhead costs - Cat. 3 | [6 empty] | 60378.696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 3
| Total Personnel costs: | [6 empty] | 261185.9175 | 6000.075 | 126015.75 | 141017.625 | 11000.1375 | 12000.15 | 6000.075 | 12000.15 | 82506.6 | 12000.15 | 12000.15 | 12000.15 | 135016.875 | 15001.2 | 32502.6 | 129016.125 | 20000.25 | 52504.2 | 210026.25 | 90007.2 | 80006.4 | 21507.525 | 8002.8 | 261032.625 | 72505.8 | 195024.375 |  | 2015881.155 |  | Total Personnel costs:
| Total Overhead | [6 empty] | 208948.734 | 1200.015 | 100812.6 | 112814.1 | 2200.0275 | 9600.12 | 1200.015 | 9600.12 | 66005.28 | 9600.12 | 9600.12 | 9600.12 | 108013.5 | 12000.96 | 26002.08 | 103212.9 | 16000.2 | 42003.36 | 168021 | 72005.76 | 64005.12 | 4301.505 | 6402.24 | 208826.1 | 58004.64 | 156019.5 |  | 1586000.2365 |  | Total Overhead
| Personnel Costs Year 2 | [35 empty] | Personnel Costs Year 2
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
| Hours on Project - Cat. 1 | [6 empty] | 418.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 1
| Hours on Project - Cat. 2 | [6 empty] | 837 | 270 | 945 | 1687.5 | 455.625 | 675 | 337.5 | 675 | 1687.5 | 675 | 675 | 675 | 1687.5 | 675 | 1147.5 | 337.5 | 675 | 1552.5 | 1755 | 270 | 270 | 708.75 | 810 | 877.5 | 472.5 | 1282.5 |  |  |  | Hours on Project - Cat. 2
| Hours on Project - Cat. 3 | [6 empty] | 699.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 3
| Hourly Rate - Cat. 1 | [6 empty] | 60.3432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 1
| Hourly Rate - Cat. 2 | [6 empty] | 49.419 | 29.63 | 44.45 | 44.45 | 29.63 | 29.63 | 29.63 | 29.63 | 37.04 | 29.63 | 29.63 | 29.63 | 44.45 | 37.04 | 37.04 | 44.45 | 29.63 | 37.04 | 44.45 | 37.04 | 37.04 | 14.82 | 14.82 | 44.45 | 37.04 | 44.45 |  |  |  | Hourly Rate - Cat. 2
| Hourly Rate - Cat. 3 | [6 empty] | 37.4544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly Rate - Cat. 3
| Personnel costs - Cat. 1 | [6 empty] | 25253.6292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 1
| Personnel costs - Cat. 2 | [6 empty] | 41363.703 | 8000.1 | 42005.25 | 75009.375 | 13500.1688 | 20000.25 | 10000.125 | 20000.25 | 62505 | 20000.25 | 20000.25 | 20000.25 | 75009.375 | 25002 | 42503.4 | 15001.875 | 20000.25 | 57504.6 | 78009.75 | 10000.8 | 10000.8 | 10503.675 | 12004.2 | 39004.875 | 17501.4 | 57007.125 |  |  |  | Personnel costs - Cat. 2
| Personnel costs - Cat. 3 | [6 empty] | 26191.8619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 3
| Hourly overhead rate - Cat. 1 | [6 empty] | 48.2746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 1
| Hourly overhead rate - Cat. 2 | [6 empty] | 39.5352 | 5.926 | 35.56 | 35.56 | 5.926 | 23.704 | 5.926 | 23.704 | 29.632 | 23.704 | 23.704 | 23.704 | 35.56 | 29.632 | 29.632 | 35.56 | 23.704 | 29.632 | 35.56 | 29.632 | 29.632 | 2.964 | 11.856 | 35.56 | 29.632 | 35.56 |  |  |  | Hourly overhead rate - Cat. 2
| Hourly overhead rate - Cat. 3 | [6 empty] | 29.9635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hourly overhead rate - Cat. 3
| Overhead costs - Cat. 1 | [6 empty] | 20202.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 1
| Overhead costs - Cat. 2 | [6 empty] | 33090.9624 | 1600.02 | 33604.2 | 60007.5 | 2700.0338 | 16000.2 | 2000.025 | 16000.2 | 50004 | 16000.2 | 16000.2 | 16000.2 | 60007.5 | 20001.6 | 34002.72 | 12001.5 | 16000.2 | 46003.68 | 62407.8 | 8000.64 | 8000.64 | 2100.735 | 9603.36 | 31203.9 | 14001.12 | 45605.7 |  |  |  | Overhead costs - Cat. 2
| Overhead costs - Cat. 3 | [6 empty] | 20953.4895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 3
| Total Personnel costs: | [6 empty] | 92809.1941 | 8000.1 | 42005.25 | 75009.375 | 13500.1688 | 20000.25 | 10000.125 | 20000.25 | 62505 | 20000.25 | 20000.25 | 20000.25 | 75009.375 | 25002 | 42503.4 | 15001.875 | 20000.25 | 57504.6 | 78009.75 | 10000.8 | 10000.8 | 10503.675 | 12004.2 | 39004.875 | 17501.4 | 57007.125 |  | 872884.5879 |  | Total Personnel costs:
| Total Overhead | [6 empty] | 74247.3553 | 1600.02 | 33604.2 | 60007.5 | 2700.0338 | 16000.2 | 2000.025 | 16000.2 | 50004 | 16000.2 | 16000.2 | 16000.2 | 60007.5 | 20001.6 | 34002.72 | 12001.5 | 16000.2 | 46003.68 | 62407.8 | 8000.64 | 8000.64 | 2100.735 | 9603.36 | 31203.9 | 14001.12 | 45605.7 |  | 673105.229 |  | Total Overhead
| PROPOSAL | [35 empty] | PROPOSAL
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
| Total PM | [6 empty] | 59 | 7 | 28 | 36 | 13 | 8 | 8 | 8 | 29 | 8 | 8 | 8 | 35 | 8 | 15 | 24 | 10 | 22 | 48 | 20 | 18 | 32 | 10 | 50 | 18 | 42 |  | 572 |  | Total PM
| Total Personnel Cost (Propsal) | [6 empty] | 354000 | 28000 | 168000 | 216000 | 52000 | 32000 | 32000 | 32000 | 145000 | 32000 | 32000 | 32000 | 210000 | 40000 | 75000 | 144000 | 40000 | 110000 | 288000 | 100000 | 90000 | 64000 | 20000 | 300000 | 90000 | 252000 |  | 2978000 |  | Total Personnel Cost
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
| Durable Equipment | [33 empty] | 0 |  | Durable Equipment
| Consumables | [6 empty] | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 |  | 78000 |  | Consumables
| Travel and Subsistence | [6 empty] | 16000 | 6000 | 6000 | 6000 | 2000 | 2000 | 2000 | 2000 | 6000 | 2000 | 2000 | 2000 | 6000 | 2000 | 2000 | 10000 | 2000 | 2000 | 6000 | 2000 | 2000 | 6000 | 2000 | 10000 | 6000 | 10000 |  | 122000 |  | Travel and Subsistence
| Computing | [6 empty] | TARX C,S,B: 10000 |  | 10000 |  | Computing
| Subcontracting | [33 empty] | 0 |  | Subcontracting
| Other Specific project costs | [33 empty] | 0 |  | Other Specific project costs
| Protection of knowledge | [33 empty] | 0 |  | Protection of knowledge
| Overhead - % | [6 empty] | 80% | 20% | 80% | 80% | 20% | 80% | 20% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 20% | 80% | 80% | 80% | 80% |  |  |  | Overhead - %
| Overhead Costs | [6 empty] | 283200 | 5600 | 134400 | 172800 | 10400 | 25600 | 6400 | 25600 | 116000 | 25600 | 25600 | 25600 | 168000 | 32000 | 60000 | 115200 | 32000 | 88000 | 230400 | 80000 | 72000 | 12800 | 16000 | 240000 | 72000 | 201600 |  | 2276800 |  | Overhead Costs
| Total Costs | [6 empty] | 656200 | 42600 | 311400 | 397800 | 67400 | 62600 | 43400 | 62600 | 280000 | 62600 | 62600 | 62600 | 387000 | 77000 | 140000 | 272200 | 77000 | 203000 | 527400 | 185000 | 167000 | 85800 | 41000 | 553000 | 171000 | 466600 |  | 5464800 |  | Total Costs
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| % Requested from EU | [6 empty] | 49.45% | 45.77% | 49.71% | 49.1% | 46.44% | 47.12% | 45.85% | 47.12% | 48.66% | 47.12% | 47.12% | 47.12% | 48.84% | 47.08% | 47.32% | 49.67% | 47.66% | 48.52% | 49.15% | 49.59% | 49.55% | 48.95% | 47.8% | 49.67% | 49.56% | 49.81% |  | 49.01% |  | % Requested from EU
| Requested contribution from EU | [6 empty] | 324500 | 19500 | 154800 | 195300 | 31300 | 29500 | 19900 | 29500 | 136250 | 29500 | 29500 | 29500 | 189000 | 36250 | 66250 | 135200 | 36700 | 98500 | 259200 | 91750 | 82750 | 42000 | 19600 | 274700 | 84750 | 232400 |  | 2678100 |  | Requested contribution from EU
| CONTRACT | [35 empty] | CONTRACT
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL |  | Partner
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S |  |  |  | Partner - TYPE
| Hours on Project - Cat. 1 | [6 empty] | 1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 1
| Hours on Project - Cat. 2 | [6 empty] | 3235.95 | 472.5 | 3780 | 4860 | 826.875 | 1080 | 540 | 1080 | 3915 | 1080 | 1080 | 1080 | 4725 | 1080 | 2025 | 3240 | 1350 | 2970 | 6480 | 2700 | 2430 | 2160 | 1350 | 6750 | 2430 | 5670 |  |  |  | Hours on Project - Cat. 2
| Hours on Project - Cat. 3 | [6 empty] | 2754.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hours on Project - Cat. 3
| Total Hours (all Cat.) | [6 empty] | 7583.625 | 472.5 | 3780 | 4860 | 826.875 | 1080 | 540 | 1080 | 3915 | 1080 | 1080 | 1080 | 4725 | 1080 | 2025 | 3240 | 1350 | 2970 | 6480 | 2700 | 2430 | 2160 | 1350 | 6750 | 2430 | 5670 |  | 72738 |  | Total Hours (all Cat.)
| Total PM (All Cat.) | [6 empty] | 56.175 | 3.5 | 28 | 36 | 6.125 | 8 | 4 | 8 | 29 | 8 | 8 | 8 | 35 | 8 | 15 | 24 | 10 | 22 | 48 | 20 | 18 | 16 | 10 | 50 | 18 | 42 |  | 538.8 |  | Total PM (All Cat.)
| Personnel costs - Cat. 1 | [6 empty] | 94737.0492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 1
| Personnel costs - Cat. 2 | [6 empty] | 157592.8305 | 14000.175 | 168021 | 216027 | 24500.3063 | 32000.4 | 16000.2 | 32000.4 | 145011.6 | 32000.4 | 32000.4 | 32000.4 | 210026.25 | 40003.2 | 75006 | 144018 | 40000.5 | 110008.8 | 288036 | 100008 | 90007.2 | 32011.2 | 20007 | 300037.5 | 90007.2 | 252031.5 |  |  |  | Personnel costs - Cat. 2
| Personnel costs - Cat. 3 | [6 empty] | 101665.2319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Personnel costs - Cat. 3
| Total Personnel costs (All Cat.): | [6 empty] | 353995.1116 | 14000.175 | 168021 | 216027 | 24500.3063 | 32000.4 | 16000.2 | 32000.4 | 145011.6 | 32000.4 | 32000.4 | 32000.4 | 210026.25 | 40003.2 | 75006 | 144018 | 40000.5 | 110008.8 | 288036 | 100008 | 90007.2 | 32011.2 | 20007 | 300037.5 | 90007.2 | 252031.5 |  | 2888765.7429 |  | Total Personnel costs (All Cat.):
| Overhead costs - Cat. 1 | [6 empty] | 75789.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 1
| Overhead costs - Cat. 2 | [6 empty] | 126074.2644 | 2800.035 | 134416.8 | 172821.6 | 4900.0612 | 25600.32 | 3200.04 | 25600.32 | 116009.28 | 25600.32 | 25600.32 | 25600.32 | 168021 | 32002.56 | 60004.8 | 115214.4 | 32000.4 | 88007.04 | 230428.8 | 80006.4 | 72005.76 | 6402.24 | 16005.6 | 240030 | 72005.76 | 201625.2 |  |  |  | Overhead costs - Cat. 2
| Overhead costs - Cat. 3 | [6 empty] | 81332.1855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Overhead costs - Cat. 3
| Total Overhead costs (All Cat.) | [6 empty] | 283196.0893 | 2800.035 | 134416.8 | 172821.6 | 4900.0612 | 25600.32 | 3200.04 | 25600.32 | 116009.28 | 25600.32 | 25600.32 | 25600.32 | 168021 | 32002.56 | 60004.8 | 115214.4 | 32000.4 | 88007.04 | 230428.8 | 80006.4 | 72005.76 | 6402.24 | 16005.6 | 240030 | 72005.76 | 201625.2 |  | 2259105.4655 |  | Total Overhead costs (All Cat.)
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
| Durable Equipment | [33 empty] | 0 |  | Durable Equipment
| Consumables | [6 empty] | 3000 | 0 | 3000 | 3000 | 0 | 3000 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 3000 | 3000 | 3000 | 3000 |  | 66000 |  | Consumables
| Travel and Subsistence | [6 empty] | 16000 | 2796 | 6000 | 6000 | 1604 | 2000 | 764 | 2000 | 6000 | 2000 | 2000 | 2000 | 6000 | 2000 | 2000 | 10000 | 2000 | 2000 | 6000 | 2000 | 2000 | 3629 | 2000 | 10000 | 6000 | 10000 |  | 114793 |  | Travel and Subsistence
| Computing | [6 empty] | TARX C,S,B: 10000 |  | 10000 |  | Computing
| Subcontracting | [33 empty] | 0 |  | Subcontracting
| Other Specific project costs | [33 empty] | 0 |  | Other Specific project costs
| Protection of knowledge | [33 empty] | 0 |  | Protection of knowledge
| Overhead Costs | [6 empty] | 283196.0893 | 2800.035 | 134416.8 | 172821.6 | 4900.0612 | 25600.32 | 3200.04 | 25600.32 | 116009.28 | 25600.32 | 25600.32 | 25600.32 | 168021 | 32002.56 | 60004.8 | 115214.4 | 32000.4 | 88007.04 | 230428.8 | 80006.4 | 72005.76 | 6402.24 | 16005.6 | 240030 | 72005.76 | 201625.2 |  | 2259105.4655 |  | Overhead Costs
| Non-Personnel costs | [6 empty] | 302196.0893 | 5596.035 | 143416.8 | 181821.6 | 6504.0612 | 30600.32 | 3964.04 | 30600.32 | 135009.28 | 30600.32 | 30600.32 | 30600.32 | 177021 | 37002.56 | 65004.8 | 128214.4 | 37000.4 | 93007.04 | 239428.8 | 85006.4 | 77005.76 | 10031.24 | 21005.6 | 253030 | 81005.76 | 214625.2 | 0 | 2449898.4655 |  | Non-Personnel costs
| Personnel costs | [6 empty] | 353995.1116 | 14000.175 | 168021 | 216027 | 24500.3063 | 32000.4 | 16000.2 | 32000.4 | 145011.6 | 32000.4 | 32000.4 | 32000.4 | 210026.25 | 40003.2 | 75006 | 144018 | 40000.5 | 110008.8 | 288036 | 100008 | 90007.2 | 32011.2 | 20007 | 300037.5 | 90007.2 | 252031.5 | 0 | 2888765.7429 |  | Personnel costs
| Total Costs | [6 empty] | 656191.2009 | 19596.21 | 311437.8 | 397848.6 | 31004.3675 | 62600.72 | 19964.24 | 62600.72 | 280020.88 | 62600.72 | 62600.72 | 62600.72 | 387047.25 | 77005.76 | 140010.8 | 272232.4 | 77000.9 | 203015.84 | 527464.8 | 185014.4 | 167012.96 | 42042.44 | 41012.6 | 553067.5 | 171012.96 | 466656.7 | 0 | 5338664.2084 |  | Total Costs
| FUNDING | [35 empty] | FUNDING
Calculated figures
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
| A) Non-Personnel costs | [6 empty] | 302196.0893 | 5596.035 | 143416.8 | 181821.6 | 6504.0612 | 30600.32 | 3964.04 | 30600.32 | 135009.28 | 30600.32 | 30600.32 | 30600.32 | 177021 | 37002.56 | 65004.8 | 128214.4 | 37000.4 | 93007.04 | 239428.8 | 85006.4 | 77005.76 | 10031.24 | 21005.6 | 253030 | 81005.76 | 214625.2 |  | 2449898.4655 |  | A) Non-Personnel costs
| Person Months (total) | [6 empty] | 56.175 | 3.5 | 28 | 36 | 6.125 | 8 | 4 | 8 | 29 | 8 | 8 | 8 | 35 | 8 | 15 | 24 | 10 | 22 | 48 | 20 | 18 | 16 | 10 | 50 | 18 | 42 |  | 538.8 |  | Person Months (total)
| Person Months (Non-Demonstration = 50% Funding) | [6 empty] | 52.175 | 0.5 | 27 | 32 | 2.125 | 5 | 1 | 5 | 24 | 5 | 5 | 5 | 30 | 5 | 10 | 23 | 7 | 18 | 43 | 19 | 17 | 13 | 7 | 48 | 17 | 41 |  | 461.8 |  | Person Months (Non-Demonstration = 50% Funding)
| Person Months (Demonstration/WP4 = 35% Funding) | [6 empty] | 4 | 3 | 1 | 4 | 4 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 5 | 3 | 5 | 1 | 3 | 4 | 5 | 1 | 1 | 3 | 3 | 2 | 1 | 1 |  | 77 |  | Person Months (Demonstration/WP4 = 35% Funding)
| Faktor (PM-Demonstration Phase/PM-total) | [6 empty] | 0.071206 | 0.85714 | 0.035714 | 0.11111 | 0.65306 | 0.375 | 0.75 | 0.375 | 0.17241 | 0.375 | 0.375 | 0.375 | 0.14286 | 0.375 | 0.33333 | 0.041667 | 0.3 | 0.18182 | 0.10417 | 0.05 | 0.055556 | 0.1875 | 0.3 | 0.04 | 0.055556 | 0.02381 |  | 0.14291 |  | Faktor (PM-Demonstration Phase/PM-total)
| B) Personnel costs (total) | [6 empty] | 353995.1116 | 14000.175 | 168021 | 216027 | 24500.3063 | 32000.4 | 16000.2 | 32000.4 | 145011.6 | 32000.4 | 32000.4 | 32000.4 | 210026.25 | 40003.2 | 75006 | 144018 | 40000.5 | 110008.8 | 288036 | 100008 | 90007.2 | 32011.2 | 20007 | 300037.5 | 90007.2 | 252031.5 |  | 2888765.7429 |  | B) Personnel costs (total)
| B1) Personnel costs (at 50% funding level) | [6 empty] | 328788.5171 | 2000.025 | 162020.25 | 192024 | 8500.1063 | 20000.25 | 4000.05 | 20000.25 | 120009.6 | 20000.25 | 20000.25 | 20000.25 | 180022.5 | 25002 | 50004 | 138017.25 | 28000.35 | 90007.2 | 258032.25 | 95007.6 | 85006.8 | 26009.1 | 14004.9 | 288036 | 85006.8 | 246030.75 |  | 2525531.2984 |  | B1) Personnel costs (at 50% funding level)
| B2) Personnel costs (at 35% funding level) | [6 empty] | 25206.5945 | 12000.15 | 6000.75 | 24003 | 16000.2 | 12000.15 | 12000.15 | 12000.15 | 25002 | 12000.15 | 12000.15 | 12000.15 | 30003.75 | 15001.2 | 25002 | 6000.75 | 12000.15 | 20001.6 | 30003.75 | 5000.4 | 5000.4 | 6002.1 | 6002.1 | 12001.5 | 5000.4 | 6000.75 |  | 363234.4445 |  | B2) Personnel costs (at 35% funding level)
| Calculated funding = 50%A + 50%B1 + 35%B2 | [6 empty] | 324314.6113 | 19596.21 | 154818.7875 | 195323.85 | 31004.3675 | 29500.3375 | 19964.24 | 29500.3375 | 136260.14 | 29500.3375 | 29500.3375 | 29500.3375 | 189023.0625 | 36252.7 | 66255.1 | 135216.0875 | 36700.4275 | 98507.68 | 259231.8375 | 91757.14 | 82756.42 | 42042.44 | 19605.985 | 274733.525 | 84756.42 | 232428.2375 |  | 2678050.9563 |  | Calculated funding = 50%A + 50%B1 + 35%B2
| Total Costs | [6 empty] | 656191.2009 | 19596.21 | 311437.8 | 397848.6 | 31004.3675 | 62600.72 | 19964.24 | 62600.72 | 280020.88 | 62600.72 | 62600.72 | 62600.72 | 387047.25 | 77005.76 | 140010.8 | 272232.4 | 77000.9 | 203015.84 | 527464.8 | 185014.4 | 167012.96 | 42042.44 | 41012.6 | 553067.5 | 171012.96 | 466656.7 |  | 5338664.2084 |  | Total Costs
| Percentage | [6 empty] | 49.42% | 100% | 49.71% | 49.1% | 100% | 47.12% | 100% | 47.12% | 48.66% | 47.12% | 47.12% | 47.12% | 48.84% | 47.08% | 47.32% | 49.67% | 47.66% | 48.52% | 49.15% | 49.59% | 49.55% | 100% | 47.8% | 49.67% | 49.56% | 49.81% |  | 50.16% |  | Percentage
| Evaluation Summary Report figures | [35 empty] | Evaluation Summary Report figures
| Cost | [6 empty] | 656200 | 42600 | 311400 | 397800 | 67400 | 62600 | 43400 | 62600 | 280000 | 62600 | 62600 | 62600 | 387000 | 77000 | 140000 | 272200 | 77000 | 203000 | 527400 | 185000 | 167000 | 85800 | 41000 | 553000 | 171000 | 466600 |  | 5464800 |  | Cost
| Funding | [6 empty] | 321538 | 19596 | 155700 | 198900 | 31004 | 29422 | 19964 | 29422 | 137200 | 29422 | 29422 | 29422 | 189630 | 36190 | 65800 | 136100 | 36960 | 99470 | 258426 | 92500 | 83500 | 42042 | 19680 | 276500 | 85500 | 233300 |  | 2686610 |  | Funding
| Contract figures | [35 empty] | Contract figures
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL |  | Partner
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S |  |  |  | Partner - TYPE
| Cost Modell | [35 empty] | Cost Modell | bar: AIT S to MOT S
| Calculated Costs | [6 empty] | 656191.2009 | 19596.21 | 311437.8 | 397848.6 | 31004.3675 | 62600.72 | 19964.24 | 62600.72 | 280020.88 | 62600.72 | 62600.72 | 62600.72 | 387047.25 | 77005.76 | 140010.8 | 272232.4 | 77000.9 | 203015.84 | 527464.8 | 185014.4 | 167012.96 | 42042.44 | 41012.6 | 553067.5 | 171012.96 | 466656.7 |  | 5338664.2084 |  | Calculated Costs
| Funding | [6 empty] | 321538 | 19596 | 155700 | 198900 | 31004 | 29422 | 19964 | 29422 | 137200 | 29422 | 29422 | 29422 | 189630 | 36190 | 65800 | 136100 | 36960 | 99470 | 258426 | 92500 | 83500 | 42042 | 19680 | 276500 | 85500 | 233300 |  | 2686610 |  | Funding
| Percentage | [6 empty] | 49% | 100% | 49.99% | 49.99% | 100% | 47% | 100% | 47% | 49% | 47% | 47% | 47% | 48.99% | 47% | 47% | 49.99% | 48% | 49% | 48.99% | 50% | 50% | 100% | 47.99% | 49.99% | 50% | 49.99% |  |  |  | Percentage