## Person Months
Effort Breakdown per task (Person/Months) Month: 1 - 24
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 8 | 4 | 7 | 10 | 3 | 1 | 1 | 1 | 6 | 1 | 3 | 11 | 3 | 1 | 4 | 8 | 1 | 5 | 15 | 8 | 6 | 7 | 14 | 5 | 133 | 23.66% | 1193.2884
T1.1 | Definition of content to be provided | IMAC | 1 | 1 |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 2 |  | 1 | 1 | 1 |  |  | 2 |  |  | 21 | 3.735% | 188.414 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | 1 | 1 |  | 2 | 1 |  |  |  | 1 |  | 1 |  |  |  | 2 |  |  | 1 | 1 |  |  | 2 |  |  | 13 | 2.312% | 116.6372 | D1 | 50%
T1.3 | Identification of standards to be used | IAT |  |  | 1 | [8 empty] | 1 | [5 empty] | 2 | 1 |  |  |  | 2 |  | 7 | 1.245% | 62.8047 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | 4 | 1 | 6 | 2 |  |  |  |  | 4 |  |  | 10 | 2 |  |  | 8 |  |  | 12 | 8 | 6 |  | 10 |  | 73 | 12.98% | 654.9628 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | 1 | [16 empty] | 1 |  |  |  | 1 |  | 1 | 4 | 0.7115% | 35.8884 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | 1 |  |  | 2 | [6 empty] | 1 | [10 empty] | 1 | 2 | 2 | 9 | 1.601% | 80.7488 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC |  | 1 |  | 2 | [17 empty] | 1 |  | 2 | 6 | 1.067% | 53.8326 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 10 | 4 | 6 | 9 | 3 | 2 | 2 | 2 | 6 | 2 | 2 | 10 | 6 | 2 | 5.5 | 8 | 4 | 3 | 12 | 6 | 6 | 12 | 14 | 8 | 144.5 | 25.7% | 1296.4675
T2.1 | Preparation of Content & Products | IMAC | 1 | 4 |  | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 |  | 1 | 2 | 5.5 |  | 4 | 2 |  |  |  | 6 |  |  | 42.5 | 7.56% | 381.314 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | 7 |  | 6 | 2 |  |  |  |  | 4 |  |  | 10 | 5 |  |  | 8 |  |  | 12 | 6 | 6 |  | 12 |  | 78 | 13.87% | 699.8233 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | 1 | [16 empty] | 1 |  |  |  | 2 |  | 2 | 6 | 1.067% | 53.8326 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | 1 |  |  | 2 | [6 empty] | 1 | [10 empty] | 2 | 2 | 3 | 11 | 1.957% | 98.693 | D6 | 50%
T2.5 | Market preparation | TINC |  |  |  | 2 | [17 empty] | 2 |  | 3 | 7 | 1.245% | 62.8047 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 5 | 2 | 3 | 5 | 4 | 2 | 2 | 2 | 6 | 2 | 2 | 3 | 6 | 2 | 0 | 6.7 | 2 | 4 | 9 | 3 | 3 | 4 | 14 | 0 | 91.7 | 16.31% | 822.741
T3.1 | Validation of the REGNET-Demonstrator | IMAC |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 3 |  | 18 | 3.202% | 161.4977 | D7 | 50%
T3.2 | Preparation of the Demonstration Phase | VALT | 1 | 1 |  | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 |  | 3 | 1 |  |  | 1 | 3 | 3 |  |  | 3 | 3 |  | 33 | 5.87% | 296.0791 | D7 | 50%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | 4 |  | 3 | 1 |  |  |  |  | 2 |  |  | 3 | 2 |  |  | 6.7 |  |  | 5 | 3 | 3 |  | 8 |  | 40.7 | 7.239% | 365.1642 | D8 | 50%
WP4 | Demonstration, Assessment and Evaluation | TARX | 1 | 5 | 1 | 4 | 6 | 3 | 3 | 3 | 5 | 3 | 3 | 1 | 5 | 3 | 0 | 1 | 3 | 4 | 5 | 1 | 1 | 6 | 14 | 1 | 82 | 14.59% | 735.7117
T4.1 | Execution of the demonstration phase (trial service) | TARX |  | 5 |  | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 |  |  | 3 | 3 | 3 |  |  | 6 | 3 |  | 55 | 9.783% | 493.4651 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | 1 |  | 1 | [5 empty] | 1 |  |  | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 |  | 11 | 1 | 21 | 3.735% | 188.414 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 | 1 | [5 empty] | 6 | 1.067% | 53.8326 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 4 | 1 | 20 | 3.557% | 179.4419
T5.1 | Development of a Technology implementation plan (draft) | MOT | 1 | [10 empty] | 1 | 1 |  | 2 |  |  | 1 | 1 |  |  |  | 2 | 1 | 10 | 1.779% | 89.7209 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 1 |  | 1 |  |  |  |  | 1 |  | 1 | 1 |  |  | 2 | [6 empty] | 1 | 2 |  | 10 | 1.779% | 89.7209 | D12 | 45%
WP6 | Information Dissemination | SPAC | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 2 | 1 | 17 | 3.024% | 152.5256
T6.1 | Information Dissemination | SPAC | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 | 1 |  | 2 |  |  | 1 | 1 |  |  | 1 | 2 | 1 | 17 | 3.024% | 152.5256 | D13 | 45%
WP7 | Project Management | AIT | 12 | 1 | 12 | 6 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 9 | 4 | 0 | 0 | 3 | 0 | 2 | 5 | 2 | 2 | 2 | 6 | 2 | 74 | 13.16% | 663.9349
T7.1 | Project Management | AIT | 12 | 1 | 12 | 6 | 2 |  |  |  | 4 |  |  | 3 | 4 |  |  | 3 |  | 2 | 5 | 2 | 2 | 2 | 6 | 2 | 68 | 12.1% | 610.1024 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 6 | [12 empty] | 6 | 1.067% | 53.8326 | D14 | 45%
| Total Person Months |  | 38 | 18 | 30 | 36 | 19 | 8 | 8 | 8 | 29 | 8 | 12 | 37 | 26 | 8 | 15.5 | 26.7 | 10 | 20 | 48 | 20 | 18 | 33 | 68 | 18 | 562.2 | 100% | 5044.111
|  | % | 6.759% | 3.202% | 5.336% | 6.403% | 3.38% | 1.423% | 1.423% | 1.423% | 5.158% | 1.423% | 2.134% | 6.581% | 4.625% | 1.423% | 2.757% | 4.749% | 1.779% | 3.557% | 8.538% | 3.557% | 3.202% | 5.87% | 12.1% | 3.202% | 100%
| PM Cost in KEURO | KEURO | 410.041 | 129.6 | 325.843 | 388.834 | 39.823 | 57.6 | 19.66 | 57.6 | 261.04 | 57.602 | 96.206 | 452.858 | 280.836 | 72.006 | 121.086 | 258.451 | 29.534 | 198.206 | 518.464 | 178.967 | 160.924 | 37.008 | 734.432 | 157.49 | 5044.111
| PM Cost in EURO | EURO | 410041 | 129600 | 325843 | 388834 | 39823 | 57600 | 19660 | 57600 | 261040 | 57602 | 96206 | 452858 | 280836 | 72006 | 121086 | 258451 | 29534 | 198206 | 518464 | 178967 | 160924 | 37008 | 734432 | 157490 | 5044111
| Faktor = 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | Average
Effort Breakdown per task (PersonMonth) Month: 1 - 24
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 8 | 4 | 7 | 10 | 3 | 1 | 1 | 1 | 6 | 1 | 3 | 11 | 3 | 1 | 4 | 8 | 1 | 5 | 15 | 8 | 6 | 7 | 14 | 5 | 133 | 23.66% | 1193.2884
T1.1 | Definition of content to be provided | IMAC | 1 | 1 |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 2 |  | 1 | 1 | 1 |  |  | 2 |  |  | 21 | 3.735% | 188.414 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | 1 | 1 |  | 2 | 1 |  |  |  | 1 |  | 1 |  |  |  | 2 |  |  | 1 | 1 |  |  | 2 |  |  | 13 | 2.312% | 116.6372 | D1 | 50%
T1.3 | Identification of standards to be used | IAT |  |  | 1 | [8 empty] | 1 | [5 empty] | 2 | 1 |  |  |  | 2 |  | 7 | 1.245% | 62.8047 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | 4 | 1 | 6 | 2 |  |  |  |  | 4 |  |  | 10 | 2 |  |  | 8 |  |  | 12 | 8 | 6 |  | 10 |  | 73 | 12.98% | 654.9628 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | 1 | [16 empty] | 1 |  |  |  | 1 |  | 1 | 4 | 0.7115% | 35.8884 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | 1 |  |  | 2 | [6 empty] | 1 | [10 empty] | 1 | 2 | 2 | 9 | 1.601% | 80.7488 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC |  | 1 |  | 2 | [17 empty] | 1 |  | 2 | 6 | 1.067% | 53.8326 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 10 | 4 | 6 | 9 | 3 | 2 | 2 | 2 | 6 | 2 | 2 | 10 | 6 | 2 | 5.5 | 8 | 4 | 3 | 12 | 6 | 6 | 12 | 14 | 8 | 144.5 | 25.7% | 1296.4675
T2.1 | Preparation of Content & Products | IMAC | 1 | 4 |  | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 |  | 1 | 2 | 5.5 |  | 4 | 2 |  |  |  | 6 |  |  | 42.5 | 7.56% | 381.314 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | 7 |  | 6 | 2 |  |  |  |  | 4 |  |  | 10 | 5 |  |  | 8 |  |  | 12 | 6 | 6 |  | 12 |  | 78 | 13.87% | 699.8233 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | 1 | [16 empty] | 1 |  |  |  | 2 |  | 2 | 6 | 1.067% | 53.8326 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | 1 |  |  | 2 | [6 empty] | 1 | [10 empty] | 2 | 2 | 3 | 11 | 1.957% | 98.693 | D6 | 50%
T2.5 | Market preparation | TINC |  |  |  | 2 | [17 empty] | 2 |  | 3 | 7 | 1.245% | 62.8047 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 5 | 2 | 3 | 5 | 4 | 2 | 2 | 2 | 6 | 2 | 2 | 3 | 6 | 2 | 0 | 6.7 | 2 | 4 | 9 | 3 | 3 | 4 | 14 | 0 | 91.7 | 16.31% | 822.741
T3.1 | Validation of the REGNET-Demonstrator | IMAC |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 3 |  | 18 | 3.202% | 161.4977 | D7 | 50%
T3.2 | Preparation of the Demonstration Phase | VALT | 1 | 1 |  | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 |  | 3 | 1 |  |  | 1 | 3 | 3 |  |  | 3 | 3 |  | 33 | 5.87% | 296.0791 | D7 | 50%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | 4 |  | 3 | 1 |  |  |  |  | 2 |  |  | 3 | 2 |  |  | 6.7 |  |  | 5 | 3 | 3 |  | 8 |  | 40.7 | 7.239% | 365.1642 | D8 | 50%
WP4 | Demonstration, Assessment and Evaluation | TARX | 1 | 5 | 1 | 4 | 6 | 3 | 3 | 3 | 5 | 3 | 3 | 1 | 5 | 3 | 0 | 1 | 3 | 4 | 5 | 1 | 1 | 6 | 14 | 1 | 82 | 14.59% | 735.7117
T4.1 | Execution of the demonstration phase (trial service) | TARX |  | 5 |  | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 |  |  | 3 | 3 | 3 |  |  | 6 | 3 |  | 55 | 9.783% | 493.4651 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | 1 |  | 1 | [5 empty] | 1 |  |  | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 |  | 11 | 1 | 21 | 3.735% | 188.414 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 | 1 | [5 empty] | 6 | 1.067% | 53.8326 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 4 | 1 | 20 | 3.557% | 179.4419
T5.1 | Development of a Technology implementation plan (draft) | MOT | 1 | [10 empty] | 1 | 1 |  | 2 |  |  | 1 | 1 |  |  |  | 2 | 1 | 10 | 1.779% | 89.7209 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 1 |  | 1 |  |  |  |  | 1 |  | 1 | 1 |  |  | 2 | [6 empty] | 1 | 2 |  | 10 | 1.779% | 89.7209 | D12 | 45%
WP6 | Information Dissemination | SPAC | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 2 | 1 | 17 | 3.024% | 152.5256
T6.1 | Information Dissemination | SPAC | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 | 1 |  | 2 |  |  | 1 | 1 |  |  | 1 | 2 | 1 | 17 | 3.024% | 152.5256 | D13 | 45%
WP7 | Project Management | AIT | 12 | 1 | 12 | 6 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 9 | 4 | 0 | 0 | 3 | 0 | 2 | 5 | 2 | 2 | 2 | 6 | 2 | 74 | 13.16% | 663.9349
T7.1 | Project Management | AIT | 12 | 1 | 12 | 6 | 2 |  |  |  | 4 |  |  | 3 | 4 |  |  | 3 |  | 2 | 5 | 2 | 2 | 2 | 6 | 2 | 68 | 12.1% | 610.1024 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 6 | [12 empty] | 6 | 1.067% | 53.8326 | D14 | 45%
| Total Person Months |  | 38 | 18 | 30 | 36 | 19 | 8 | 8 | 8 | 29 | 8 | 12 | 37 | 26 | 8 | 15.5 | 26.7 | 10 | 20 | 48 | 20 | 18 | 33 | 68 | 18 | 562.2 | 100% | 5044.111
|  | % | 6.759% | 3.202% | 5.336% | 6.403% | 3.38% | 1.423% | 1.423% | 1.423% | 5.158% | 1.423% | 2.134% | 6.581% | 4.625% | 1.423% | 2.757% | 4.749% | 1.779% | 3.557% | 8.538% | 3.557% | 3.202% | 5.87% | 12.1% | 3.202% | 100%
Effort Breakdown per task (PersonMonth) Month: 1 - 6
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 8 | 4 | 7 | 10 | 3 | 1 | 1 | 1 | 6 | 1 | 3 | 11 | 3 | 1 | 4 | 8 | 1 | 5 | 15 | 8 | 6 | 7 | 14 | 5 | 133 | 23.66% | 1193.2884
T1.1 | Definition of content to be provided | IMAC | 1 | 1 |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 2 |  | 1 | 1 | 1 |  |  | 2 |  |  | 21 | 3.735% | 188.414 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | 1 | 1 |  | 2 | 1 |  |  |  | 1 |  | 1 |  |  |  | 2 |  |  | 1 | 1 |  |  | 2 |  |  | 13 | 2.312% | 116.6372 | D1 | 50%
T1.3 | Identification of standards to be used | IAT |  |  | 1 | [8 empty] | 1 | [5 empty] | 2 | 1 |  |  |  | 2 |  | 7 | 1.245% | 62.8047 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | 4 | 1 | 6 | 2 |  |  |  |  | 4 |  |  | 10 | 2 |  |  | 8 |  |  | 12 | 8 | 6 |  | 10 |  | 73 | 12.98% | 654.9628 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | 1 | [16 empty] | 1 |  |  |  | 1 |  | 1 | 4 | 0.7115% | 35.8884 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | 1 |  |  | 2 | [6 empty] | 1 | [10 empty] | 1 | 2 | 2 | 9 | 1.601% | 80.7488 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC |  | 1 |  | 2 | [17 empty] | 1 |  | 2 | 6 | 1.067% | 53.8326 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T2.1 | Preparation of Content & Products | IMAC | [24 empty] | 0 | 0% | 0 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | [24 empty] | 0 | 0% | 0 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.5 | Market preparation | TINC | [24 empty] | 0 | 0% | 0 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T3.1 | Validation of the REGNET-Demonstrator | IMAC | [24 empty] | 0 | 0% | 0 | D7 | 50%
T3.2 | Preparation of the Demonstration Phase | VALT | [24 empty] | 0 | 0% | 0 | D7 | 50%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | [24 empty] | 0 | 0% | 0 | D8 | 50%
WP4 | Demonstration, Assessment and Evaluation | TARX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T4.1 | Execution of the demonstration phase (trial service) | TARX | [24 empty] | 0 | 0% | 0 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | [24 empty] | 0 | 0% | 0 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT | [24 empty] | 0 | 0% | 0 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 0.25 | 0.25 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.5 | 0.25 | 0 | 1 | 0 | 0 | 0.25 | 0.25 | 0 | 0 | 0.25 | 1 | 0.25 | 5 | 0.8894% | 44.8605
T5.1 | Development of a Technology implementation plan (draft) | MOT | 0.25 | [10 empty] | 0.25 | 0.25 |  | 0.5 |  |  | 0.25 | 0.25 |  |  |  | 0.5 | 0.25 | 2.5 | 0.4447% | 22.4302 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 0.25 |  | 0.25 |  |  |  |  | 0.25 |  | 0.25 | 0.25 |  |  | 0.5 | [6 empty] | 0.25 | 0.5 |  | 2.5 | 0.4447% | 22.4302 | D12 | 45%
WP6 | Information Dissemination | SPAC | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.25 | 0.25 | 0 | 0.5 | 0 | 0 | 0.25 | 0.25 | 0 | 0 | 0.25 | 0.5 | 0.25 | 4.25 | 0.756% | 38.1314
T6.1 | Information Dissemination | SPAC | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  |  | 0.25 |  | 0.25 | 0.25 | 0.25 |  | 0.5 |  |  | 0.25 | 0.25 |  |  | 0.25 | 0.5 | 0.25 | 4.25 | 0.756% | 38.1314 | D13 | 45%
WP7 | Project Management | AIT | 3 | 0.25 | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 1 | 0 | 0 | 2.25 | 1 | 0 | 0 | 0.75 | 0 | 0.5 | 1.25 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 18.5 | 3.291% | 165.9837
T7.1 | Project Management | AIT | 3 | 0.25 | 3 | 1.5 | 0.5 |  |  |  | 1 |  |  | 0.75 | 1 |  |  | 0.75 |  | 0.5 | 1.25 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 17 | 3.024% | 152.5256 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 1.5 | [12 empty] | 1.5 | 0.2668% | 13.4581 | D14 | 45%
| Total Person Months |  | 11.5 | 4.75 | 10.25 | 12 | 3.75 | 1 | 1 | 1 | 7.5 | 1 | 3.5 | 14 | 4.5 | 1 | 5.5 | 8.75 | 1 | 6 | 16.75 | 8.5 | 6.5 | 8 | 17 | 6 | 160.75 | 28.59% | 1442.264
|  | % | 2.046% | 0.8449% | 1.823% | 2.134% | 0.667% | 0.1779% | 0.1779% | 0.1779% | 1.334% | 0.1779% | 0.6226% | 2.49% | 0.8004% | 0.1779% | 0.9783% | 1.556% | 0.1779% | 1.067% | 2.979% | 1.512% | 1.156% | 1.423% | 3.024% | 1.067% | 28.59%
Effort Breakdown per task (PersonMonth) Month: 7 - 12
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T1.1 | Definition of content to be provided | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.3 | Identification of standards to be used | IAT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC | [24 empty] | 0 | 0% | 0 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 10 | 4 | 6 | 9 | 3 | 2 | 2 | 2 | 6 | 2 | 1 | 10 | 6 | 2 | 5.5 | 8 | 4 | 3 | 12 | 6 | 6 | 12 | 14 | 8 | 143.5 | 25.52% | 1287.4954
T2.1 | Preparation of Content & Products | IMAC | 1 | 4 |  | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 |  | 1 | 2 | 5.5 |  | 4 | 2 |  |  |  | 6 |  |  | 42.5 | 7.56% | 381.314 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | 7 |  | 6 | 2 |  |  |  |  | 4 |  |  | 10 | 5 |  |  | 8 |  |  | 12 | 6 | 6 |  | 12 |  | 78 | 13.87% | 699.8233 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | 1 | [16 empty] | 1 |  |  |  | 2 |  | 2 | 6 | 1.067% | 53.8326 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | 1 |  |  | 2 | [17 empty] | 2 | 2 | 3 | 10 | 1.779% | 89.7209 | D6 | 50%
T2.5 | Market preparation | TINC |  |  |  | 2 | [17 empty] | 2 |  | 3 | 7 | 1.245% | 62.8047 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T3.1 | Validation of the REGNET-Demonstrator | IMAC | [24 empty] | 0 | 0% | 0 | D7 | 50%
T3.2 | Preparation of the Demonstration Phase | VALT | [24 empty] | 0 | 0% | 0 | D7 | 50%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | [24 empty] | 0 | 0% | 0 | D8 | 50%
WP4 | Demonstration, Assessment and Evaluation | TARX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T4.1 | Execution of the demonstration phase (trial service) | TARX | [24 empty] | 0 | 0% | 0 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | [24 empty] | 0 | 0% | 0 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT | [24 empty] | 0 | 0% | 0 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 0.25 | 0.25 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.5 | 0.25 | 0 | 1 | 0 | 0 | 0.25 | 0.25 | 0 | 0 | 0.25 | 1 | 0.25 | 5 | 0.8894% | 44.8605
T5.1 | Development of a Technology implementation plan (draft) | MOT | 0.25 | [10 empty] | 0.25 | 0.25 |  | 0.5 |  |  | 0.25 | 0.25 |  |  |  | 0.5 | 0.25 | 2.5 | 0.4447% | 22.4302 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 0.25 |  | 0.25 |  |  |  |  | 0.25 |  | 0.25 | 0.25 |  |  | 0.5 | [6 empty] | 0.25 | 0.5 |  | 2.5 | 0.4447% | 22.4302 | D12 | 45%
WP6 | Information Dissemination | SPAC | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.25 | 0.25 | 0 | 0.5 | 0 | 0 | 0.25 | 0.25 | 0 | 0 | 0.25 | 0.5 | 0.25 | 4.25 | 0.756% | 38.1314
T6.1 | Information Dissemination | SPAC | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  |  | 0.25 |  | 0.25 | 0.25 | 0.25 |  | 0.5 |  |  | 0.25 | 0.25 |  |  | 0.25 | 0.5 | 0.25 | 4.25 | 0.756% | 38.1314 | D13 | 45%
WP7 | Project Management | AIT | 3 | 0.25 | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 1 | 0 | 0 | 2.25 | 1 | 0 | 0 | 0.75 | 0 | 0.5 | 1.25 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 18.5 | 3.291% | 165.9837
T7.1 | Project Management | AIT | 3 | 0.25 | 3 | 1.5 | 0.5 |  |  |  | 1 |  |  | 0.75 | 1 |  |  | 0.75 |  | 0.5 | 1.25 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 17 | 3.024% | 152.5256 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 1.5 | [12 empty] | 1.5 | 0.2668% | 13.4581 | D14 | 45%
| Total Person Months |  | 13.5 | 4.75 | 9.25 | 11 | 3.75 | 2 | 2 | 2 | 7.5 | 2 | 1.5 | 13 | 7.5 | 2 | 7 | 8.75 | 4 | 4 | 13.75 | 6.5 | 6.5 | 13 | 17 | 9 | 171.25 | 30.46% | 1536.471
|  | % | 2.401% | 0.8449% | 1.645% | 1.957% | 0.667% | 0.3557% | 0.3557% | 0.3557% | 1.334% | 0.3557% | 0.2668% | 2.312% | 1.334% | 0.3557% | 1.245% | 1.556% | 0.7115% | 0.7115% | 2.446% | 1.156% | 1.156% | 2.312% | 3.024% | 1.601% | 30.46%
Effort Breakdown per task (PersonMonth) Month: 13 - 18
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T1.1 | Definition of content to be provided | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.3 | Identification of standards to be used | IAT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC | [24 empty] | 0 | 0% | 0 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T2.1 | Preparation of Content & Products | IMAC | [24 empty] | 0 | 0% | 0 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | [24 empty] | 0 | 0% | 0 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.5 | Market preparation | TINC | [24 empty] | 0 | 0% | 0 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 5 | 2 | 3 | 5 | 4 | 2 | 2 | 2 | 6 | 2 | 2 | 3 | 6 | 2 | 0 | 6.7 | 2 | 4 | 9 | 3 | 3 | 4 | 14 | 0 | 91.7 | 16.31% | 822.741
T3.1 | Validation of the REGNET-Demonstrator | IMAC |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 3 |  | 18 | 3.202% | 161.4977 | D7 | 50%
T3.2 | Preparation of the Demonstration Phase | VALT | 1 | 1 |  | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 |  | 3 | 1 |  |  | 1 | 3 | 3 |  |  | 3 | 3 |  | 33 | 5.87% | 296.0791 | D7 | 50%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | 4 |  | 3 | 1 |  |  |  |  | 2 |  |  | 3 | 2 |  |  | 6.7 |  |  | 5 | 3 | 3 |  | 8 |  | 40.7 | 7.239% | 365.1642 | D8 | 50%
WP4 | Demonstration, Assessment and Evaluation | TARX | 0.5 | 2.5 | 0.5 | 1.5 | 2.5 | 1.5 | 1.5 | 1.5 | 2 | 1.5 | 1.5 | 0.5 | 2 | 1.5 | 0 | 0.5 | 1.5 | 1.5 | 2 | 0.5 | 0.5 | 3 | 7 | 0.5 | 38 | 6.759% | 340.9396
T4.1 | Execution of the demonstration phase (trial service) | TARX |  | 2.5 |  | 1.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  | 1.5 | 1.5 |  |  | 1.5 | 1.5 | 1.5 |  |  | 3 | 1.5 |  | 27.5 | 4.891% | 246.7326 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | 0.5 | 0 | 0.5 | [5 empty] | 0.5 |  |  | 0.5 | 0.5 |  |  | 0.5 |  |  | 0.5 | 0.5 | 0.5 |  | 5.5 | 0.5 | 10.5 | 1.868% | 94.207 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT | [24 empty] | 0 | 0% | 0 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 0.25 | 0.25 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.5 | 0.25 | 0 | 1 | 0 | 0 | 0.25 | 0.25 | 0 | 0 | 0.25 | 1 | 0.25 | 5 | 0.8894% | 44.8605
T5.1 | Development of a Technology implementation plan (draft) | MOT | 0.25 | [10 empty] | 0.25 | 0.25 |  | 0.5 |  |  | 0.25 | 0.25 |  |  |  | 0.5 | 0.25 | 2.5 | 0.4447% | 22.4302 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 0.25 |  | 0.25 |  |  |  |  | 0.25 |  | 0.25 | 0.25 |  |  | 0.5 | [6 empty] | 0.25 | 0.5 |  | 2.5 | 0.4447% | 22.4302 | D12 | 45%
WP6 | Information Dissemination | SPAC | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.25 | 0.25 | 0 | 0.5 | 0 | 0 | 0.25 | 0.25 | 0 | 0 | 0.25 | 0.5 | 0.25 | 4.25 | 0.756% | 38.1314
T6.1 | Information Dissemination | SPAC | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  |  | 0.25 |  | 0.25 | 0.25 | 0.25 |  | 0.5 |  |  | 0.25 | 0.25 |  |  | 0.25 | 0.5 | 0.25 | 4.25 | 0.756% | 38.1314 | D13 | 45%
WP7 | Project Management | AIT | 3 | 0.25 | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 1 | 0 | 0 | 2.25 | 1 | 0 | 0 | 0.75 | 0 | 0.5 | 1.25 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 18.5 | 3.291% | 165.9837
T7.1 | Project Management | AIT | 3 | 0.25 | 3 | 1.5 | 0.5 |  |  |  | 1 |  |  | 0.75 | 1 |  |  | 0.75 |  | 0.5 | 1.25 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 17 | 3.024% | 152.5256 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 1.5 | [12 empty] | 1.5 | 0.2668% | 13.4581 | D14 | 45%
| Total Person Months |  | 9 | 5.25 | 6.75 | 8.5 | 7.25 | 3.5 | 3.5 | 3.5 | 9.5 | 3.5 | 4 | 6.5 | 9.5 | 3.5 | 1.5 | 7.95 | 3.5 | 6.5 | 12.75 | 4 | 4 | 8 | 24 | 1.5 | 157.45 | 28.01% | 1412.6561
|  | % | 1.601% | 0.9338% | 1.201% | 1.512% | 1.29% | 0.6226% | 0.6226% | 0.6226% | 1.69% | 0.6226% | 0.7115% | 1.156% | 1.69% | 0.6226% | 0.2668% | 1.414% | 0.6226% | 1.156% | 2.268% | 0.7115% | 0.7115% | 1.423% | 4.269% | 0.2668% | 28.01%
Effort Breakdown per task (PersonMonth) Month: 19 - 24
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T1.1 | Definition of content to be provided | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.3 | Identification of standards to be used | IAT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC | [24 empty] | 0 | 0% | 0 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T2.1 | Preparation of Content & Products | IMAC | [24 empty] | 0 | 0% | 0 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | [24 empty] | 0 | 0% | 0 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.5 | Market preparation | TINC | [24 empty] | 0 | 0% | 0 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T3.1 | Validation of the REGNET-Demonstrator | IMAC | [24 empty] | 0 | 0% | 0 | D7 | 35%
T3.2 | Preparation of the Demonstration Phase | VALT | [24 empty] | 0 | 0% | 0 | D7 | 35%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | [24 empty] | 0 | 0% | 0 | D8 | 35%
WP4 | Demonstration, Assessment and Evaluation | TARX | 0.5 | 2.5 | 0.5 | 2.5 | 3.5 | 1.5 | 1.5 | 1.5 | 3 | 1.5 | 1.5 | 0.5 | 3 | 1.5 | 0 | 0.5 | 1.5 | 2.5 | 3 | 0.5 | 0.5 | 3 | 7 | 0.5 | 44 | 7.826% | 394.7721
T4.1 | Execution of the demonstration phase (trial service) | TARX |  | 2.5 |  | 1.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  | 1.5 | 1.5 |  |  | 1.5 | 1.5 | 1.5 |  |  | 3 | 1.5 |  | 27.5 | 4.891% | 246.7326 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | 0.5 |  | 0.5 | [5 empty] | 0.5 |  |  | 0.5 | 0.5 |  |  | 0.5 |  |  | 0.5 | 0.5 | 0.5 |  | 5.5 | 0.5 | 10.5 | 1.868% | 94.207 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 | 1 | [5 empty] | 6 | 1.067% | 53.8326 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 0.25 | 0.25 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.5 | 0.25 | 0 | 1 | 0 | 0 | 0.25 | 0.25 | 0 | 0 | 0.25 | 1 | 0.25 | 5 | 0.8894% | 44.8605
T5.1 | Development of a Technology implementation plan (draft) | MOT | 0.25 | [10 empty] | 0.25 | 0.25 |  | 0.5 |  |  | 0.25 | 0.25 |  |  |  | 0.5 | 0.25 | 2.5 | 0.4447% | 22.4302 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 0.25 |  | 0.25 |  |  |  |  | 0.25 |  | 0.25 | 0.25 |  |  | 0.5 | [6 empty] | 0.25 | 0.5 |  | 2.5 | 0.4447% | 22.4302 | D12 | 45%
WP6 | Information Dissemination | SPAC | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.25 | 0.25 | 0 | 0.5 | 0 | 0 | 0.25 | 0.25 | 0 | 0 | 0.25 | 0.5 | 0.25 | 4.25 | 0.756% | 38.1314
T6.1 | Information Dissemination | SPAC | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  |  | 0.25 |  | 0.25 | 0.25 | 0.25 |  | 0.5 |  |  | 0.25 | 0.25 |  |  | 0.25 | 0.5 | 0.25 | 4.25 | 0.756% | 38.1314 | D13 | 45%
WP7 | Project Management | AIT | 3 | 0.25 | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 1 | 0 | 0 | 2.25 | 1 | 0 | 0 | 0.75 | 0 | 0.5 | 1.25 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 18.5 | 3.291% | 165.9837
T7.1 | Project Management | AIT | 3 | 0.25 | 3 | 1.5 | 0.5 |  |  |  | 1 |  |  | 0.75 | 1 |  |  | 0.75 |  | 0.5 | 1.25 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 17 | 3.024% | 152.5256 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 1.5 | [12 empty] | 1.5 | 0.2668% | 13.4581 | D14 | 45%
| Total Person Months |  | 4 | 3.25 | 3.75 | 4.5 | 4.25 | 1.5 | 1.5 | 1.5 | 4.5 | 1.5 | 2 | 3.5 | 4.5 | 1.5 | 1.5 | 1.25 | 1.5 | 3.5 | 4.75 | 1 | 1 | 4 | 10 | 1.5 | 71.75 | 12.76% | 643.7477
|  | % | 0.7115% | 0.5781% | 0.667% | 0.8004% | 0.756% | 0.2668% | 0.2668% | 0.2668% | 0.8004% | 0.2668% | 0.3557% | 0.6226% | 0.8004% | 0.2668% | 0.2668% | 0.2223% | 0.2668% | 0.6226% | 0.8449% | 0.1779% | 0.1779% | 0.7115% | 1.779% | 0.2668% | 12.76%

## Cost (KEURO)
Effort Breakdown per task (Person/Months) Month: 1 - 24
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 8 | 4 | 7 | 10 | 3 | 1 | 1 | 1 | 6 | 1 | 3 | 11 | 3 | 1 | 4 | 8 | 1 | 5 | 15 | 8 | 6 | 7 | 14 | 5 | 133 | 23.66% | 1193.2884
T1.1 | Definition of content to be provided | IMAC | 1 | 1 |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 2 |  | 1 | 1 | 1 |  |  | 2 |  |  | 21 | 3.735% | 188.414 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | 1 | 1 |  | 2 | 1 |  |  |  | 1 |  | 1 |  |  |  | 2 |  |  | 1 | 1 |  |  | 2 |  |  | 13 | 2.312% | 116.6372 | D1 | 50%
T1.3 | Identification of standards to be used | IAT |  |  | 1 | [8 empty] | 1 | [5 empty] | 2 | 1 |  |  |  | 2 |  | 7 | 1.245% | 62.8047 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | 4 | 1 | 6 | 2 |  |  |  |  | 4 |  |  | 10 | 2 |  |  | 8 |  |  | 12 | 8 | 6 |  | 10 |  | 73 | 12.98% | 654.9628 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | 1 | [16 empty] | 1 |  |  |  | 1 |  | 1 | 4 | 0.7115% | 35.8884 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | 1 |  |  | 2 | [6 empty] | 1 | [10 empty] | 1 | 2 | 2 | 9 | 1.601% | 80.7488 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC |  | 1 |  | 2 | [17 empty] | 1 |  | 2 | 6 | 1.067% | 53.8326 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 10 | 4 | 6 | 9 | 3 | 2 | 2 | 2 | 6 | 2 | 2 | 10 | 6 | 2 | 5.5 | 8 | 4 | 3 | 12 | 6 | 6 | 12 | 14 | 8 | 144.5 | 25.7% | 1296.4675
T2.1 | Preparation of Content & Products | IMAC | 1 | 4 |  | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 |  | 1 | 2 | 5.5 |  | 4 | 2 |  |  |  | 6 |  |  | 42.5 | 7.56% | 381.314 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | 7 |  | 6 | 2 |  |  |  |  | 4 |  |  | 10 | 5 |  |  | 8 |  |  | 12 | 6 | 6 |  | 12 |  | 78 | 13.87% | 699.8233 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | 1 | [16 empty] | 1 |  |  |  | 2 |  | 2 | 6 | 1.067% | 53.8326 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | 1 |  |  | 2 | [6 empty] | 1 | [10 empty] | 2 | 2 | 3 | 11 | 1.957% | 98.693 | D6 | 50%
T2.5 | Market preparation | TINC |  |  |  | 2 | [17 empty] | 2 |  | 3 | 7 | 1.245% | 62.8047 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 5 | 2 | 3 | 5 | 4 | 2 | 2 | 2 | 6 | 2 | 2 | 3 | 6 | 2 | 0 | 6.7 | 2 | 4 | 9 | 3 | 3 | 4 | 14 | 0 | 91.7 | 16.31% | 822.741
T3.1 | Validation of the REGNET-Demonstrator | IMAC |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 3 |  | 18 | 3.202% | 161.4977 | D7 | 50%
T3.2 | Preparation of the Demonstration Phase | VALT | 1 | 1 |  | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 |  | 3 | 1 |  |  | 1 | 3 | 3 |  |  | 3 | 3 |  | 33 | 5.87% | 296.0791 | D7 | 50%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | 4 |  | 3 | 1 |  |  |  |  | 2 |  |  | 3 | 2 |  |  | 6.7 |  |  | 5 | 3 | 3 |  | 8 |  | 40.7 | 7.239% | 365.1642 | D8 | 50%
WP4 | Demonstration, Assessment and Evaluation | TARX | 1 | 5 | 1 | 4 | 6 | 3 | 3 | 3 | 5 | 3 | 3 | 1 | 5 | 3 | 0 | 1 | 3 | 4 | 5 | 1 | 1 | 6 | 14 | 1 | 82 | 14.59% | 735.7117
T4.1 | Execution of the demonstration phase (trial service) | TARX |  | 5 |  | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 |  |  | 3 | 3 | 3 |  |  | 6 | 3 |  | 55 | 9.783% | 493.4651 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | 1 |  | 1 | [5 empty] | 1 |  |  | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 |  | 11 | 1 | 21 | 3.735% | 188.414 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 | 1 | [5 empty] | 6 | 1.067% | 53.8326 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 4 | 1 | 20 | 3.557% | 179.4419
T5.1 | Development of a Technology implementation plan (draft) | MOT | 1 | [10 empty] | 1 | 1 |  | 2 |  |  | 1 | 1 |  |  |  | 2 | 1 | 10 | 1.779% | 89.7209 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 1 |  | 1 |  |  |  |  | 1 |  | 1 | 1 |  |  | 2 | [6 empty] | 1 | 2 |  | 10 | 1.779% | 89.7209 | D12 | 45%
WP6 | Information Dissemination | SPAC | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 2 | 1 | 17 | 3.024% | 152.5256
T6.1 | Information Dissemination | SPAC | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 | 1 |  | 2 |  |  | 1 | 1 |  |  | 1 | 2 | 1 | 17 | 3.024% | 152.5256 | D13 | 45%
WP7 | Project Management | AIT | 12 | 1 | 12 | 6 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 9 | 4 | 0 | 0 | 3 | 0 | 2 | 5 | 2 | 2 | 2 | 6 | 2 | 74 | 13.16% | 663.9349
T7.1 | Project Management | AIT | 12 | 1 | 12 | 6 | 2 |  |  |  | 4 |  |  | 3 | 4 |  |  | 3 |  | 2 | 5 | 2 | 2 | 2 | 6 | 2 | 68 | 12.1% | 610.1024 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 6 | [12 empty] | 6 | 1.067% | 53.8326 | D14 | 45%
| Total PM |  | 38 | 18 | 30 | 36 | 19 | 8 | 8 | 8 | 29 | 8 | 12 | 37 | 26 | 8 | 15.5 | 26.7 | 10 | 20 | 48 | 20 | 18 | 33 | 68 | 18 | 562.2 | 100% | 5044.111
|  | % | 6.759% | 3.202% | 5.336% | 6.403% | 3.38% | 1.423% | 1.423% | 1.423% | 5.158% | 1.423% | 2.134% | 6.581% | 4.625% | 1.423% | 2.757% | 4.749% | 1.779% | 3.557% | 8.538% | 3.557% | 3.202% | 5.87% | 12.1% | 3.202% | 100%
| PM Cost in KEURO | KEURO | 410.041 | 129.6 | 325.843 | 388.834 | 39.823 | 57.6 | 19.66 | 57.6 | 261.04 | 57.602 | 96.206 | 452.858 | 280.836 | 72.006 | 121.086 | 258.451 | 29.534 | 198.206 | 518.464 | 178.967 | 160.924 | 37.008 | 734.432 | 157.49 | 5044.111
| PM Cost in EURO | EURO | 410041 | 129600 | 325843 | 388834 | 39823 | 57600 | 19660 | 57600 | 261040 | 57602 | 96206 | 452858 | 280836 | 72006 | 121086 | 258451 | 29534 | 198206 | 518464 | 178967 | 160924 | 37008 | 734432 | 157490 | 5044111
| 1PM KEURO | KEURO | 10.7906 | 7.2 | 10.8614 | 10.8009 | 2.0959 | 7.2 | 2.4575 | 7.2 | 9.0014 | 7.2002 | 8.0172 | 12.2394 | 10.8014 | 9.0008 | 7.812 | 9.6798 | 2.9534 | 9.9103 | 10.8013 | 8.9483 | 8.9402 | 1.1215 | 10.8005 | 8.7494 |  |  | 8.1076 | Average
Effort Breakdown per task (Cost in KEURO) Month: 1 - 24
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 86.3244 | 28.8 | 76.03 | 108.0094 | 6.2878 | 7.2 | 2.4575 | 7.2 | 54.0083 | 7.2002 | 24.0515 | 134.6335 | 32.4042 | 9.0008 | 31.248 | 77.4385 | 2.9534 | 49.5515 | 162.02 | 71.5868 | 53.6413 | 7.8502 | 151.2066 | 43.7472 | 1234.8512 | 24.48% | 1234.8512
T1.1 | Definition of content to be provided | IMAC | 10.7906 | 7.2 |  | 21.6019 | 4.1919 | 7.2 | 2.4575 | 7.2 | 9.0014 | 7.2002 | 8.0172 |  | 10.8014 | 9.0008 | 15.624 |  | 2.9534 | 9.9103 | 10.8013 |  |  | 2.2429 |  |  | 146.1947 | 2.898% | 146.1947 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | 10.7906 | 7.2 |  | 21.6019 | 2.0959 |  |  |  | 9.0014 |  | 8.0172 |  |  |  | 15.624 |  |  | 9.9103 | 10.8013 |  |  | 2.2429 |  |  | 97.2855 | 1.929% | 97.2855 | D1 | 50%
T1.3 | Identification of standards to be used | IAT |  |  | 10.8614 | [8 empty] | 12.2394 | [5 empty] | 19.8206 | 10.8013 |  |  |  | 21.6009 |  | 75.3237 | 1.493% | 75.3237 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | 43.1622 | 7.2 | 65.1686 | 21.6019 |  |  |  |  | 36.0055 |  |  | 122.3941 | 21.6028 |  |  | 77.4385 |  |  | 129.616 | 71.5868 | 53.6413 |  | 108.0047 |  | 757.4224 | 15.02% | 757.4224 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | 10.7906 | [16 empty] | 9.9103 |  |  |  | 1.1215 |  | 8.7494 | 30.5718 | 0.6061% | 30.5718 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | 10.7906 |  |  | 21.6019 | [6 empty] | 8.0172 | [10 empty] | 1.1215 | 21.6009 | 17.4989 | 80.6309 | 1.599% | 80.6309 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC |  | 7.2 |  | 21.6019 | [17 empty] | 1.1215 |  | 17.4989 | 47.4222 | 0.9402% | 47.4222 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 107.9055 | 28.8 | 65.1686 | 97.2085 | 6.2878 | 14.4 | 4.915 | 14.4 | 54.0083 | 14.4005 | 16.0343 | 122.3941 | 64.8083 | 18.0015 | 42.966 | 77.4385 | 11.8136 | 29.7309 | 129.616 | 53.6901 | 53.6413 | 13.4575 | 151.2066 | 69.9956 | 1262.2885 | 25.02% | 1262.2885
T2.1 | Preparation of Content & Products | IMAC | 10.7906 | 28.8 |  | 32.4028 | 6.2878 | 14.4 | 4.915 | 14.4 | 18.0028 | 14.4005 | 8.0172 |  | 10.8014 | 18.0015 | 42.966 |  | 11.8136 | 19.8206 |  |  |  | 6.7287 |  |  | 262.5485 | 5.205% | 262.5485 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | 75.5339 |  | 65.1686 | 21.6019 |  |  |  |  | 36.0055 |  |  | 122.3941 | 54.0069 |  |  | 77.4385 |  |  | 129.616 | 53.6901 | 53.6413 |  | 129.6056 |  | 818.7024 | 16.23% | 818.7024 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | 10.7906 | [16 empty] | 9.9103 |  |  |  | 2.2429 |  | 17.4989 | 40.4427 | 0.8018% | 40.4427 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | 10.7906 |  |  | 21.6019 | [6 empty] | 8.0172 | [10 empty] | 2.2429 | 21.6009 | 26.2483 | 90.5018 | 1.794% | 90.5018 | D6 | 50%
T2.5 | Market preparation | TINC |  |  |  | 21.6019 | [17 empty] | 2.2429 |  | 26.2483 | 50.0931 | 0.9931% | 50.0931 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 53.9528 | 14.4 | 32.5843 | 54.0047 | 8.3838 | 14.4 | 4.915 | 14.4 | 54.0083 | 14.4005 | 16.0343 | 36.7182 | 64.8083 | 18.0015 | 0 | 64.8547 | 5.9068 | 39.6412 | 97.212 | 26.8451 | 26.8207 | 4.4858 | 151.2066 | 0 | 817.9846 | 16.22% | 817.9846
T3.1 | Validation of the REGNET-Demonstrator | IMAC |  | 7.2 |  | 10.8009 | 2.0959 | 7.2 | 2.4575 | 7.2 | 9.0014 | 7.2002 | 8.0172 |  | 10.8014 | 9.0008 |  |  | 2.9534 | 9.9103 | 10.8013 |  |  | 1.1215 | 32.4014 |  | 138.1632 | 2.739% | 138.1632 | D7 | 50%
T3.2 | Preparation of the Demonstration Phase | VALT | 10.7906 | 7.2 |  | 32.4028 | 6.2878 | 7.2 | 2.4575 | 7.2 | 27.0041 | 7.2002 | 8.0172 |  | 32.4042 | 9.0008 |  |  | 2.9534 | 29.7309 | 32.404 |  |  | 3.3644 | 32.4014 |  | 258.0193 | 5.115% | 258.0193 | D7 | 50%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | 43.1622 |  | 32.5843 | 10.8009 |  |  |  |  | 18.0028 |  |  | 36.7182 | 21.6028 |  |  | 64.8547 |  |  | 54.0067 | 26.8451 | 26.8207 |  | 86.4038 |  | 421.8021 | 8.362% | 421.8021 | D8 | 50%
WP4 | Demonstration, Assessment and Evaluation | TARX | 10.7906 | 36 | 10.8614 | 43.2038 | 12.5757 | 21.6 | 7.3725 | 21.6 | 45.0069 | 21.6008 | 24.0515 | 12.2394 | 54.0069 | 27.0023 | 0 | 9.6798 | 8.8602 | 39.6412 | 54.0067 | 8.9483 | 8.9402 | 6.7287 | 151.2066 | 8.7494 | 644.6729 | 12.78% | 644.6729
T4.1 | Execution of the demonstration phase (trial service) | TARX |  | 36 |  | 32.4028 | 10.4797 | 21.6 | 7.3725 | 21.6 | 27.0041 | 21.6008 | 24.0515 |  | 32.4042 | 27.0023 |  |  | 8.8602 | 29.7309 | 32.404 |  |  | 6.7287 | 32.4014 |  | 371.6431 | 7.368% | 371.6431 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | 10.7906 |  | 10.8614 | [5 empty] | 9.0014 |  |  | 12.2394 | 10.8014 |  |  | 9.6798 |  |  | 10.8013 | 8.9483 | 8.9402 |  | 118.8052 | 8.7494 | 219.6185 | 4.354% | 219.6185 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT |  |  |  | 10.8009 | 2.0959 |  |  |  | 9.0014 |  |  |  | 10.8014 |  |  |  |  | 9.9103 | 10.8013 | [5 empty] | 53.4113 | 1.059% | 53.4113 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 10.7906 | 7.2 | 0 | 10.8009 | 0 | 0 | 0 | 0 | 9.0014 | 0 | 8.0172 | 24.4788 | 10.8014 | 0 | 31.248 | 0 | 0 | 9.9103 | 10.8013 | 0 | 0 | 1.1215 | 43.2019 | 8.7494 | 186.1227 | 3.69% | 186.1227
T5.1 | Development of a Technology implementation plan (draft) | MOT | 10.7906 | [10 empty] | 12.2394 | 10.8014 |  | 15.624 |  |  | 9.9103 | 10.8013 |  |  |  | 21.6009 | 8.7494 | 100.5174 | 1.993% | 100.5174 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 7.2 |  | 10.8009 |  |  |  |  | 9.0014 |  | 8.0172 | 12.2394 |  |  | 15.624 | [6 empty] | 1.1215 | 21.6009 | 0 | 85.6053 | 1.697% | 85.6053 | D12 | 45%
WP6 | Information Dissemination | SPAC | 10.7906 | 7.2 | 10.8614 | 10.8009 | 2.0959 | 0 | 0 | 0 | 9.0014 | 0 | 8.0172 | 12.2394 | 10.8014 | 0 | 15.624 | 0 | 0 | 9.9103 | 10.8013 | 0 | 0 | 1.1215 | 21.6009 | 8.7494 | 149.6157 | 2.966% | 149.6157
T6.1 | Information Dissemination | SPAC | 10.7906 | 7.2 | 10.8614 | 10.8009 | 2.0959 |  |  |  | 9.0014 |  | 8.0172 | 12.2394 | 10.8014 |  | 15.624 |  |  | 9.9103 | 10.8013 |  |  | 1.1215 | 21.6009 | 8.7494 | 149.6157 | 2.966% | 149.6157 | D13 | 45%
WP7 | Project Management | AIT | 129.4866 | 7.2 | 130.3372 | 64.8057 | 4.1919 | 0 | 0 | 0 | 36.0055 | 0 | 0 | 110.1546 | 43.2055 | 0 | 0 | 29.0394 | 0 | 19.8206 | 54.0067 | 17.8967 | 17.8804 | 2.2429 | 64.8028 | 17.4989 | 748.5756 | 14.84% | 748.5756
T7.1 | Project Management | AIT | 129.4866 | 7.2 | 130.3372 | 64.8057 | 4.1919 |  |  |  | 36.0055 |  |  | 36.7182 | 43.2055 |  |  | 29.0394 |  | 19.8206 | 54.0067 | 17.8967 | 17.8804 | 2.2429 | 64.8028 | 17.4989 | 675.1391 | 13.38% | 675.1391 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 73.4364 | [12 empty] | 73.4364 | 1.456% | 73.4364 | D14 | 45%
| Total KEURO |  | 410.041 | 129.6 | 325.843 | 388.834 | 39.823 | 57.6 | 19.66 | 57.6 | 261.04 | 57.602 | 96.206 | 452.858 | 280.836 | 72.006 | 121.086 | 258.451 | 29.534 | 198.206 | 518.464 | 178.967 | 160.924 | 37.008 | 734.432 | 157.49 | 5044.111 | 100% | 5044.111
|  | % | 8.129% | 2.569% | 6.46% | 7.709% | 0.7895% | 1.142% | 0.3898% | 1.142% | 5.175% | 1.142% | 1.907% | 8.978% | 5.568% | 1.428% | 2.401% | 5.124% | 0.5855% | 3.929% | 10.28% | 3.548% | 3.19% | 0.7337% | 14.56% | 3.122% | 100%
Effort Breakdown per task (Cost in KEURO) Month: 1 - 6
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 86.3244 | 28.8 | 76.03 | 108.0094 | 6.2878 | 7.2 | 2.4575 | 7.2 | 54.0083 | 7.2002 | 16.0343 | 134.6335 | 32.4042 | 9.0008 | 31.248 | 77.4385 | 2.9534 | 49.5515 | 162.02 | 71.5868 | 53.6413 | 7.8502 | 151.2066 | 43.7472 | 1226.834 | 24.32% | 1226.834
T1.1 | Definition of content to be provided | IMAC | 10.7906 | 7.2 |  | 21.6019 | 4.1919 | 7.2 | 2.4575 | 7.2 | 9.0014 | 7.2002 | 8.0172 |  | 10.8014 | 9.0008 | 15.624 |  | 2.9534 | 9.9103 | 10.8013 |  |  | 2.2429 |  |  | 146.1947 | 2.898% | 146.1947 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | 10.7906 | 7.2 |  | 21.6019 | 2.0959 |  |  |  | 9.0014 |  | 8.0172 |  |  |  | 15.624 |  |  | 9.9103 | 10.8013 |  |  | 2.2429 |  |  | 97.2855 | 1.929% | 97.2855 | D1 | 50%
T1.3 | Identification of standards to be used | IAT |  |  | 10.8614 | [8 empty] | 12.2394 | [5 empty] | 19.8206 | 10.8013 |  |  |  | 21.6009 |  | 75.3237 | 1.493% | 75.3237 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | 43.1622 | 7.2 | 65.1686 | 21.6019 |  |  |  |  | 36.0055 |  |  | 122.3941 | 21.6028 |  |  | 77.4385 |  |  | 129.616 | 71.5868 | 53.6413 |  | 108.0047 |  | 757.4224 | 15.02% | 757.4224 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | 10.7906 | [16 empty] | 9.9103 |  |  |  | 1.1215 |  | 8.7494 | 30.5718 | 0.6061% | 30.5718 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | 10.7906 |  |  | 21.6019 | [17 empty] | 1.1215 | 21.6009 | 17.4989 | 72.6137 | 1.44% | 72.6137 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC |  | 7.2 |  | 21.6019 | [17 empty] | 1.1215 |  | 17.4989 | 47.4222 | 0.9402% | 47.4222 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T2.1 | Preparation of Content & Products | IMAC | [24 empty] | 0 | 0% | 0 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | [24 empty] | 0 | 0% | 0 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.5 | Market preparation | TINC | [24 empty] | 0 | 0% | 0 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T3.1 | Validation of the REGNET-Demonstrator | IMAC | [24 empty] | 0 | 0% | 0 | D7 | 50%
T3.2 | Preparation of the Demonstration Phase | VALT | [24 empty] | 0 | 0% | 0 | D7 | 50%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | [24 empty] | 0 | 0% | 0 | D8 | 50%
WP4 | Demonstration, Assessment and Evaluation | TARX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T4.1 | Execution of the demonstration phase (trial service) | TARX | [24 empty] | 0 | 0% | 0 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | [24 empty] | 0 | 0% | 0 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT | [24 empty] | 0 | 0% | 0 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 2.6976 | 1.8 | 0 | 2.7002 | 0 | 0 | 0 | 0 | 2.2503 | 0 | 2.0043 | 6.1197 | 2.7003 | 0 | 7.812 | 0 | 0 | 2.4776 | 2.7003 | 0 | 0 | 0.28036 | 10.8005 | 2.1874 | 46.5307 | 0.9225% | 46.5307
T5.1 | Development of a Technology implementation plan (draft) | MOT | 2.6976 | [10 empty] | 3.0599 | 2.7003 |  | 3.906 |  |  | 2.4776 | 2.7003 |  |  |  | 5.4002 | 2.1874 | 25.1293 | 0.4982% | 25.1293 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 1.8 |  | 2.7002 |  |  |  |  | 2.2503 |  | 2.0043 | 3.0599 |  |  | 3.906 | [6 empty] | 0.28036 | 5.4002 |  | 21.4013 | 0.4243% | 21.4013 | D12 | 45%
WP6 | Information Dissemination | SPAC | 2.6976 | 1.8 | 2.7154 | 2.7002 | 0.52399 | 0 | 0 | 0 | 2.2503 | 0 | 2.0043 | 3.0599 | 2.7003 | 0 | 3.906 | 0 | 0 | 2.4776 | 2.7003 | 0 | 0 | 0.28036 | 5.4002 | 2.1874 | 37.4039 | 0.7415% | 37.4039
T6.1 | Information Dissemination | SPAC | 2.6976 | 1.8 | 2.7154 | 2.7002 | 0.52399 |  |  |  | 2.2503 |  | 2.0043 | 3.0599 | 2.7003 |  | 3.906 |  |  | 2.4776 | 2.7003 |  |  | 0.28036 | 5.4002 | 2.1874 | 37.4039 | 0.7415% | 37.4039 | D13 | 45%
WP7 | Project Management | AIT | 32.3717 | 1.8 | 32.5843 | 16.2014 | 1.048 | 0 | 0 | 0 | 9.0014 | 0 | 0 | 27.5387 | 10.8014 | 0 | 0 | 7.2599 | 0 | 4.9551 | 13.5017 | 4.4742 | 4.4701 | 0.56073 | 16.2007 | 4.3747 | 187.1439 | 3.71% | 187.1439
T7.1 | Project Management | AIT | 32.3717 | 1.8 | 32.5843 | 16.2014 | 1.048 |  |  |  | 9.0014 |  |  | 9.1796 | 10.8014 |  |  | 7.2599 |  | 4.9551 | 13.5017 | 4.4742 | 4.4701 | 0.56073 | 16.2007 | 4.3747 | 168.7848 | 3.346% | 168.7848 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 18.3591 | [12 empty] | 18.3591 | 0.364% | 18.3591 | D14 | 45%
| Total KEURO |  | 124.0914 | 34.2 | 111.3297 | 129.6113 | 7.8598 | 7.2 | 2.4575 | 7.2 | 67.5103 | 7.2002 | 20.0429 | 171.3517 | 48.6062 | 9.0008 | 42.966 | 84.6984 | 2.9534 | 59.4618 | 180.9223 | 76.061 | 58.1114 | 8.9716 | 183.608 | 52.4967 | 1497.9125 | 29.7% | 1497.9125
|  | % | 2.46% | 0.678% | 2.207% | 2.57% | 0.1558% | 0.1427% | 0.04872% | 0.1427% | 1.338% | 0.1427% | 0.3974% | 3.397% | 0.9636% | 0.1784% | 0.8518% | 1.679% | 0.05855% | 1.179% | 3.587% | 1.508% | 1.152% | 0.1779% | 3.64% | 1.041% | 29.7%
Effort Breakdown per task (Cost in KEURO) Month: 7 - 12
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T1.1 | Definition of content to be provided | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.3 | Identification of standards to be used | IAT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC | [24 empty] | 0 | 0% | 0 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 107.9055 | 28.8 | 65.1686 | 97.2085 | 6.2878 | 14.4 | 4.915 | 14.4 | 54.0083 | 14.4005 | 16.0343 | 122.3941 | 64.8083 | 18.0015 | 42.966 | 77.4385 | 11.8136 | 29.7309 | 129.616 | 53.6901 | 53.6413 | 13.4575 | 151.2066 | 69.9956 | 1262.2885 | 25.02% | 1262.2885
T2.1 | Preparation of Content & Products | IMAC | 10.7906 | 28.8 |  | 32.4028 | 6.2878 | 14.4 | 4.915 | 14.4 | 18.0028 | 14.4005 | 8.0172 |  | 10.8014 | 18.0015 | 42.966 |  | 11.8136 | 19.8206 |  |  |  | 6.7287 |  |  | 262.5485 | 5.205% | 262.5485 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | 75.5339 |  | 65.1686 | 21.6019 |  |  |  |  | 36.0055 |  |  | 122.3941 | 54.0069 |  |  | 77.4385 |  |  | 129.616 | 53.6901 | 53.6413 |  | 129.6056 |  | 818.7024 | 16.23% | 818.7024 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | 10.7906 | [16 empty] | 9.9103 |  |  |  | 2.2429 |  | 17.4989 | 40.4427 | 0.8018% | 40.4427 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | 10.7906 |  |  | 21.6019 | [6 empty] | 8.0172 | [10 empty] | 2.2429 | 21.6009 | 26.2483 | 90.5018 | 1.794% | 90.5018 | D6 | 50%
T2.5 | Market preparation | TINC |  |  |  | 21.6019 | [17 empty] | 2.2429 |  | 26.2483 | 50.0931 | 0.9931% | 50.0931 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T3.1 | Validation of the REGNET-Demonstrator | IMAC | [24 empty] | 0 | 0% | 0 | D7 | 50%
T3.2 | Preparation of the Demonstration Phase | VALT | [24 empty] | 0 | 0% | 0 | D7 | 50%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | [24 empty] | 0 | 0% | 0 | D8 | 50%
WP4 | Demonstration, Assessment and Evaluation | TARX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T4.1 | Execution of the demonstration phase (trial service) | TARX | [24 empty] | 0 | 0% | 0 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | [24 empty] | 0 | 0% | 0 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT | [24 empty] | 0 | 0% | 0 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 2.6976 | 1.8 | 0 | 2.7002 | 0 | 0 | 0 | 0 | 2.2503 | 0 | 2.0043 | 6.1197 | 2.7003 | 0 | 7.812 | 0 | 0 | 2.4776 | 2.7003 | 0 | 0 | 0.28036 | 10.8005 | 2.1874 | 46.5307 | 0.9225% | 46.5307
T5.1 | Development of a Technology implementation plan (draft) | MOT | 2.6976 | [10 empty] | 3.0599 | 2.7003 |  | 3.906 |  |  | 2.4776 | 2.7003 |  |  |  | 5.4002 | 2.1874 | 25.1293 | 0.4982% | 25.1293 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 1.8 |  | 2.7002 |  |  |  |  | 2.2503 |  | 2.0043 | 3.0599 |  |  | 3.906 | [6 empty] | 0.28036 | 5.4002 |  | 21.4013 | 0.4243% | 21.4013 | D12 | 45%
WP6 | Information Dissemination | SPAC | 2.6976 | 1.8 | 2.7154 | 2.7002 | 0.52399 | 0 | 0 | 0 | 2.2503 | 0 | 2.0043 | 3.0599 | 2.7003 | 0 | 3.906 | 0 | 0 | 2.4776 | 2.7003 | 0 | 0 | 0.28036 | 5.4002 | 2.1874 | 37.4039 | 0.7415% | 37.4039
T6.1 | Information Dissemination | SPAC | 2.6976 | 1.8 | 2.7154 | 2.7002 | 0.52399 |  |  |  | 2.2503 |  | 2.0043 | 3.0599 | 2.7003 |  | 3.906 |  |  | 2.4776 | 2.7003 |  |  | 0.28036 | 5.4002 | 2.1874 | 37.4039 | 0.7415% | 37.4039 | D13 | 45%
WP7 | Project Management | AIT | 32.3717 | 1.8 | 32.5843 | 16.2014 | 1.048 | 0 | 0 | 0 | 9.0014 | 0 | 0 | 27.5387 | 10.8014 | 0 | 0 | 7.2599 | 0 | 4.9551 | 13.5017 | 4.4742 | 4.4701 | 0.56073 | 16.2007 | 4.3747 | 187.1439 | 3.71% | 187.1439
T7.1 | Project Management | AIT | 32.3717 | 1.8 | 32.5843 | 16.2014 | 1.048 |  |  |  | 9.0014 |  |  | 9.1796 | 10.8014 |  |  | 7.2599 |  | 4.9551 | 13.5017 | 4.4742 | 4.4701 | 0.56073 | 16.2007 | 4.3747 | 168.7848 | 3.346% | 168.7848 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 18.3591 | [12 empty] | 18.3591 | 0.364% | 18.3591 | D14 | 45%
| Total KEURO |  | 145.6725 | 34.2 | 100.4683 | 118.8104 | 7.8598 | 14.4 | 4.915 | 14.4 | 67.5103 | 14.4005 | 20.0429 | 159.1123 | 81.0104 | 18.0015 | 54.684 | 84.6984 | 11.8136 | 39.6412 | 148.5183 | 58.1643 | 58.1114 | 14.5789 | 183.608 | 78.745 | 1533.367 | 30.4% | 1533.367
|  | % | 2.888% | 0.678% | 1.992% | 2.355% | 0.1558% | 0.2855% | 0.09744% | 0.2855% | 1.338% | 0.2855% | 0.3974% | 3.154% | 1.606% | 0.3569% | 1.084% | 1.679% | 0.2342% | 0.7859% | 2.944% | 1.153% | 1.152% | 0.289% | 3.64% | 1.561% | 30.4%
Effort Breakdown per task (Cost in KEURO) Month: 13 - 18
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T1.1 | Definition of content to be provided | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.3 | Identification of standards to be used | IAT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC | [24 empty] | 0 | 0% | 0 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T2.1 | Preparation of Content & Products | IMAC | [24 empty] | 0 | 0% | 0 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | [24 empty] | 0 | 0% | 0 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.5 | Market preparation | TINC | [24 empty] | 0 | 0% | 0 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 53.9528 | 14.4 | 32.5843 | 54.0047 | 8.3838 | 14.4 | 4.915 | 14.4 | 54.0083 | 14.4005 | 16.0343 | 36.7182 | 64.8083 | 18.0015 | 0 | 64.8547 | 5.9068 | 39.6412 | 97.212 | 26.8451 | 26.8207 | 4.4858 | 151.2066 | 0 | 817.9846 | 16.22% | 817.9846
T3.1 | Validation of the REGNET-Demonstrator | IMAC |  | 7.2 |  | 10.8009 | 2.0959 | 7.2 | 2.4575 | 7.2 | 9.0014 | 7.2002 | 8.0172 |  | 10.8014 | 9.0008 |  |  | 2.9534 | 9.9103 | 10.8013 |  |  | 1.1215 | 32.4014 |  | 138.1632 | 2.739% | 138.1632 | D7 | 50%
T3.2 | Preparation of the Demonstration Phase | VALT | 10.7906 | 7.2 |  | 32.4028 | 6.2878 | 7.2 | 2.4575 | 7.2 | 27.0041 | 7.2002 | 8.0172 |  | 32.4042 | 9.0008 |  |  | 2.9534 | 29.7309 | 32.404 |  |  | 3.3644 | 32.4014 |  | 258.0193 | 5.115% | 258.0193 | D7 | 50%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | 43.1622 |  | 32.5843 | 10.8009 |  |  |  |  | 18.0028 |  |  | 36.7182 | 21.6028 |  |  | 64.8547 |  |  | 54.0067 | 26.8451 | 26.8207 |  | 86.4038 |  | 421.8021 | 8.362% | 421.8021 | D8 | 50%
WP4 | Demonstration, Assessment and Evaluation | TARX | 5.3953 | 18 | 5.4307 | 16.2014 | 5.2399 | 10.8 | 3.6862 | 10.8 | 18.0028 | 10.8004 | 12.0258 | 6.1197 | 21.6028 | 13.5011 | 0 | 4.8399 | 4.4301 | 14.8654 | 21.6027 | 4.4742 | 4.4701 | 3.3644 | 75.6033 | 4.3747 | 295.6308 | 5.861% | 295.6308
T4.1 | Execution of the demonstration phase (trial service) | TARX |  | 18 |  | 16.2014 | 5.2399 | 10.8 | 3.6862 | 10.8 | 13.5021 | 10.8004 | 12.0258 |  | 16.2021 | 13.5011 |  |  | 4.4301 | 14.8654 | 16.202 |  |  | 3.3644 | 16.2007 |  | 185.8216 | 3.684% | 185.8216 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | 5.3953 |  | 5.4307 | [5 empty] | 4.5007 |  |  | 6.1197 | 5.4007 |  |  | 4.8399 |  |  | 5.4007 | 4.4742 | 4.4701 |  | 59.4026 | 4.3747 | 109.8092 | 2.177% | 109.8092 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT | [24 empty] | 0 | 0% | 0 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 2.6976 | 1.8 | 0 | 2.7002 | 0 | 0 | 0 | 0 | 2.2503 | 0 | 2.0043 | 6.1197 | 2.7003 | 0 | 7.812 | 0 | 0 | 2.4776 | 2.7003 | 0 | 0 | 0.28036 | 10.8005 | 2.1874 | 46.5307 | 0.9225% | 46.5307
T5.1 | Development of a Technology implementation plan (draft) | MOT | 2.6976 | [10 empty] | 3.0599 | 2.7003 |  | 3.906 |  |  | 2.4776 | 2.7003 |  |  |  | 5.4002 | 2.1874 | 25.1293 | 0.4982% | 25.1293 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 1.8 |  | 2.7002 |  |  |  |  | 2.2503 |  | 2.0043 | 3.0599 |  |  | 3.906 | [6 empty] | 0.28036 | 5.4002 |  | 21.4013 | 0.4243% | 21.4013 | D12 | 45%
WP6 | Information Dissemination | SPAC | 2.6976 | 1.8 | 2.7154 | 2.7002 | 0.52399 | 0 | 0 | 0 | 2.2503 | 0 | 2.0043 | 3.0599 | 2.7003 | 0 | 3.906 | 0 | 0 | 2.4776 | 2.7003 | 0 | 0 | 0.28036 | 5.4002 | 2.1874 | 37.4039 | 0.7415% | 37.4039
T6.1 | Information Dissemination | SPAC | 2.6976 | 1.8 | 2.7154 | 2.7002 | 0.52399 |  |  |  | 2.2503 |  | 2.0043 | 3.0599 | 2.7003 |  | 3.906 |  |  | 2.4776 | 2.7003 |  |  | 0.28036 | 5.4002 | 2.1874 | 37.4039 | 0.7415% | 37.4039 | D13 | 45%
WP7 | Project Management | AIT | 32.3717 | 1.8 | 32.5843 | 16.2014 | 1.048 | 0 | 0 | 0 | 9.0014 | 0 | 0 | 27.5387 | 10.8014 | 0 | 0 | 7.2599 | 0 | 4.9551 | 13.5017 | 4.4742 | 4.4701 | 0.56073 | 16.2007 | 4.3747 | 187.1439 | 3.71% | 187.1439
T7.1 | Project Management | AIT | 32.3717 | 1.8 | 32.5843 | 16.2014 | 1.048 |  |  |  | 9.0014 |  |  | 9.1796 | 10.8014 |  |  | 7.2599 |  | 4.9551 | 13.5017 | 4.4742 | 4.4701 | 0.56073 | 16.2007 | 4.3747 | 168.7848 | 3.346% | 168.7848 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 18.3591 | [12 empty] | 18.3591 | 0.364% | 18.3591 | D14 | 45%
| Total KEURO |  | 97.115 | 37.8 | 73.3147 | 91.808 | 15.1956 | 25.2 | 8.6013 | 25.2 | 85.5131 | 25.2009 | 32.0687 | 79.5561 | 102.6132 | 31.5026 | 11.718 | 76.9545 | 10.3369 | 64.4169 | 137.717 | 35.7934 | 35.7609 | 8.9716 | 259.2113 | 13.1242 | 1384.6939 | 27.45% | 1384.6939
|  | % | 1.925% | 0.7494% | 1.453% | 1.82% | 0.3013% | 0.4996% | 0.1705% | 0.4996% | 1.695% | 0.4996% | 0.6358% | 1.577% | 2.034% | 0.6245% | 0.2323% | 1.526% | 0.2049% | 1.277% | 2.73% | 0.7096% | 0.709% | 0.1779% | 5.139% | 0.2602% | 27.45%
Effort Breakdown per task (Cost in KEURO) Month: 19 - 24
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | TOTAL |  | Cost
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | CERTH | ICCS | VALT | TINC | TASK | % | KEURO | Del. | Fund.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T1.1 | Definition of content to be provided | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | [24 empty] | 0 | 0% | 0 | D1 | 50%
T1.3 | Identification of standards to be used | IAT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.4 | Development of the System Specifications | VALT | [24 empty] | 0 | 0% | 0 | D2 | 50%
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.6 | Definition of supported Business Functions | VALT | [24 empty] | 0 | 0% | 0 | D3 | 50%
T1.7 | Identification of Market (Segments) and User Groups | TINC | [24 empty] | 0 | 0% | 0 | D3 | 50%
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T2.1 | Preparation of Content & Products | IMAC | [24 empty] | 0 | 0% | 0 | D4 | 50%
T2.2 | System Implementation (1. Version) | ZEUS | [24 empty] | 0 | 0% | 0 | D5 | 50%
T2.3 | Setup of the legal framework | AIT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.4 | Business process (re-) engineering | VALT | [24 empty] | 0 | 0% | 0 | D6 | 50%
T2.5 | Market preparation | TINC | [24 empty] | 0 | 0% | 0 | D6 | 50%
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
T3.1 | Validation of the REGNET-Demonstrator | IMAC | [24 empty] | 0 | 0% | 0 | D7 | 50%
T3.2 | Preparation of the Demonstration Phase | VALT | [24 empty] | 0 | 0% | 0 | D7 | 50%
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | [24 empty] | 0 | 0% | 0 | D8 | 50%
WP4 | Demonstration, Assessment and Evaluation | TARX | 5.3953 | 18 | 5.4307 | 27.0024 | 7.3358 | 10.8 | 3.6862 | 10.8 | 27.0041 | 10.8004 | 12.0258 | 6.1197 | 32.4042 | 13.5011 | 0 | 4.8399 | 4.4301 | 24.7757 | 32.404 | 4.4742 | 4.4701 | 3.3644 | 75.6033 | 4.3747 | 349.0421 | 6.92% | 349.0421
T4.1 | Execution of the demonstration phase (trial service) | TARX |  | 18 |  | 16.2014 | 5.2399 | 10.8 | 3.6862 | 10.8 | 13.5021 | 10.8004 | 12.0258 |  | 16.2021 | 13.5011 |  |  | 4.4301 | 14.8654 | 16.202 |  |  | 3.3644 | 16.2007 |  | 185.8216 | 3.684% | 185.8216 | D9 | 35%
T4.2 | Refinement of system and services where appropriate and necessary | VALT | 5.3953 |  | 5.4307 | [5 empty] | 4.5007 |  |  | 6.1197 | 5.4007 |  |  | 4.8399 |  |  | 5.4007 | 4.4742 | 4.4701 | 0 | 59.4026 | 4.3747 | 109.8092 | 2.177% | 109.8092 | D10 | 35%
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT |  |  |  | 10.8009 | 2.0959 |  |  |  | 9.0014 |  |  |  | 10.8014 |  |  |  |  | 9.9103 | 10.8013 | [5 empty] | 53.4113 | 1.059% | 53.4113 | D11 | 35%
WP5 | Development of an exploitation plan | MOT | 2.6976 | 1.8 | 0 | 2.7002 | 0 | 0 | 0 | 0 | 2.2503 | 0 | 2.0043 | 6.1197 | 2.7003 | 0 | 7.812 | 0 | 0 | 2.4776 | 2.7003 | 0 | 0 | 0.28036 | 10.8005 | 2.1874 | 46.5307 | 0.9225% | 46.5307
T5.1 | Development of a Technology implementation plan (draft) | MOT | 2.6976 | [10 empty] | 3.0599 | 2.7003 |  | 3.906 |  |  | 2.4776 | 2.7003 |  |  |  | 5.4002 | 2.1874 | 25.1293 | 0.4982% | 25.1293 | D12 | 45%
T5.2 | Development of a Technology implementation plan (final) |  |  | 1.8 |  | 2.7002 |  |  |  |  | 2.2503 |  | 2.0043 | 3.0599 |  |  | 3.906 | [6 empty] | 0.28036 | 5.4002 |  | 21.4013 | 0.4243% | 21.4013 | D12 | 45%
WP6 | Information Dissemination | SPAC | 2.6976 | 1.8 | 2.7154 | 2.7002 | 0.52399 | 0 | 0 | 0 | 2.2503 | 0 | 2.0043 | 3.0599 | 2.7003 | 0 | 3.906 | 0 | 0 | 2.4776 | 2.7003 | 0 | 0 | 0.28036 | 5.4002 | 2.1874 | 37.4039 | 0.7415% | 37.4039
T6.1 | Information Dissemination | SPAC | 2.6976 | 1.8 | 2.7154 | 2.7002 | 0.52399 |  |  |  | 2.2503 |  | 2.0043 | 3.0599 | 2.7003 |  | 3.906 |  |  | 2.4776 | 2.7003 |  |  | 0.28036 | 5.4002 | 2.1874 | 37.4039 | 0.7415% | 37.4039 | D13 | 45%
WP7 | Project Management | AIT | 32.3717 | 1.8 | 32.5843 | 16.2014 | 1.048 | 0 | 0 | 0 | 9.0014 | 0 | 0 | 27.5387 | 10.8014 | 0 | 0 | 7.2599 | 0 | 4.9551 | 13.5017 | 4.4742 | 4.4701 | 0.56073 | 16.2007 | 4.3747 | 187.1439 | 3.71% | 187.1439
T7.1 | Project Management | AIT | 32.3717 | 1.8 | 32.5843 | 16.2014 | 1.048 |  |  |  | 9.0014 |  |  | 9.1796 | 10.8014 |  |  | 7.2599 |  | 4.9551 | 13.5017 | 4.4742 | 4.4701 | 0.56073 | 16.2007 | 4.3747 | 168.7848 | 3.346% | 168.7848 | D15-17 | 45%
T7.2 | Quality Assurance | MOT | [11 empty] | 18.3591 | [12 empty] | 18.3591 | 0.364% | 18.3591 | D14 | 45%
| Total KEURO |  | 43.1622 | 23.4 | 40.7304 | 48.6043 | 8.9078 | 10.8 | 3.6862 | 10.8 | 40.5062 | 10.8004 | 16.0343 | 42.8379 | 48.6062 | 13.5011 | 11.718 | 12.0998 | 4.4301 | 34.6861 | 51.3063 | 8.9483 | 8.9402 | 4.4858 | 108.0047 | 13.1242 | 620.1206 | 12.29% | 620.1206
|  | % | 0.8557% | 0.4639% | 0.8075% | 0.9636% | 0.1766% | 0.2141% | 0.07308% | 0.2141% | 0.803% | 0.2141% | 0.3179% | 0.8493% | 0.9636% | 0.2677% | 0.2323% | 0.2399% | 0.08783% | 0.6877% | 1.017% | 0.1774% | 0.1772% | 0.08893% | 2.141% | 0.2602% | 12.29%