## Tabelle1
REGNET - Budget: 1.Draft (9.5.2000) in EURO
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
|  | Duration | Start | End | Phase | Funding | Lead | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
| Monthly Rate | [6 empty] | 6000 | 4000 | 6000 | 6000 | 4000 | 4000 | 4000 | 4000 | 5000 | 4000 | 4000 | 4000 | 6000 | 5000 | 5000 | 6000 | 4000 | 5000 | 6000 | 5000 | 5000 | 2000 | 2000 | 6000 | 5000 | 6000
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP1 | Analysis of the State of the Art and Development of Concepts | 6 | 1 | 6 | 1 |  | ZEUS | 15 | 1 | 6 | 10 | 2 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 9 | 1 | 2 | 8 | 1 | 5 | 15 | 8 | 6 | 7 | 2 | 18 | 5 | 11 | 144 | 144 | WP1 | Analysis of the State...
T1.1 | Def.of Content | 3 | 1 | 3 |  | 50% | IMAC | 1 | 1 |  | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 | 1 |  |  |  |  | 20 | T1.1 | Def.of Content
T1.2 | Doc&Dig.Plan | 3 | 4 | 6 |  | 50% | IMAC | AIT S: 1; IMAC S,C: 2; SUL C,B: 1; TARX C,S,B: 1; SPAC S: 1; CC C,B: 1; IAT S,B: 1; ZEUS S: 1; ICCS C,S: 1; SUSU C,S: 1 |  | 11 | T1.2 | Doc&Dig.Plan
T1.3 | Ident.of.Standards | 2 | 1 | 2 |  | 50% | IAT | AIT S: 1; SPAC S: 1; IAT S,B: 2; ZEUS S: 1; VALT S: 2; MOT S: 1 |  | 8 | T1.3 | Ident.of.Standards
T1.4.1 | Repository | 4 | 3 | 6 |  | 50% | TARX | AIT S: 1; IMAC S,C: 2; TARX C,S,B: 2; SIE S: 2; ITI C,S: 2; ICCS C,S: 2 |  | 11 | T1.4.1 | Repository
T1.4.2 | Reference System | 4 | 3 | 6 |  | 50% | AIT | AIT S: 4; SIE S: 2 |  | 6 | T1.4.2 | Reference System
T1.4.3 | Knowledge Base | 4 | 3 | 6 |  | 50% | ITI | AIT S: 2; ZEUS S: 1; SI SI: 2; ITI C,S: 4; VALT S: 2 |  | 11 | T1.4.3 | Knowledge Base
T1.4.4 | Data Generation | 4 | 3 | 6 |  | 50% | SPAC | AIT S: 2; TARX C,S,B: 2; SPAC S: 4; MOT S: 2 |  | 10 | T1.4.4 | Data Generation
T1.4.5 | Search System | 4 | 3 | 6 |  | 50% | SIE | AIT S: 1; SIE S: 4; SI SI: 2; MOT S: 2 |  | 9 | T1.4.5 | Search System
T1.4.6 | e-Business | 4 | 3 | 6 |  | 50% | ZEUS | ZEUS S: 4; VALT S: 4; MOT S: 2 |  | 10 | T1.4.6 | e-Business
T1.4.7 | Product Catalogue | 4 | 3 | 6 |  | 50% | ZEUS | ZEUS S: 2; VALT S: 2 |  | 4 | T1.4.7 | Product Catalogue
T1.4.8 | Production Process | 4 | 3 | 6 |  | 50% | TZ | TZ S: 4; SPAC S: 2 |  | 6 | T1.4.8 | Production Process
T1.4.9 | Products and Services | 4 | 3 | 6 |  | 50% | ZEUS | TZ S: 2; ZEUS S: 2 |  | 4 | T1.4.9 | Products and Services
T1.4.10 | GUI/Portals | 4 | 3 | 6 |  | 50% | MOT | ZEUS S: 2; ICCS C,S: 2; MOT S: 2 |  | 6 | T1.4.10 | GUI/Portals
T1.4.11 | Data Management | 4 | 3 | 6 |  | 50% | SI | SI SI: 4; MOT S: 2 |  | 6 | T1.4.11 | Data Management
T1.4.12 | Core System | 4 | 3 | 6 |  | 50% | VALT | ZEUS S: 1; VALT S: 4 |  | 5 | T1.4.12 | Core System
T1.4.13 | Implementation Platform | 4 | 3 | 6 |  | 50% | VALT | VALT S: 2 |  | 2 | T1.4.13 | Implementation Platform
T1.5 | Dev.of Legal FW | 3 | 4 | 6 |  | 50% | AIT | AIT S: 2; IAT S,B: 1; TINC S: 1 |  | 4 | T1.5 | Dev.of Legal FW
T1.6 | Def.of supp.Bus.Fct | 3 | 1 | 3 |  | 50% | VALT | IMAC S,C: 2; VALT S: 2; TINC S: 2 |  | 6 | T1.6 | Def.of supp.Bus.Fct
T1.7 | Ident.of.Market/User Gr. | 3 | 1 | 3 |  | 50% | TINC | IMAC S,C: 2; ICCS C,S: 1; TINC S: 2 |  | 5 | T1.7 | Ident.of.Market/User Gr.
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | S | C,S | C,S | C,S | S | S | S
WP2 | Implementation of the System and Preparation of Services and Product Generation | 6 | 7 | 12 | 1 |  | VALT | 22 | 2 | 9 | 10 | 2 | 2 | 2 | 2 | 8 | 2 | 2 | 2 | 11 | 2 | 4 | 12 | 4 | 3 | 17 | 9 | 9 | 12 | 2 | 22 | 8 | 15 | 195 | 195 | WP2 | Implementation of the....
T2.1 | Preparation of Content & Products | 6 | 7 | 12 |  | 50% | IMAC | 2 | 2 |  | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 |  | 4 | 2 |  |  |  | 4 | 2 |  |  |  |  | 43 | T2.1 | Preparation of Content & Products
T2.2.1 | Repository | 6 | 7 | 12 |  | 50% | TARX | AIT S: 3; 2 IMAC S,C: 3; 2 TARX C,S,B: 3; 2 SIE S: 3; 2 ITI C,S: 3; 1 ICCS C,S: 3 |  | 18 | T2.2.1 | Repository
T2.2.2 | Reference System | 6 | 7 | 12 |  | 50% | AIT | AIT S: 6; 2 SIE S: 3 |  | 9 | T2.2.2 | Reference System
T2.2.3 | Knowledge Base | 6 | 7 | 12 |  | 50% | ITI | AIT S: 3; 2 ZEUS S: 2; 2 SI S: 3; 2 ITI C,S: 6; 1 VALT S: 2 |  | 16 | T2.2.3 | Knowledge Base
T2.2.4 | Data Generation | 6 | 7 | 12 |  | 50% | SPAC | AIT S: 3; 2 TARX C,S,B: 3; 2 SPAC S: 6; 2 MOT S: 2 |  | 14 | T2.2.4 | Data Generation
T2.2.5 | Search System | 6 | 7 | 12 |  | 50% | SIE | AIT S: 3; 2 SIE S: 6; 2 SI S: 3; 2 MOT S: 2 |  | 14 | T2.2.5 | Search System
T2.2.6 | e-Business | 6 | 7 | 12 |  | 50% | ZEUS | 2 ZEUS S: 6; 1 VALT S: 6; 2 MOT S: 2 |  | 14 | T2.2.6 | e-Business
T2.2.7 | Product Catalogue | 6 | 7 | 12 |  | 50% | ZEUS | 2 ZEUS S: 3; 1 VALT S: 3 |  | 6 | T2.2.7 | Product Catalogue
T2.2.8 | Production Process | 6 | 7 | 12 |  | 50% | TZ | TZ S: 6; 2 SPAC S: 3 |  | 9 | T2.2.8 | Production Process
T2.2.9 | Products ans Services | 6 | 7 | 12 |  | 50% | ZEUS | TZ S: 3; 2 ZEUS S: 2 |  | 5 | T2.2.9 | Products ans Services
T2.2.10 | GUI/Portals | 6 | 7 | 12 |  | 50% | MOT | 2 ZEUS S: 3; 1 ICCS C,S: 3; 2 MOT S: 6 |  | 12 | T2.2.10 | GUI/Portals
T2.2.11 | Data Management | 6 | 7 | 12 |  | 50% | SI | 2 SI S: 3; 2 MOT S: 3 |  | 6 | T2.2.11 | Data Management
T2.2.12 | Core System | 2 | 7 | 8 |  | 50% | VALT | 2 ZEUS S: 1; 1 VALT S: 4 |  | 5 | T2.2.12 | Core System
T2.2.13 | System Integration | 2 | 11 | 12 |  | 50% | VALT | 1 VALT S: 4 |  | 4 | T2.2.13 | System Integration
T2.3 | Contracts&Partnerships | 6 | 7 | 12 |  | 50% | AIT | AIT S: 2; 2 IAT S,B: 1; 2 TINC S: 2 |  | 5 | T2.3 | Contracts&Partnerships
T2.4 | Business Process | 6 | 7 | 12 |  | 50% | VALT | 2 IMAC S,C: 2; 1 VALT S: 3; 2 TINC S: 3 |  | 8 | T2.4 | Business Process
T2.5 | Market Engineering | 6 | 7 | 12 |  | 50% | TINC | 2 IMAC S,C: 2; 1 ICCS C,S: 2; 2 TINC S: 3 |  | 7 | T2.5 | Market Engineering
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP3 | Validation and Preparation | 3 | 13 | 15 | 1 |  | IMAC | 4 | 1 | 0 | 4 | 2 | 2 | 2 | 2 | 4 | 2 | 2 | 2 | 4 | 2 | 2 | 0 | 2 | 4 | 4 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 52 | 52 | WP3 | Validation and Preparation
T3.1 | Validation of demonstrator | 3 | 13 | 15 |  | 50% | IMAC | [27 empty] | 19 | T3.1 | Validation of demonstrator | bar: AIT S to ONB C,B,S; 2 IMAC S,C to 2 CC C,B; 2 GRAN C,B to 2 ZEUS S; 2 ICCS C,S to 2 SUSU C,S
T3.2 | Preparation of demonstration | 3 | 13 | 15 |  | 50% | VALT | 3 |  |  | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 |  | 1 | 3 | 3 |  |  | 3 | 2 |  |  |  |  | 33 | T3.2 | Preparation of demonstration
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP4 | Demonstration | 8 | 16 | 23 | 2 |  | TARX | 4 | 3 | 1 | 4 | 4 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 5 | 3 | 5 | 1 | 3 | 4 | 5 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 77 | 77 | WP4 | Demonstration
T4.1 | Demonstration | 6 | 16 | 21 |  | 35% | TARX | 3 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 | 3 |  |  | 3 | 3 |  |  |  |  | 57 | T4.1 | Demonstration
T4.2 | System Modification | 6 | 16 | 21 |  | 35% | VALT | AIT S: 1; TZ S: 1; TARX C,S,B: 1; SPAC S: 1; SIE S: 1; ZEUS S: 1; SI SI: 1; ITI C,S: 1; VALT S: 2; TINC S: 1; MOT S: 1 |  | 12 | T4.2 | System Modification
T4.3 | Analysis | 2 | 22 | 23 |  | 35% | CC | IMAC S,C: 1; SUL C,B: 1; TARX C,S,B: 1; SPAC S: 1; CC C,B: 2; IAT S,B: 1; ZEUS S: 1 |  | 8 | T4.3 | Analysis
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP5 | Development of an exploitation plan | 18 | 7 | 24 | all |  | MOT | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 2 | 12 | 12 | WP5 | Development of an exploitation plan
T5.1 | Dev.of Exploitation Plan |  |  |  |  | 50% | MOT | AIT S: 1; 1 IMAC S,C: 1; 1 TARX C,S,B: 1; 1 SPAC S: 1; 2 CC C,B: 1; 1 IAT S,B: 1; 1 ZEUS S: 1; 1 ICCS C,S: 1; 1 VALT S: 1; 1 TINC S: 1; 1 MOT S: 2 |  | 12 | T5.1 | Dev.of Exploitation Plan
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP6 | Information Dissemination | 24 | 1 | 24 | all |  | SPAC | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 12 | 12 | WP6 | Information Dissemination
T6.1 | Information Dissemination | 24 | 1 | 24 |  | 50% | SPAC | [27 empty] | 12 | T6.1 | Information Dissemnination | bar: 1 AIT S; 1 IMAC S,C to 1 SUL C,B; 1 TARX C,S,B; 1 SPAC S; 1 CC C,B; 1 IAT S,B to 1 ZEUS S; 1 ICCS C,S; 1 VALT S to 2 MOT S
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
WP7 | Project Management | 24 | 1 | 24 | all |  | AIT | 12 | 0 | 12 | 6 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 0 | 4 | 5 | 2 | 2 | 4 | 0 | 6 | 2 | 12 | 80 | 80 | WP7 | Project Management
T7.1 | Management | 24 | 1 | 24 |  | 50% | AIT | 1 AIT S: 12; 1 TZ S: 12; 1 IMAC S,C: 6; 1 SUL C,B: 2; 1 TARX C,S,B: 4; 1 SPAC S: 4; 1 SIE S: 3; 1 IAT S,B: 4; 1 ZEUS S: 5; 1 SI SI: 2; 1 ITI C,S: 2; 1 ICCS C,S: 4; 1 VALT S: 6; 1 TINC S: 2; 1 MOT S: 4 |  | 72 | T7.1 | Management
T7.2 | Quality Assurance | 24 | 1 | 24 |  | 50% | MOT | 1 MOT S: 8 |  | 8 | T7.2 | Quality Assurance
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
| Total PM | [6 empty] | 59 | 7 | 28 | 36 | 13 | 8 | 8 | 8 | 29 | 8 | 8 | 8 | 35 | 8 | 15 | 24 | 10 | 22 | 48 | 20 | 18 | 32 | 10 | 50 | 18 | 42 |  | 1144 |  | Total PM
| Total Personnel Cost | [6 empty] | 354000 | 28000 | 168000 | 216000 | 52000 | 32000 | 32000 | 32000 | 145000 | 32000 | 32000 | 32000 | 210000 | 40000 | 75000 | 144000 | 40000 | 110000 | 288000 | 100000 | 90000 | 64000 | 20000 | 300000 | 90000 | 252000 |  | 2978000 |  | Total Personnel Cost
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| Partner - TYPE | [6 empty] | S | C,B,S | S | S,C | C,B | C,B | C.B | C | C,S,B | C,B | C | C,B | S | C | C,B | S | C,B | S,B | S | SI | C,S | C,S | C,S | S | S | S
[35 empty] | 210000 | Non-Personal Cost
| Durable Equipment | [33 empty] | 0 |  | Durable Equipment
| Consumables | [6 empty] | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 |  | 78000 |  | Consumables
| Travel and Subsistence | [6 empty] | 16000 | 6000 | 6000 | 6000 | 2000 | 2000 | 2000 | 2000 | 6000 | 2000 | 2000 | 2000 | 6000 | 2000 | 2000 | 10000 | 2000 | 2000 | 6000 | 2000 | 2000 | 6000 | 2000 | 10000 | 6000 | 10000 |  | 122000 |  | Travel and Subsistence
| Computing | [6 empty] | TARX C,S,B: 10000 |  | 10000 |  | Computing
| Subcontracting | [33 empty] | 0 |  | Subcontracting
| Other Specific project costs | [33 empty] | 0 |  | Other Specific project costs
| Protection of knowledge | [33 empty] | 0 |  | Protection of knowledge
| Overhead - % | [6 empty] | 80% | 20% | 80% | 80% | 20% | 80% | 20% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 20% | 80% | 80% | 80% | 80% |  |  |  | Overhead - %
| Overhead Costs | [6 empty] | 283200 | 5600 | 134400 | 172800 | 10400 | 25600 | 6400 | 25600 | 116000 | 25600 | 25600 | 25600 | 168000 | 32000 | 60000 | 115200 | 32000 | 88000 | 230400 | 80000 | 72000 | 12800 | 16000 | 240000 | 72000 | 201600 |  | 2276800 |  | Overhead Costs
| Total Costs | [6 empty] | 656200 | 42600 | 311400 | 397800 | 67400 | 62600 | 43400 | 62600 | 280000 | 62600 | 62600 | 62600 | 387000 | 77000 | 140000 | 272200 | 77000 | 203000 | 527400 | 185000 | 167000 | 85800 | 41000 | 553000 | 171000 | 466600 |  | 5464800 |  | Total Costs
| Partner | [6 empty] | AIT | ONB | TZ | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | RCM | SPAC | ALI | CC | SIE | GRAN | IAT | ZEUS | SI | ITI | ICCS | SUSU | VALT | TINC | MOT |  | TOTAL
| % Requested from EU | [6 empty] | 49.45% | 45.77% | 49.71% | 49.1% | 46.44% | 47.12% | 45.85% | 47.12% | 48.66% | 47.12% | 47.12% | 47.12% | 48.84% | 47.08% | 47.32% | 49.67% | 47.66% | 48.52% | 49.15% | 49.59% | 49.55% | 48.95% | 47.8% | 49.67% | 49.56% | 49.81% |  | 49.01% |  | % Requested from EU
| Requested contribution from EU | [6 empty] | 324500 | 19500 | 154800 | 195300 | 31300 | 29500 | 19900 | 29500 | 136250 | 29500 | 29500 | 29500 | 189000 | 36250 | 66250 | 135200 | 36700 | 98500 | 259200 | 91750 | 82750 | 42000 | 19600 | 274700 | 84750 | 232400 |  | 2678100 |  | Requested contribution from EU