REGNET-IST-2000-26336

Bimonthly Report

| Project acronym | REGNET |  | Contract nr. |  | IST-2000-26336 |
| --- | --- | --- | --- | --- | --- |
| Type and number | Bimonthly Report no. 02 |  |  |  |  |
| Covered period | From | YYYY-MM-DD | To | YYYY-MM-DD |  |
| Code name | input.doc |  | Version draft  final  |  |  |
| Date of issue | YYYY-MM-DD |  |  |  |  |
| Project Partner | Tel: Fax: Email: |  |  |  |  |
| Objective | Bimonthly Report |  |  |  |  |

Table of Contents

1	Identifications	2

2	Achievements	2

3	Effort	3

4	Deliverables Dates	3

5	Incidents	3

5.1	Issues	3

5.2	Red Flags	3

5.3	Deviations from Plan	4

5.4	Others	4

# Identifications

The list of active tasks in the reporting period, with the involved partners (the Task Leader in bold type) are detailed.

| Task | Task Description | Involved Partners | Start Date | End Date |
| --- | --- | --- | --- | --- |
| 1.1 | Definition of content to be provided | AIT ONB IMAC SUL LMG NRM KVA TARX MECH MUS SPAC ALI CC IAT GRAN ICCS ZEUS | 2001-04-01 | 2001-06-30 |
| 1.2 | Development of a documentation and digitization plan for content reation and management | AIT ONB IMAC SUL TARX MUS CC IAT ICCS ZEUS | 2001-07-01 | 2001-09-30 |
| 1.3 | Identification of standards to be used | IAT MOT SR VALT ZEUS | 2001-04-01 | 2001-05-31 |
| 1.4 | Development of the System Specifications | AIT IMAC MOT SPAC VALT ZEUS CERT ONB TARX SI SR | 2001-05-01 | 2001-09-30 |
| 1.4.1 | Node-1: Portal | AIT IMAC MOT SPAC VALT ZEUS | 2001-05-01 | 2001-09-30 |
| 1.4.2 | Node-2: CH Data Management | AIT CERT ONB SPAC TARX | 2001-05-01 | 2001-09-30 |
| 1.4.3 | Node-3: eBusines Data Management | IMAC MOT VALT ZEUS | 2001-05-01 | 2001-09-30 |
| 1.4.4 | Node-4: Ontology Checker | AIT CERT SI | 2001-05-01 | 2001-09-30 |
| 1.4.5 | Node-5: Electronic Publisher | SR SI | 2001-05-01 | 2001-09-30 |
| 1.4.6 | Core System | VALT ZEUS | 2001-05-01 | 2001-09-30 |
| 1.5 | Setup of the Legal Framework and Partnership Model | AIT IAT ICCS TINC | 2001-07-01 | 2001-09-30 |
| 1.6 | Definition of supported Business Functions | AIT ICCS IMAC MUS VALT TINC | 2001-04-01 | 2001-06-30 |
| 1.7 | Identification of Market (Segments) and User Groups | ICCS IMAC ONB TINC | 2001-04-01 | 2001-09-30 |
| 5.1 | Development of a Technology implementation plan (draft) | AIT CC IAT MOT SPAC TINC VALT ZEUS | 2001-04-01 | 2002-03-31 |
| 6.1 | Information Dissemination | AIT CC IAT ICCS IMAC MOT MUS ONB SPAC SR SUL TARX TINC VALT ZEUS | 2001-04-01 | 2003-03-31 |
| 7.1 | Project Management | AIT CERT IAT ICCS IMAC MOT ONB SI SPAC SR SUL TARX TINC VALT ZEUS | 2001-04-01 | 2003-03-31 |
| 7.2 | Quality Assurance | MOT | 2001-04-01 | 2003-03-31 |

# Achievements

Summarise the main achievements in the active tasks for the involved partners.

| Task | Achievements |
| --- | --- |
| 1.x | eg. document.x was finalized and ….. |

# Effort

| Period | YYYY-MM-DD – YYYY-MM-DD |
| --- | --- |

| Planned effort per active task (Person*Months) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Partners | Tx.y | Tx.y | Tx.y | Tx.y | Tx.y | Tx.y | Tx.y | Tx.y | Tx.y | Tx.y | Tx.y | Tx.y | Tx.y | Tx.y | Tx.y | Planned |

To be filled in by the partners involved

| Effort resources used for the reporting period (Person*Months) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Partners | T1.1 | T1.2 | T1.3 | T1.4 | T1.5 | T1.6 | T1.7 | T5.1 | T6.1 | T7.1 | T7.2 | Tx.y | Tx.y | Tx.y | Tx.y | Total |

To be filled in by the PM

| Cumulative Project effort in person-months |  |  |  |  |
| --- | --- | --- | --- | --- |
| Originally |  |  | Actually |  |
| Plan. | Cumul. | Period | Spent | Cumul. |

# Deliverables Dates

| Deliverables Code & Description | Originally planned | Current planned | Actual delivery | Partner Responsible |
| --- | --- | --- | --- | --- |

# Incidents

Summarise the mayor incidents if any in the reporting period.

## Issues

| Task | Issue description | Action Items |
| --- | --- | --- |
| Tx.y | Here describe the issues or problems that might affect achievements, delay activities, deliverables or milestones. | Corrective action envisaged by the project to overcome the issue. This includes the expected impact in terms of delays, quality and quantity of work. |

## Red Flags

| Task | Red Flag description | Recommended Solutions |
| --- | --- | --- |
| Tx.y | Here describe serious problems that cannot be addressed at the project level and require urgent attention from the Commission Services. | Describe possible solutions with pros and cons, and if possible recommend one of them. |

## Deviations from Plan

| Task | Deviation description | Recommended Solutions |
| --- | --- | --- |
| Tx.y | List any deviation from plan | Describe the action that will be taken: - Which deliverables and Work packages are affected - Why are deliverables not on schedule - What is proposed - Rationale for requested change. |

## Others

Report any item of interest, such as name or address changes, team changes, responsibilities reassignment, or other.