REGNET-IST-2000-26336

Task Brief

| WP Number and Title |  |  | WP 1 | Analysis of the State of the Art and Development of Concepts |  |
| --- | --- | --- | --- | --- | --- |
| Task Number and Title |  |  | T 1.4 | Development of the System Specifications: |  |
| Sub-Task Number and Title |  |  | T 1.4.1.1 | Node-1: Portal – Data Generation |  |
| Task Leader and Contact |  |  | MOT | <name@organisation> |  |
| Deliverable Number and Title |  |  | D 2 | Report: “The REGNET – System: Specification and State of the Art” |  |
| Interm. Report Number and Title |  |  | IR 1.4.1 | REGNET Node-1: Portal – Data Generation (2001-06-30) |  |
| Start Date: |  | 2001.05.02 |  | End Date: | 2001.09.30 |
| Objectives: |  |  |  |  |  |
| Description of Work: |  |  |  |  |  |
| Description of Sub-Component: Data Generation (node-1/subsystem-4): This subsystem (component) enables the generation of meta data either via a (configurable) data entry facility (loaded into the user's browser) or by sending a harvester to repositories included in Subsystem-1. Meta data are either stored in Subsystem-1 or -2. Data entry and harvester processes can be triggered by document type definitions (residing in Subsystem-3) according to the needs of the end user (librarian, archivist, curator). The client connected to this subsystem might even support multimedia and 2/3D data input of digital content. |  |  |  |  |  |
| Methodology: |  |  |  |  |  |
| Partner | PM | Contact (email) |  | Obligation |  |
| - AIT | 0,3 | <name@organisation> |  | Contribution to IR 1.4.1 |  |
| - IMAC | 1 | <name@organisation> |  | Contribution to IR 1.4.1 |  |
| - MOT | 2 | <name@organisation> |  | Task Management and Contribution to IR 1.4.1 |  |
| - SPAC | 1 | <name@organisation> |  | Baseline for this sub-chapter of Interim Report IR 1.4.1 |  |
| Total Effort | 4,3 | Comment |  |  |  |