- REGNET-IST-2000-26336

Task Brief

| WP Number and Title |  |  | WP2 | Implementation of the System and reparation of Services and Product Generation |  |
| --- | --- | --- | --- | --- | --- |
| Task Number and Title |  |  | T 2.2 | System Implementation |  |
| Sub-Task Number and Title |  |  | T 2.2.1.2 | Search & Retrieval (subsystem-5) |  |
| Task Leader and Contact |  |  | AIT | bogenspergerm@ait.co.at |  |
| Deliverable Number and Title |  |  | D 5 | Prototype: "The REGNET - System: Version 1" |  |
| Interm. Report Number and Title |  |  | IR 2.2 | The REGNET - System: Version 1 |  |
| Start Date: | 2001.10.01 |  |  | End Date: | 2001.03.30 |
| Task & team objectives: - Objectives: - Design the S&R subsystem - Develop the subsystem (core functionalities) - Integrate the Search & Retrieval subsystem into the Portal - Deliver the subsystem (with all functionalities specified and marked with priority=1 in D2) - Milestones: - 2001.11.30 - P1 – Design ready - 2002.01.31 - P2 - Review of first S&R development phase - 2002.03.15 - P3 - Quality gate - 2002.03.29 - P4 - End of second S&R development phase - Specific Deliveries and output: - First draft of interfaces specification (P1) - S&R test cases (P1) - S&R structure (P1) - S&R core functionalities (P2) - S&R test results (P2) - S&R subsystem integrated into Portal (P3) - Quality gate results (P3) - S&R first version (P3) |  |  |  |  |  |
| Description of Work: - Detailed Schedule: 1st Increment: - 2001.10.26 - DS1 – Complete detailed description of each prototype (functionalities and interfaces), in order to allow harmonization between prototypes. - 2001.11.05 - DS2 – First draft of S&R design - DS3 – Reached agreement about prototypes interactions with Portal and other subsystems. - 2001.11.30 - P1 – Design ready. - DS4 – Completed test cases 2nd Increment: - 2001.12.07 - DS5 - Identification of requirements to be addressed by second and by third phases of development. - 2002.01.11 - DS6 – End of consolidation of interfaces between all modules. - 2002.01.25 - DS7 – End of first development iteration - DS8 – Completed tests for first development iteration - DS9 – Start of integration into Portal - 2002.01.31 - P2 - Review of first development phase. 3rd Increment: - 2002.03.01 - DS10 - Consolidated interfaces. - 2002.03.08 - DS11 - End of development & start integration into Portal. - 2002.03.15 - P3 – Work Package Quality gate. - 2002.03.29 - P4 - End of second Portal development phase. - Critical Path: The on time achivement of the following tasks shall be considered critical as a delay in one of them could cause the delay of the overall work package: Task; Date. DS6; 2002.01.11. DS10; 2002.03.01. - Configuration Items: - Task Brief shall undergo configuration management. After 2001.10.26 it will be subject of CCB procedure. - Prototype code shall undergo configuration management. - Contributes (code & documentation) T 2.2.1.2 shall undergo configuration management. It is not subject of CCB procedure until the delivery of D5. - Quality Gates: - Date: 2002.03.15 - Partecipants: MOT, IMAC, VALT, ZEUS, AIT, SPAC. - Preconditions: S&R is inspected against requirements and tested following test cases. |
| Description of Component: |  |  |  |  |  |
| - Methodology: see D2 (sections 4.3, 10.1-10.3, and 10.9). - Risks: see D2-Annex. - Dependencies: see D2, section 5. - Goals: see Goals in TaskBrief 2.2.1 |  |  |  |  |  |
| Partner | PM | Contact (email) |  | Obligation |  |
| - AIT | 1 | bogenspergerm@ait.co.at |  | Developement of Search & Retrieval subsystem |  |
| Total Effort | 1 | Comment |  |  |  |