- REGNET-IST-2000-26336

Task Brief

| WP Number and Title |  |  | WP2 | Implementation of the System and reparation of Services and Product Generation |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task Number and Title |  |  | T 2.2 | System Implementation |  |  |
| Sub-Task Number and Title |  |  | T 2.2.1 | Portal Development |  |  |
| Task Leader and Contact |  |  | MOT | roberto.cicci@motorola.com |  |  |
| Deliverable Number and Title |  |  | D5 | Prototype: "The REGNET - System: Version 1" |  |  |
| Interm. Report Number and Title |  |  | IR 2.2 | The REGNET - System: Version 1 |  |  |
| Start Date: | 2001.10.01 |  |  | End Date: |  | 2002.03.31 |
| Task & team objectives: - Objectives: - Validate the architecture - Develop the Regnet Portal (common functionalities) - Integrate the Portal Sub-systems - Deliver the Demonstrator - Milestones: - 2001.11.30 - P1 - End of architecture validation & Portal structure release - 2002.01.31 - P2 - Review of first Portal development phase - 2002.03.15 - P3 - Quality gate - 2002.03.29 - P4 - End of second Portal development phase - Specific Deliveries and output: - Portal wap prototype release (P1) - First draft of interfaces specification (P1) - Portal test cases (P1) - Portal Structure (P1) - The REGNET System – Portal core functionalities (P2) - Portal test results (P2) - Quality gate results (P3)… - The REGNET System – Portal first version (P3) - <S&R, DG, EB milestones> |  |  |  |  |  |  |
| Description of Work: - Detailed Schedule: 1st Increment: - 2001.10.26 - DS1 – Complete detailed description of each prototype in the context of Portal node (scope, functionalities, and interfaces), in order to allow harmonization between prototypes. The attempt to harmonize the prototypes is intended both for the prototypes included in the Portal node, and between the Portal sub-systems and the REGNET back-end prototypes. - DS2 - First draft of Portal structure, gathering the work done for demos in WP1. - DS3 – Complete Identification of roles and responsibilities for Configuration Management regarding Portal configuration items - 2001.11.05 - DS4 – Reached agreement about prototypes interactions. - 2001.11.23 - DS5 – End of prototype development & start Prototypes integration. - 2001.11.30 - P1 - End of architecture validation & release of portal structure. - DS6 – Completed Portal test cases 2nd Increment: - 2001.12.07 - DS7 - Identification of requirements to be addressed by second and by third phases of development. - 2002.01.11 - DS8 – End of consolidation of interfaces between Portal modules, and between Portal and other node’s modules. - 2002.01.25 - DS9 - Completed Portal test and results - DS10 – End of development & start Portal sub-systems Integration. - 2002.01.31 - P2 - Review of first Portal development phase. 3rd Increment: - 2002.03.01 - DS11 - Consolidated interfaces (phase 3) between Portal modules, and between Portal and other node’s modules. - 2002.03.08 - DS12 - End of development & start Portal sub-systems Integration (phase 3). - 2002.03.15 - P3 – Work Package Quality gate. - 2002.03.29 - P4 - End of second Portal development phase. Paths: - DS1 - DS4 – DS5 – P1; DS2; DS3; DS6; - DS7 – DS8 – DS10 – P2; DS9; - DS11 – DS12 – P3; |  |  |  |  |  |  |
| - Critical Path: The on time achivement of the following tasks shall be considered critical as a delay in one of them could cause the delay of the overall work package: Task; Date. DS7; 2001.12.07. DS8; 2002.01.11. DS11; 2002.03.01. - Configuration Items: - Task Brief 2.2.1 and 2.2.1.x shall undergo configuration management. After 2001.10.26 they will be subject of CCB procedure. - Prototype code shall undergo configuration management. - Contributes (code & documentation) for 2.2.1 and 2.2.1.x shall undergo configuration management. They are not subject of CCB procedure until the delivery of D5. - Quality Gates: - Date: 2002.03.15 - Partecipants: MOT, IMAC, VALT, ZEUS, AIT, SPAC. - Preconditions: Every contribute is inspected against requirements and tested following test cases. |
| Description of Component: see D2. |  |  |  |  |  |  |
| - Methodology: see D2 (sections 4.3, 10.1-10.3, and 10.9). - Risks: see D2, section ??? [risks]. - Dependencies: see D2, section 5. - Goals: - Usability – GUI must be simple and intuitive, and easy to use according to terminal capabilities - Security – the system must assure non-occurrence of unhautorized disclosure of information, and non-occurrence of improper alterations of information - Maintainability – despite of the distributed nature of the system, maintenance must impact as far as possible central components - Upgrade – portal extensions shall be added with minimal impact on pre-existent functionalities and regional nodes organization |  |  |  |  |  |  |
| Partner | PM | Contact (email) |  |  | Obligation |  |
| - AIT | 7 | kochw@ait.co.at |  |  | With reference to detailed shedule, every task except DS2, with main focus on S&R sub-system. |  |
| - IMAC | 2 | grossmann@imac.de |  |  | DS2, DS6. |  |
| - MOT | 10 | Roberto.cicci@motorola.com |  |  | With reference to detailed shedule, every task with main focus on common layer functionalities. |  |
| - SPAC | 5 | paolo.alongi@spacespa.it |  |  | With reference to detailed shedule, every task except DS2, with main focus on DG sub-system. |  |
| - ZEUS | 12 | kgiotop@zeusnet.gr |  |  | With reference to detailed shedule, every task except DS2, with main focus on EB sub-system. |  |
| - VALT | 12 | jean-pierre.Lorre@toulouse.valtech.fr |  |  | With reference to detailed shedule, every task except DS2, with main focus on EB sub-system. |  |
| Total Effort | 48 | Comment |  |  |  |  |