- REGNET-IST-2000-26336

Task Brief

| WP Number and Title |  |  | WP 2 | Implementation of the System and reparation of Services and Product Generation |  |
| --- | --- | --- | --- | --- | --- |
| Task Number and Title |  |  | T 2.2 | System Implementation |  |
| Sub-Task Number and Title |  |  | T 2.2.3.1 | Node-3 – Catalogue Management |  |
| Task Leader and Contact |  |  | ZEUS | kgiotop@zeusnet.gr |  |
| Deliverable Number and Title |  |  | D 5 | Prototype: "The REGNET - System: Version 1" |  |
| Interm. Report Number and Title |  |  | IR 2.2 | The REGNET - System: Version 1 |  |
| Start Date: | 2001.10.01 |  |  | End Date: | 2002.03.31 |
| Task & team objectives: - Objectives: Main objectives of this task is to validate technical aspects relevant to Product Catalogue Management (PCM) and to produce the first version of PCM sub-system. These objectives can be split in: - Validate the PCM architecture - Develop the first version of the PCM sub-system - Integrate the PCM with the Procurement Sub-system - Deliver the Demonstrator - Milestones: According to the three increments splitting: - 2001.11.30 - P1 - End of architecture validation - 2002.03.29 - P2 - End of development phase for the first version of PCM subsystem - Specific Deliveries and output: - PCM technical prototype (P1) - First version of PCM sub-system (P2) |  |  |  |  |  |
| Description of Work: - Detailed Schedule: 1st Increment: - 2001.10.30 - DS1 - Description of protoype based on technologies: PHP + XML Databases + SOAP and communication with Data Generation (DG) and Search & Retrieval (SR) and E-Business (EB). - 2001.11.10 - DS2 - Reached agreement about prototypes interactions. - 2001.11.25 - DS3 – End of prototype development & start Prototypes integration. - 2001.11.30 - P1 - End of architecture validation 2nd Increment:. 3rd Increment: - 2002.03.01 - DS4 - Consolidated interfaces between: - PCM and DG. - PCM and SR. - PCM and EB - 2002.03.08 - DS5 - End of development. Start Integration. - 2002.03.29 P4 - End of development phase. - Critical Path: The on time achivement of the following tasks shall be considered critical as a delay in one of them could cause the delay of the overall work package: Task; Date. DS3; 2001.11.25. DS4; 2002.03.01. - Configuration Items: - Code and related documentation. - External interfaces. - Interim Report 2.2. - Quality Gates: The output of this task will be evaluated in reviews held at the end of each increment. |
| Description of Component: see D2 |  |  |  |  |  |
| - Methodology: see D2. - Risks: see D2, section [risks]. - Dependencies: see D2. - Goals: : - Usability – Provides simple functionality for the management of the on-line catalogues.. |  |  |  |  |  |
| Partner | PM | Contact (email) |  | Obligation |  |
| - ZEUS |  | kgiotop@zeusnet.gr |  | With reference to detailed shedule, every task. |  |
| Total Effort |  | Comment |  |  |  |