# REGNET-IST-2000-26336

Task Brief

| WP Number and Title | WP 2 | Implementation of the System and reparation of Services and Product Generation |
| --- | --- | --- |
| Task Number and Title | T 2.2 | System Implementation |
| Sub-Task Number and Title | T 2.2.4 | Ontology Checker |
| Task Leader and Contact | SI | nikos.karatzoulis@systema.gr |
| Deliverable Number and Title | D 5 | Prototype: "The REGNET - System: Version 1" |
| Interm. Report Number and Title | IR 2.2 | The REGNET - System: Version 1 |
| Start Date: | 2001.10.01 | End Date: | 2002.03.31 |
| Task & team objectives: Objectives: Validate the Ontology Node architecture Develop the Regnet Ontology Develop the Ontology Checker Integrate the Ontology Checker to the Regnet Portal Deliver the demonstrator Milestones: According to the three increments splitting: 2001.11.30 - P1 - End of architecture validation 2002.03.10 - P2 – End of Development phase 2002.03.29 - P3 – Review of the implemented Ontology Checker. Specific Deliveries and output: Specification & Design of the Regnet Ontology (P1) Development of the Ontology checker (P2) Integration of the Ontology checker to the related sub-systems (P2) Testing of the Ontology checker (P3) |
| Description of Work: Detailed Schedule: 1st Increment 2001.10.26 DS1 – Identification of methodologies allowing the integration of the SHOE data type definition to Topic Maps DS2 – Design of the Regnet Ontology based on Topic Maps technology 2001.11.05 DS3 - Design of the Ontology checker Interface 2001.11.26 DS4 – Produce first version of the Ontology Checker (limited functionalities) 2001.11.29 P1- End of architecture validation 2st Increment 2001.12.07 DS5 - Consolidation between Ontology checker module and other modules: - Electronic Publishing node - Search and Retrieval node - Product Catalogue Management node - Data Generation node - E-Business node - Reference System node - Procurement & Delivery node 2002.03.5 DS6 - End of Development and start Integration with Regnet Portal 2002.03.10 P2-End of Development Phase 3rd Increment 2002.03.15 DS7 - Testing of the developed Ontology Checker 2002.03.25 DS8 - Work Package Quality Gate 2002.03.29 P3 - End of Testing Phase Critical Path: The on time achivement of the following tasks shall be considered critical as a delay in one of them could cause the delay of the overall work package: Task Date End of architecture validation 2001.11.29 End of Development Phase 2002.03.10 Configuration Items: - Code and related documentation (API documentation, Ontology documentation, Test cases, Test Results) - External Interfaces - Interim Report 2.2 Quality Gates: The output of this task will be evaluated in reviews held at the end of each increment. Review participants should be at least SI, CERT, AIT, VALT, SR, ZEUS, MOT. |
| Description of Component: see D2 |
| Methodology: see D2 Risks: see D2, section Risks Dependencies: see D2 Goals: Usability: The Ontology checking will be a complicated process, therefore the GUI has to be very carefully designed to be user friendly. Security: The Ontology node will contain information of user profiles and therefore a high level of security must be assured. Maintainability: New Ontologies and data must be easily added and integrate to the Ontology Checker |
| Partner | PM | Contact (email) | Obligation |
| SI | 2 | nikos.karatzoulis@systema.gr | Contribution to IR 2.2 |
| CERT | 3 | Dimitris.Tzovaras@iti.gr | Contribution to IR 2.2 |
| AIT | 1 | kochw@ait.co.at | Contribution to IR 2.2 |
| Total Effort | 6 | Comment |  |