- REGNET-IST-2000-26336

Task Brief

| WP Number and Title |  |  | WP 2 | Implementation of the System and reparation of Services and Product Generation |  |
| --- | --- | --- | --- | --- | --- |
| Task Number and Title |  |  | T 2.2 | System Implementation |  |
| Sub-Task Number and Title |  |  | T 2.2.4 | Ontology Checker |  |
| Task Leader and Contact |  |  | SI | nikos.karatzoulis@systema.gr |  |
| Deliverable Number and Title |  |  | D 5 | Prototype: "The REGNET - System: Version 1" |  |
| Interm. Report Number and Title |  |  | IR 2.2 | The REGNET - System: Version 1 |  |
| Start Date: | 2001.10.01 |  |  | End Date: | 2002.03.31 |
| Task & team objectives: - Objectives: - Validate the Ontology Node architecture - Develop the Regnet Ontology - Develop the Ontology Checker - Integrate the Ontology Checker to the Regnet Portal - Deliver the demonstrator - Milestones: According to the three increments splitting: - 2001.11.30 - P1 - End of architecture validation - 2002.03.10 - P2 – End of Development phase - 2002.03.29 - P3 – Review of the implemented Ontology Checker. - Specific Deliveries and output: - Specification & Design of the Regnet Ontology (P1) - Development of the Ontology checker (P2) - Integration of the Ontology checker to the related sub-systems (P2) - Testing of the Ontology checker (P3) |  |  |  |  |  |
| Description of Work: - Detailed Schedule: 1st Increment - 2001.10.26 - DS1 – Identification of methodologies allowing the integration of the SHOE data type definition to Topic Maps - DS2 – Design of the Regnet Ontology based on Topic Maps technology - 2001.11.05 - DS3 - Design of the Ontology checker Interface - 2001.11.26 - DS4 – Produce first version of the Ontology Checker (limited functionalities) - 2001.11.29 - P1- End of architecture validation 2st Increment - 2001.12.07 - DS5 - Consolidation between Ontology checker module and other modules: - Electronic Publishing node - Search and Retrieval node - Product Catalogue Management node - Data Generation node - E-Business node - Reference System node - Procurement & Delivery node - 2002.03.5 - DS6 - End of Development and start Integration with Regnet Portal - 2002.03.10 - P2-End of Development Phase 3rd Increment - 2002.03.15 - DS7 - Testing of the developed Ontology Checker - 2002.03.25 - DS8 - Work Package Quality Gate - 2002.03.29 - P3 - End of Testing Phase Critical Path: The on time achivement of the following tasks shall be considered critical as a delay in one of them could cause the delay of the overall work package: Task; Date. End of architecture validation; 2001.11.29. End of Development Phase; 2002.03.10. - Configuration Items: - Code and related documentation (API documentation, Ontology documentation, Test cases, Test Results) - External Interfaces - Interim Report 2.2 - Quality Gates: The output of this task will be evaluated in reviews held at the end of each increment. Review participants should be at least SI, CERT, AIT, VALT, SR, ZEUS, MOT. |
| Description of Component: see D2 |  |  |  |  |  |
| - Methodology: see D2 - Risks: see D2, section Risks - Dependencies: see D2 - Goals: - Usability: The Ontology checking will be a complicated process, therefore the GUI has to be very carefully designed to be user friendly. - Security: The Ontology node will contain information of user profiles and therefore a high level of security must be assured. - Maintainability: New Ontologies and data must be easily added and integrate to the Ontology Checker |  |  |  |  |  |
| Partner | PM | Contact (email) |  |  | Obligation |
| - SI | 2 | nikos.karatzoulis@systema.gr |  |  | Contribution to IR 2.2 |
| - CERT | 3 | Dimitris.Tzovaras@iti.gr |  |  | Contribution to IR 2.2 |
| - AIT | 1 | kochw@ait.co.at |  |  | Contribution to IR 2.2 |
| Total Effort | 6 | Comment |  |  |  |