REGNET-IST-2000-26336

Interim Report

| Project acronym | REGNET |  | Contract nr. |  | IST-2000-26336 |
| --- | --- | --- | --- | --- | --- |
| Type and Number | Interim Report no. 3.1 |  |  |  |  |
| Work package | WP 3 Validation of the REGNET system operation & Preparation of the REGNET - Demonstration Phase |  |  |  |  |
| Task | WP 3.1 Validation of the REGNET demonstrator |  |  |  |  |
| Date of delivery | Contractual | 2002-06-30 | Actual | 2002-06-30 |  |
| Code name | input.doc |  | Version 01 draft  final  |  |  |
| Objective | Report |  |  |  |  |
| Distribution Type | Restricted |  |  |  |  |
| Authors (Partner) | IMAC |  |  |  |  |
| Contact Person | Silke Grossmann |  |  |  |  |
| Abstract | This report describes the validation concept which build the basis for WP 3.1. It gives an overview about the tests to be carried out, the methodology choosen and the tasks. |  |  |  |  |
| Keywords List | Validation, task assignment, test types |  |  |  |  |
| Version log |  |  |  |  |  |

Table of Contents

1	Introduction	3

2	Test Strategy	3

2.1	Tests based on use cases	3

2.1.1	Function testing	3

2.1.2	Database Testing	4

2.1.3	Access Control Testing	5

2.2	Technical Tests	5

2.2.1	Load Testing	5

2.2.2	Volume Testing	7

2.3	Usability tests	7

2.4	Content checks	8

2.4.1	Content Integrity Checks	8

2.4.2	Content Quality Checks	9

3	Regnet members participation in validation phase	10

3.1	Roles and activities	10

4	Proposed Project Plan	10

5	Detailed Task Assignments / Effort Estimation	12

# Introduction

The purpose of this document is threefold:

- To define the single tasks which have to be carried out during the Regnet validation phase

- To agree on common quality criteria on the work performed by the Regnet-consortium during the implementation phase

- To structure the validation phase in the form of a subproject

Four types of tests will be carried out during the validation phase of the Regnet information system:

- Functional tests (including security and access control tests and database tests). These tests are based on the Use Cases defined in the documents ...)

- Usability tests performed by a selected end-user group

- Technical tests (including load tests, stress tests)

- Content checks

A reporting procedure will be proposed to enable the proper handling of all incidents and change requests occurring during the validation phase. This reporting environment can also be used for incident reporting and change request management in further phases of the REGNET project.

This document specifies the methods and criteria proposed by IMAC to measure the different levels of quality and to define the tasks, the members of the REGNET consortium have to carry out during the validation phase, to enable the successful completion of this phase and the proceeding to the demonstration phase of the REGNET project.

# Test Strategy

## Tests based on use cases

### Function testing

Function testing of the REGNET system focuses on the requirements for tests that can be traced directly to use cases. The goals of these tests are to verify proper data acceptance, processing, and retrieval, and the appropriate implementation of the business rules.

These tests are based upon black box techniques; that is verifying the application and its internal processes by interacting with the application via the Graphical User Interface (GUI) and analysing the output or results.

| Test Objective: | To ensure proper target-of-test functionality, including navigation, data entry, processing, and retrieval. |
| --- | --- |
| Technique: | Each use case is executed (main flows and alternative flows) till the completion criteria are reached using valid and invalid data, to verify the following: - The expected results occur when valid data is used. - The appropriate error or warning messages are displayed when invalid data is used. - Each business rule is properly applied. |
| Completion Criteria: | All planned tests have been executed within the beta test phase. All identified defects have been addressed. |
| Special Considerations: | These tests will be carried out in the form of beta tests by Regnet consortium members |
| Requirements for tests | - The REGNET prototype is in a testable (stable) state - Agreed functionalities are implemented - Incident reporting environment is set-up |
| Work to be done: | - Estimate no. of test cases - Develop test cases - Develop test manual - Distribute test cases - Carry out tests - Report incidents - Monitor incident reporting - Monitor incident solving - Re-test reported issues - Closure of resolved issues - Agreement upon completion of functional tests |

### Database Testing

The databases and the database processes will be tested as a subsystem within the Regnet project. These subsystems are tested using the GUI-interface of the system.

The prerequisites for these tests are the functional tests carried out by the Regnet members. Each database operation invoked by a successful functional test (e.g. registering of a user, creating a list of items to be displayed etc.) will be checked for proper function.

| Test Objective: | To ensure that database access methods and Processes function properly and without data Corruption. |
| --- | --- |
| Technique | Each database access method and process is invoked to seed the database with valid and invalid data and requests for data The database is inspected to ensure the data has been populated as intended and that all database events occurred properly The returned data is reviewed to ensure that the correct data was retrieved for the correct reasons |
| Completion Criteria: | All database access methods and processes function as designed and without any data corruption |
| Special considerations | None |
| Requirements for tests | - Regnet prototype is in a testable (stable) state - Agreed functionalities are implemented - Incident reporting environment is set-up |
| Work to be done: | - Estimate no. of test cases - Develop test cases - Develop test manual - Distribute test cases - Carry out tests - Report incidents - Monitor incident reporting - Monitor incident solving - Re-test reported issues - Closure of resolved issues - Agreement upon completion of database tests |

### Access Control Testing

Access Control Testing focuses on a key area of security:

- Application-level security, including access to the data or business functions.

Application-level security ensures that, based upon the desired security, actors are restricted to specific functions or use cases, or are limited in the data that is available to them.

| Test Objective: | To verify that an actor can access only those functions or data for which their user type is provided permissions. |
| --- | --- |
| Technique: | To identify and list each user type and the Functions or data each type has permissions for. To create tests for each user type and verify each permission by creating transactions specific to each user type. To modify user type and re-run tests for same Users. In each case, verify those additional functions or data are correctly available or denied. |
| Completion Criteria: | For each known actor type the appropriate function or data are available, and all transactions function as expected and run in prior application function tests. |
| Special considerations | None |
| Requirements for tests | - Regnet prototype is in a testable (stable) state - Agreed functionality's are implemented - Incident reporting environment is set-up |
| Work to be done: | - Estimate no. of test cases - Develop test cases - Develop test manual - Distribute test cases - Carry out test - Report incidents - Monitor incident reporting - Monitor incident solving - Re-test reported issues - Closure of resolved issues - Agreement upon completion of functional tests |

## Technical Tests

### Load Testing

Load testing is a performance test which subjects the target-of-test to varying workloads to measure and evaluate the performance behaviours and ability of the target-of-test to continue to function properly under these different workloads.

The goal of load testing is to determine and ensure that the system functions properly beyond the expected maximum workload. Additionally, load testing evaluates the performance characteristics, such as response times, transaction rates, and other time sensitive issues.

Transactions below refer to “logical business transactions”. These transactions are defined as specific functions that an end user of the system is expected to perform using the application, such as add or modify a given catalogue item.

| Test Objective: | Verify performance behaviour time for designated transactions or business cases under varying workload conditions. |
| --- | --- |
| Technique: | Tests developed for function testing will be used in the test definition: Data files are modified to increase the number of transactions or the number of times each transaction occurs. |
| Completion Criteria: | Single Transaction or single user: Successful completion of the test scripts without any failures and within the expected or required time allocation per transaction: Response time per page request < ... seconds Multiple users: Successful completion of the test scripts Without any failures and within acceptable time allocation per transaction: Response time per page request < ... seconds with a maximum of ... concurrent users Multiple transactions: Successful completion of the test scripts without any failures and within acceptable time allocation per transaction: Response time < ... seconds with a maximum of ... concurrent users carrying out different transactions A load test is successfully performed to validate performance to a minimum of ... catalogue item requests / day and ... catalogue item requests / hour |
| Special considerations | A load testing software will be used to carry out the load tests |
| Requirements for tests | - Regnet prototype is in a testable (stable) state - Agreed functionality's are implemented as specified (functional tests are completed and all issues are addressed) |
| Work to be done: | - Define requirements for load testing software - Select load testing software - Estimate no. of test cases - Develop test cases - Implement test cases in software - Carry out test - Evaluate outcome of tests - Recommend system adaptation or sign-off system - Agreement upon successful completion of load tests |

### Volume Testing

Volume Testing subjects the target-of-test to large amounts of data to determine if limits are reached that cause the software to fail. Volume Testing also identifies the continuous maximum load or volume the target-of-test can handle for a given period. For example, if the target-of-test is processing a set of database records to generate a report, a Volume Test would use a large test database and check that the software behaved normally and produced the correct report.

| Test Objective: | To verify that the target-of-test successfully functions under the following high volume scenarios: Maximum database size has been reached (actual or scaled) and multiple queries or report transactions are executed simultaneously. |
| --- | --- |
| Technique: | Multiple clients should be used, either running the same tests or complementary tests to produce the worst case transaction volume or mix for an extended period. Maximum database size is created (actual, scaled, or filled with representative data) and multiple clients used to run queries and report transactions simultaneously for extended periods. All the tests described as load tests will be carried out on this configuration with the same response times to be achieved. |
| Completion Criteria: | All planned tests have been executed and specified system limits are reached or exceeded without the software failing. |
| Requirements for tests | - Regnet prototype is in a testable (stable) state - Agreed functionalities are implemented as specified (functional tests are completed and all issues are addressed) - Datasets with representative data are available in a machine readable format and loaded into the database |
| Special Considerations: |  |
| Tasks to be done | - Estimate no. of test cases - Develop test cases - Implement test cases in software - Define necessary test data - Acquire necessary test data - Load test data into the database - Carry out test - Evaluate outcome of tests - Recommend system adaptation or sign-off system - Agreement upon successful completion of load tests |

## Usability tests

The purpose of the usability tests is to ensure, that the GUI interface of the Regnet information system and the implementation of the functionalities meet the requirements of the end user of the system.

| Test objective: | To ensure the usability of the system |
| --- | --- |
| Technique: | Users will be asked to carry out "real life tasks" based on the functional tests of the system. User behaviour will be monitored during these tests by Regnet staff. Users will be debriefed by Regnet staff using a standard questionnaire. The questionnaires will be evaluated and proposals for the enhancement of usability extracted. The Regnet consortium has to agree upon the changes to be implemented. Heuristic tests will be carried out to ensure meeting of generally accepted quality criteria Card sorting will be used to validate the information architecture of the site |
| Completion Criteria: | All Changes which have been agreed upon by the Regnet consortium are addressed by the implementation partners of the project. All functional changes have been re-tested using the test cases modified according to the specifications of the change requests |
| Considerations | The user tests will be carried out by the evaluation partners of the Regnet project |
| Requirements for tests | - Regnet prototype is in a testable (stable) state - Agreed functionalities are implemented - Availability of test users |
| Tasks to be done | - Develop test cases - Develop questionnaires - Develop test manuals - Set-up test environment - Select test persons - Carry out tests - Collect tests results - Evaluate test results - Estimate changes needed - Agreement upon implementation of changes |

## Content checks

### Content Integrity Checks

The purpose of content integrity checks is, to ensure, that the migration of the content from the various sources is done correctly.

| Test Objective: | To ensure that the content has been entered into the database correctly and that the content is displayed in the right content containers |
| --- | --- |
| Technique: | To develop test cases out of existing material of the participating organisations. Beta testing personnel is asked to review content items as displayed by the system and to confirm that all information delivered by the system is correct. |
| Completion Criteria: | All planned tests have been executed within the beta test phase. All identified defects have been addressed. |
| Considerations |  |
| Requirements for tests | - Regnet prototype is in a testable (stable) state - Agreed functionalities are implemented as specified (functional tests are completed and all issues are addressed) - Datasets with representative data are available in a machine readable format and loaded into the database |
| Tasks to be done | - Estimate no. of test cases - Develop test cases - Define necessary test data - Acquire necessary test data - Load test data into the database - Carry out test - Report incidents - Monitor incident reporting - Monitor incident solving - Re-test reported issues - Closure of resolved issues - Agreement upon completion of content integrity tests |

### Content Quality Checks

The purpose of content quality checks is, to ensure, that the content provided by the system meets the users and content providers quality expectations

| Test Objective: | To ensure that the content provided by the system meets quality expectations |
| --- | --- |
| Technique: | A checklist of content quality will be applied to each content item in the Regnet system |
| Completion Criteria: | All planned tests have been executed within the beta test phase. All identified defects have been addressed. |
| Considerations |  |
| Requirements for tests | - Regnet prototype is in a testable (stable) state - Agreed functionalities are implemented as specified (functional tests are completed and all issues are addressed) - Datasets with final data are available in a machine readable format and loaded into the database |
| Tasks to be done | - Definition of quality checklist - Estimate no. of test cases - Application of checklist to content items - Report incidents - Monitor incident reporting - Monitor incident solving - Re-test reported issues - Closure of resolved issues - Agreement upon completion of content quality tests |

# Regnet members participation in validation phase

## Roles and activities

|  | Task description |
| --- | --- |
| Test designer | To estimate the test effort To define test cases To provide testing guidelines To interpret test results |
| Tester | To carry out tests according to test cases To report issues |
| Tool specialist | To implement testing tools |
| Test reviewer | To re-check resolved issues |
| Technical support staff | To load databases |
| Test person | To perform user tests under supervision by testers |
| Usability specialist | To define usability criteria, to design usability tests and to evaluate the outcome of usability tests |
| Regnet implementation group | To implement the Regnet system |
| Regnet content group | To collect the content, to carry out test, to ensure content quality |
| Regnet consortium | To agree on test criteria To agree on the closure of the validation phase |
| Validation PM | To define requirements To define workflows To extract reports To collect and distribute documentation and test results To propose decisions |

# Proposed Project Plan

The following high-level Gantt-chart shows the different project phases of the sub-project "validation" with their interdependencies. The red line marks the delivery of the Regnet prototype to be tested as the key input from a previous project phase. The dotted arrows indicate the iterative nature of the tests: The review of test results might lead to the start of a complete new test cycle for a certain functionality.

| Set up reporting environment |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Software specification |  |  |  |  |  |  |  |  |  |  |  |
| Software acquisition |  |  |  |  |  |  |  |  |  |  |  |
| Software Implementation |  |  |  |  |  |  |  |  |  |  |  |
| Training |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring |  |  |  |  |  |  |  |  |  |  |  |
| Test environment Set up |  |  |  |  |  |  |  |  |  |  |  |
| Software specification |  |  |  |  |  |  |  |  |  |  |  |
| Software acquisition |  |  |  |  |  |  |  |  |  |  |  |
| Software implementation |  |  |  |  |  |  |  |  |  |  |  |
| Training |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring |  |  |  |  |  |  |  |  |  |  |  |
| Testing |  |  |  |  |  |  |  |  |  |  |  |
| Test case definition |  |  |  |  |  |  |  |  |  |  |  |
| Test case creation |  |  |  |  |  |  |  |  |  |  |  |
| Automatic test Implementation (where applicable) |  |  |  |  |  |  |  |  |  |  |  |
| Testing |  |  |  |  |  |  |  |  |  |  |  |
| Reporting |  |  |  |  |  |  |  |  |  |  |  |
| Incident solving |  |  |  |  |  |  |  |  |  |  |  |
| Review |  |  |  |  |  |  |  |  |  |  |  |
| Closing |  |  |  |  |  |  |  |  |  |  |  |
| Agreement on phase completion |  |  |  |  |  |  |  |  |  |  |  |

# Detailed Task Assignments / Effort Estimation

| Task No | Task | Description | Responsible | Effort estimation |
| --- | --- | --- | --- | --- |
| 1 | Regnet System Implementation | Requirement for validation phase | - Regnet implementation group |  |
| 2 | Regnet Sofia Meeting | Roll up procedure |  |  |
| 3 | Technical Quality Criteria Definition | To define the technical quality criteria and to agree on schedules and requirements | - Test designer - Regnet implementation group - Regnet consortium - Validation PM | 3t (Sofia) |
| 4 | Content Quality Criteria Definition | To define the technical quality criteria and to agree on schedules and requirements | - Test designer - Regnet content group - Regnet consortium - Validation PM | 3t (Sofia) |
| 5 | Usability Quality Criteria Definition | To define the technical quality criteria and to agree on schedules and requirements | - Test designer - Regnet content group - Regnet consortium - Validation PM | 3t (Sofia) |
| 6 | Reporting Workflow Specification | To agree on the reporting workflow | - Test designer - Regnet consortium - Validation PM | 3t (Sofia) |
| 7 | Agreement on Functional Test Cases | To agree on test cases | - Test designer - Regnet consortium - Validation PM | 3t (Sofia) |
| 8 | Validation Phase Agreement | To agree on the sub-project schedule, the tasks and the task assignements | - Test designer - Regnet consortium - Validation PM | 3t (Sofia) |
| 9 | Regnet Validation Phase | Roll up procedure |  | 62t |
| 10 | Regnet Load + Stress Tests | Roll up procedure |  | 60t |
| 11 | Finalisation of test criteria | To finally define the pass / fail criteria | - Test designer - Regnet consortium - Validation PM - Regnet implementation group | 3t |
| 12 | Detailed user modelling (test scenarios) | To define the exact simulated user behaviour | - Test designer - Validation PM - Regnet implementation group | 3t |
| 13 | Test data gathering | To acquire the data needed for testing | - Regnet content group - Technical support staff - Validation PM | 3t |
| 14 | Software acquisition | To acquire the software needed for testing | - Tool specialist | 1t |
| 15 | Set-up of test environment | To set-up the test environment | - Tool specialist | 2t |
| 16 | Test case implementation | To implement the test cases in test software | - Tool specialist | 2t |
| 17 | Carrying out of tests | To carry out the test | - Tools specialist | 1t |
| 18 | Results gathering | To gather data for evaluation | - Tools specialist | 1t |
| 19 | Results evaluation + Recommendations | To evaluate the results and to give recommendations | - Test designer - Regnet implementation group - Validation PM | 3t |
| 20 | Performance testing QA | To ensure that all issues agreed upon are addressed | - Validation PM - Test reviewer | 3t |
| 21 | Regnet Functional Tests | Roll up procedure |  | 62t |
| 22 | Creation of test manual | To create the test manual for the end users | - Test designer | 5t |
| 23 | Carrying out tests | To carry out the tests | - Regnet content group - Tester - Test person - Validation PM | 15t |
| 24 | Reporting and monitoring | To report all issues and to monitor issue resolutions | - Regnet content group - Validation PM - Regnet implementation group | 3t |
| 25 | Functional tests QA | To ensure, that all issues have been successfully addressed in time | - Regnet content group - Validation PM - Test reviewer | 5t |
| 26 | Regnet Usability Tests | Roll up procedure |  | 60t |
| 27 | Heuristic tests | Roll up procedure |  | 59t |
| 28 | Carrying out of tests | To carry out the heuristic tests | - Regnet content group | 3t |
| 29 | Data gathering | To collect the result data of the heuristic tests | - Regnet content group - Validation PM | 3t |
| 30 | Results evaluation + Recommendations | To evaluate the results of the heuristic tests and to give recommendations for improvement | - Test designer - Validation PM - Usability specialist | 5t |
| 31 | Heuristic tests QA | To ensure, that all improvements agreed upon are implemented | - Test reviewer - Validation PM | 2t |
| 32 | Scenario based tests | Roll up procedure |  | 60t |
| 33 | Create test guidelines | To create the test guidelines | - Test designer - Usability specialist | 2t |
| 34 | Translation of template | To translate the questionnaires | - Regnet content group | 2t |
| 35 | Set-up test environment | To set up the test environment | - Regnet content group | 2t |
| 36 | Identify test persons | To acquire test persons | - Regnet content group | 10t |
| 37 | Carry out tests | To carry out the test | - Regnet content group - Tester - Test person | 10t |
| 38 | Collect reports | To collect the results of the tests | - Validation PM | 1t |
| 39 | Evaluate reports + Recommend | To evaluate the outcome of the tests and to give recommendations for improvement | - Test designer - Usability specialist - Validation PM | 10t |
| 40 | Scenario based tests QA | To ensure, that all improvements agreed upon are implemented | - Regnet content group - Validation PM - Test reviewer | 3t |
| 41 | Card Sorting | Roll up procedure |  | 59t |
| 42 | Create test guidelines | To create the guidelines for card sorting | - Test designer | 2t |
| 43 | Translate cards | To translate the cards into the test persons language | - Regnet content group | 1t |
| 44 | Set-up test environment | To install the software / to set up test room | - Regnet content group | 2t |
| 45 | Identify test persons | To acquire test persons for tests | - Regnet content group | 6t |
| 46 | Carry out tests | To carry out the test | - Regnet content group - Tester - Test person | 4t |
| 47 | Collect Reports | To collect all results and to send them to the evaluator | - Regnet content group - Validation PM | 2t |
| 48 | Evaluate Reports and Recommend | To evaluate the test and to recommend improvements | - Test designer - Usability specialist - Validation PM | 2t |
| 49 | Scenario based tests QA | To ensure, that all improvements agreed upon are implemented | - Test reviewer - Validation PM | 2t |
| 50 | Regnet Content gathering and Content QA | Roll up procedure |  | 55t |
| 51 | Content gathering (continuously) | Continuos procedure | - Regnet content group | 50t |
| 52 | Content QA (continuously) | Roll up procedure |  | 5t |
| 60 | Content Integrity Checks | To ensure that data upload works properly | - Regnet content group - Technical support staff | 5t |
| 61 | Content Quality checks | To ensure that content meets commonly defined quality criteria | - Regnet content group | 5t |
| 53 | Regnet Agreement on Validation Phase Completion | Roll up procedure |  | 9t |
| 54 | Reporting on Regnet Load + Stress Tests | To report on the outcome of the load testing phase | - Validation PM - Test reviewer - Regnet consortium | 3t |
| 55 | Reporting on Regnet Functional Tests | To report on the outcome of the functional phase | - Validation PM - Test reviewer - Regnet consortium | 4t |
| 56 | Reporting on Regnet Content gathering and Content QA | To report on the outcome of the content QA phase | - Validation PM - Test reviewer - Regnet consortium | 4t |
| 57 | Reporting on Regnet Usability Tests | To report on the outcome of the usability test phase | - Validation PM - Test reviewer - Regnet consortium | 4t |
| 58 | Formal Closure and Formal Reporting on Validation | To report on the outcome of the validation phase | - Validation PM - Regnet consortium | 5t |
| 59 | Regnet Test Results Implementation Phase | To implement all issues and to tackle all incidents | - Regnet implementation group | 20t |