## Goal per Content Partner
Regnet Project Content Tracking Template for Content Partners Content Collection Goals per Content Partner
2002-06-19
IMAC
| Define data objects | Existing content | New content | New content identified from external sources | New content created internally | Content completed (1 language) | Content translated | Entered into Regnet system | Approved internally | Content loaded on staging server | Check content on staging server | Content approved on staging server
| inventory |  |  | analysis |  | data transfer |  |  |  |  | content qa
SUM (of objects in the database) | 87 | 67 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
News / Newsletter | 20 | 16 | 4
Collection | 5 | 4 | 1
Profile | 30 | 30 | 0
Address | 17 | 17 | 0
Events | 5 | 0 | 5
Links | 5 | 0 | 5
Vocabulary | 5 | 0 | 5
Note on C5: The number of objects which have to be collected by the content partner
Note on D5: Content is identified as already existing and complete
Note on E5: Number of content items to be created
Note on F5: No of new content items to be acquired from external sources
Note on G5: No of content items to be created internally
Note on H5: Number of sections where content has been created in 1 language
Note on I5: Number of content items which have been translated to target languages
Note on J5: No of content items which have been entered into the Regnet System
Note on K5: Number of content items which have been quality assured internally
Note on L5: Number content items which have been published to the staging server
Note on M5: Samuel Bruns: Number of pages that are checked in the final system
Note on N5: Number of sections that has been run through the regulatory process and is OK.

## Actual per Content Partner
Regnet Project Content Tracking Template for Content Partners Content Collection Actuals per Content Partner
2002-06-19
IMAC
| Define data objects | Existing content | New content | New content identified from external sources | New content created internally | Content completed (1 language) | Content translated | Entered into Regnet system | Approved internally | Content loaded on staging server | Check content on staging server | Content approved on staging server
| inventory |  |  | analysis |  | data transfer |  |  |  |  | content qa
SUM (of objects in the database) | 87 | 67 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
News / Newsletter | 20 | 16 | 4
Collection | 5 | 4 | 1
Profile | 30 | 30 | 0
Address | 17 | 17 | 0
Events | 5 | 0 | 5
Links | 5 | 0 | 5
Vocabulary | 5 | 0 | 5
Note on C5: The number of objects has been defined
Note on D5: Content is already existing and complete
Note on E5: Number of content items to be created
Note on F5: No of new content items to be acquired from external sources
Note on G5: No of content items to be created internally
Note on H5: Number of sections where content has been created in 1 language
Note on I5: Number of content items which have been translated to target languages
Note on J5: No of content items which have been entered into the Regnet System
Note on K5: Number of content items which have been quality assured internally
Note on L5: Number content items which have been published to the staging server
Note on M5: Samuel Bruns: Number of pages that are checked in the final system
Note on N5: Number of sections that has been run through the regulatory process and is OK.

## Actual in %
Regnet Project Content Tracking Template for Content Partners Content Collection Actuals per Content Partner in %
2002-06-19
IMAC
| Define data objects | Existing content | New content | Identified from external sources | Created internally | Content completed (1 language) | Content translated | Entered into Regnet system | Approved internally | Content loaded on staging server | Check content on staging server | Content approved on staging server
| inventory |  |  | analysis |  | data transfer |  |  |  |  | content qa
SUM (of objects in the database) | 87 | 67 | 20 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
News / Newsletter | 20 | 16 | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Collection | 5 | 4 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Profile | 30 | 30 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Address | 17 | 17 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Events | 5 | 0 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Links | 5 | 0 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Vocabulary | 5 | 0 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%