REGNET-IST-2000-26336

Interim Report

| Project acronym | REGNET |  | Contract nr. |  | IST-2000-26336 |
| --- | --- | --- | --- | --- | --- |
| Type and Number | Interim Report no. 6.1 |  |  |  |  |
| Work package | WP 6 Information Dissemination |  |  |  |  |
| Task | T 6.1 Information Dissemination |  |  |  |  |
| Date of delivery | Contractual | 2001-06-30 | Actual | 2001-08-16 |  |
| Code name | input.docC |  | Version 01 draft  final  |  |  |
| Objective | Report |  |  |  |  |
| Distribution Type | Public |  |  |  |  |
| Authors (Partner) | SPAC |  |  |  |  |
| Contact Person |  |  |  |  |  |
| Abstract | This document describes the foreseen dissemination activities according to the Technical Annex, gives an overview of carried out activities as reported in the first Bimonthly Report, provides a methodology and a template in order to collect the contributions of the partners, organizes the activities planned for the first year of the project in a Gantt chart and fixes a schedule for updates in order to regularly check the dissemination plan. |  |  |  |  |
| Keywords List | Dissemination, events, conferences, meetings, publications, presentations web sites |  |  |  |  |
| Version log | First version |  |  |  |  |

Table of Contents

1	Introduction	3

1.1	Situation	3

1.2	Purpose	3

1.3	Overview	3

2	Foreseen dissemination activities	4

2.1	Partners involved	4

2.2	Methodology	4

2.3	Activities	6

2.3.1	Publications	6

2.3.2	Conferences/Events	7

2.3.3	Web-Sites	9

3	Carried out dissemination activities	10

3.1	Publications (printed and electronic)	10

3.2	Presentations at conferences, meetings, seminars	10

3.3	Web Sites	10

3.4	Other conventional and/or electronic printed matter	10

3.5	Contribution(s) to standardisation bodies and contributions to special interest groups	11

3.6	Contacts	11

3.7	Other	11

4	Organizing and collecting partners’contributions. Methodology and Template	11

5	To do list	13

5.1	IR6.1 updates schedule	13

5.2	Gantt chart	13

# Introduction

## Situation

The project started on April 2001. At an early stage (month 3 of 24), a Task Brief (T6.1) has been drawn up, shortly describing the Information Dissemination Acitvities as understood by the REGNET consortium in the Technical Annex.

Following the methodology outlined in the Task Brief, a template has then been designed in order to collect the contributions of the partners to WP6 Information Dissemination during the first year of the project. The template is organized in categories which correspond to different types of dissemination channels:

- publications (printed and electronic)

- presentations at conferences, meetings, seminars

- web sites

- other conventional and/or electronic printed matter

- contribution(s) to standardisation bodies and contributions to special interest groups

- contacts

- other

The template has already been distributed to the partners: their contributions will be reported in an update of this document at month 6.

While waiting for the partners’ inputs, this version of IR6.1 describes the foreseen dissemination activities according to the Technical Annex and gives an overview of the activities already carried out as reported by the partners in the first Bimonthly Report.

A plan of the activities for the first year of the project has been organized in a Gantt Chart  following the above-mentioned categories.

## Purpose

The aim of this document, quarterly updated, is to provide a plan of the dissemination activities on the basis of the inputs supplied by the partners through a template regularly updated.

IR6.1 is thus to be considered a living document throughout the entire project timeframe.

## Overview

This Interim Report IR6.1:

- analyses the foreseen dissemination activities according to the Technical Annex and provides an updated list of events for the first year of the project (section 2);

- gives an overview the activities already carried out as reported in the first Bimonthly Report (section 3);

- describes the methodology that has been followed in order to design a template through which the contributions of the partners are going to be regularly collected (section 4);

- organizes the ativities planned for the first year of the project in a Gantt chart (section 5);

- fixes a schedule for IR6.1 updates in order to regularly check the dissemination plan (section 5).

# Foreseen dissemination activities

In this section the foreseen dissemination activities are described according to the Technical Annex. The list of events for the first year of the project has been updated.

## Partners involved

As stated in the Technical Annex, 15 partners contribute to WP6 Information Dissemination.

| Partner n° | Partner short name | Person/ month |
| --- | --- | --- |
| 1 | AIT | 1 |
| 2 | ONB | 1 |
| 3 | SR | 1 |
| 4 | IMAC | 1 |
| 5 | SUL | 1 |
| 9 | TARX | 1 |
| 11 | MUS | 1 |
| 12 | MOT | 1 |
| 13 | SPAC | 1 |
| 15 | CC | 2 |
| 16 | IAT | 1 |
| 18 | ICCS | 1 |
| 19 | ZEUS | 1 |
| 22 | VALT | 2 |
| 23 | TINC | 1 |

## Methodology

Target groups

Due the multidisciplinarity (cultural institutions: museums, libraries, archives etc.; cultural industries: new  media enterprises, ASPs etc.) REGNET addresses different target groups: individuals, organisations, enterprises, associations.

The target groups addressed are coming from two domains: Cultural Heritage and New Economy.

- In the field of CH the addressees are professional at CH organizations as well as the relevant clientele and the organizations themselves. There will also be information dissemination to national and international organizations like ICOM, CIMI or ICA.

- The second domain covers the evolving new media industries and internet and application services providers. REGNET will seek the cooperation of these organizations for common workshops as well as for the organization of special seminars (digitisation, eBusiness, etc). All these activities might also rise the potential of having new customers to the REGNET network.

Territorial levels of dissemination

  - Direct Direct contacts with regional museums and archives with known interest in digitising their collections and/or possessing content suited for the development of cross-regional themes. Possible candidates are the regions of East Anglia and Buckinghamshire in the UK.

  - Half-day seminar in Flanders via personal invitation by mail, followed by the same event for the French-speaking part.

  - Publications mainly focused on the cultural and technological sections of newspapers and magazines covering a wide potential of REGNET-customers and -users: De Standaard, De Morgen, De Financieel Economische Tijd, Knack, Openbaar Kunstbezit in Vlaanderen. The same applies again for the French speaking part: Le Soir, La Libre Belgique, L’Echo de la Bourse, Le Journal des Arts.

  - Contacts with regional and federal authorities for the further deployment of the REGNET-services.

  - Lectures and publications within the standard activities of the involved partners.

  - Similar publication efforts will be made for other regions.

A specific publication strand will be focused on analysing and disseminating the implications of innovation and valorisation of cultural heritage resources in regional contexts, with special attention to the relationships between cultural heritage and tourism, and to the potential and effects of investment on cultural resources in developing regions (e.g., Obj. 1 and 2 regions). In particular 4-5 publications – coordinated with relevant activities carried out within the OpenHeritage project -  will be issued covering following themes:

- Scenarios for the investment of Cultural Heritage structural resources in less favoured Regions throughout Europe.

- Policies and facilitators for the widespread adoption of new technologies and solutions for the valorisation of Cultural Heritage.

- The meaning of "Regional" Cultural Heritage.

- Museum systems in regional contexts: between thematic networks and theme parks.

Dissemination channels

The Technical Annex identifies different types of dissemination channels:

- printed and electronic publications

- conferences, seminars,

- project WEB-Site

- participation of project members in relevant standardisation committees (e.g.CEN/ISS) and workshops

On the basis of this list a more detailed one has been structured (see section 4) in the template which will be used to regularly collect the contributions of the partners.

## Activities

Several activities had already been accurately planned in the Technical Annex. The list of Conferences/Events provided in the Technical Annex has been updated.

### Publications

- The progress of the REGNET project, especially outcomes of current research work, will be published in international and national journals either in printed or electronic form e.g:

  - Cultivate Interactive

  - e-Culture

  - Publications published by the Council on Library and Information Resources, Washington.

  - Archives & Museum Informatics, Pittsburgh.

  - D-Lib Magazine

  - ICOM News

- Besides English language publications, journals in other languages will be used to transport REGNET issues. E.g. in the German speaking region:

  - Neues Museum, Wien

  - Museum Aktuell, München

  - Nachrichten für Dokumentation, Frankfurt

- In cooperation with the Austrian National Library it is planned to start a new electronic publication, backup by a printing on demand service: “New Economy & Cultural Heritage”.

- Special publications as already foreseen now include:

  - Grossmann, S./Herget, J.: E-Commerce und Museen - Das Projekt REGNET, VMS-Bulletin, 2001

  - Grossmann, S./Herget, J.: Museen auf dem Weg in die Informationsgesellschaft, nfd - Zeitschift für Informationswissenschaft und -praxis, 2001

  - Herget, J.: New Economy, Museen und Informationswirtschaft - Bedeutung und Synergien, in: Tagung der Deutschen Gesellschaft für Informationswissenschaft und -praxis, 2002

  - Grossmann, S.: Metainformationen in der Kulturwirtschaft – Ein Analysekonzept am Beispiel des Projektes REGNET, nfd - Zeitschift für Informationswissenschaft und -praxis, 2001

  - Herget, J./Grossmann, S.: Neue Geschäftsmodelle in der Kulturwirtschaft – Am Beispiel von Museen. Publikation der DSK, Bern 2001

  - JOOP : The Journal of Object Oriented Programming (SIGS publication)

  - "Automatics and Informatics" - bimonthly national scientific journal

  - Newspaper: PC WEEK - Bulgaria

  - National bulletin  of the Union of Artists of Bulgaria

  - Web site of the European Innovation Centre, branch Sofia (electronic)

### Conferences/Events

ICHIM2001, International Cultural Heritage Informatics Meeting, Milan (Italy) September 3-7 2001. Under the aegis of: Cultural Heritage Ministry (Italy), European Commission IST Programme, Fondazione CARIPLO, Camera di Commercio di Milano. The REGNET project will be presented by AIT Title of the presentation : New Economy and Digital Culture – the REGNET project Authors: Koch Walter, Koch Gerda (AIT) Information about the meeting: The International Cultural Heritage Informatics Meeting (ICHIM) is, traditionally, the best international forum in which to examine the relationships between Technology and Cultural Heritage. ICHIM-2001 has the theme Cultural Heritage and Technologies in the Third Millennium, with the aim to emphasise the interplay between innovative technologies and their applications to Cultural Heritage (www.ichim01.polimi.it).

XML ONE-Amsertdam Conference, Amsterdam (Netherlands) 19-21 September 2001 (www.xmlone-amsterdam.com).

First Workshop on “Intelligent Cultural Heritage under FP6”, Rostock (Germany) 21 September 2001. Supported by FP5 IST Programm and organised by the Fraunhofer Institute for Computer Graphics Rostock (www.rostock.igd.fhg.de)

International Conference "Automatics and Informatics' 2001", Sofia (Bulgaria) October 2001

e2001 Conference, Venice (Italy), 17-19 October 2001. Information about the conference: the eBusiness and eWork Conference will show how emerging technologies are generating exciting research opportunities and new business ideas. This event is aimed at delegates who want to: learn about the latest developments exchange information and experiences make and renew contacts Formerly known as EMMSEC, the event’s scope is now based on the new European initiative in New Methods of Work and Electronic Commerce, which is part of the European Commission’s Information Society Technologies (IST) programme. The conference provides a forum for presentation and discussion of new highly innovative developments in e-work, e-business and e-commerce and issues related to individuals, organisations and markets in the emerging digital economy. (www.ebew.net)

European Cultural Forum of Cities and Regions of the E.U. “Supporting the European Cultural Action”, Brussels, 17 October 2001. With the support of the European Parliament, the General Directorate for Education and Culture of the European Commission, and the Committee of the Regions.

International Conference Application of new methodologies and tools for socio-economic analysis in the cultural heritage domain, Cagliari (Italy), 19-20 October. Organized by Gruppo Atlantis and CRENOS (Centro Ricerche Economiche Nord Sud, Università di Cagliari). (www.crenos.unica.it).

EVA 2001 Berlin (Electronic Imaging & the Visual Art), Berlin, 14-16 November. IMAC will contribute to the conference: Title of the paper: Cultural Heritage in Regional Networks - Neue Modelle, Konzepte undInformationssysteme für den Kulturbetrieb (New Models, Concepts and Information Systems for the Cultural Area) Authors:Silke Grossmann, Josef Herget Information about the Conference: EVA Berlin as a part of the EVA Conference Network (Electronic Imaging & theVisual Arts) is to bring together especially scientists producing information technology tools for modern presentation, representation and working methods and interested people from museums, galleries, libraries and public administration. (www.vasari.co.uk)

IST 2001 Technologies Serving People, Düsseldorf (Germany) 3-5 December 2001. The IST 2001 Event is organised by the Information Society Directorate-General of the European Commission, in close co-operation with the State of Nordrhein-Westfalen (Germany). (http://europa.eu.int/information_society/newsroom/istevent/)

Culturalia, Rome (Italy) December 2001 (www.fieradiroma.it)

Eva 2002 Florence (Electronic Imaging & the Visual Art) Florence (Italy) 25-29 March. Information about the conference: one of the main topics of this conference, which we would like to draw your special attention to, are the Mediterranean Initiatives in Technology for Cultural Heritage. Offers of Papers, Workshops & Demonstrations must be submitted to at least one of the Co-Chairman by 30 November 2001. (www.vasari.co.uk)

A REGNET Conference is scheduled to be held in third quarter 2002. The Austrian National Library has offered their facilities to host such a conference. The theme will be: “Cultural Heritage and the new economy”. Main topics will cover: - New economy models for Cultural Heritage - E-Business perspectives for museums, libraries and archives - Wireless access to Cultural Content and services - Electronic and personalized production of digital goods - Information management strategies for cultural institutions - New job opportunities - The “digital value chain” - Standards and methods - Education and training The conference will be accompanied by a exhibition (vendors and providers of innovative software solutions, e.g. virtual exhibition generator, etc). If possible the conference will be organized in combination with an event of the CIMI Institute (Consortium for the Interchange of Museum Information) to reach also non European guests.

### Web-Sites

The REGNET-Project Activities will be supported by a WEB-Server which is located at AIT. The Server can be accessed by the project members via: http://www.regnet.org and is protected by User Id and Password. There is also a public area which can be accessed via: http://www.regnet.org/pub . The Server is already up and running.

# Carried out dissemination activities

In this section the dissemination activities carried out by the partners during the first two months of the Project are described according to the first Bimonthly Report. The description is organized in categories, according to the list defined in the template which have been designed in order to collect the contributions of the partners (see section 4).

## Publications (printed and electronic)

AIT Part of an article and  interview on culture and Information technology for the official journal for the national Austrian book fair, held at Graz university from the 24th to the 26th of April.

SR Press text

IMAC Preparation of publications: Decision about themes and publication titles (see section 2.3.1), contact to possible publishers.

MUS A first draft was made for a publication in the Journal of the Dutch Museum Society

ICCS Publication of REGNET project description in the Bulgarian bimonthly Journal “Automatics and Informatics”, No 1-2, 2001

## Presentations at conferences, meetings, seminars

AIT Presentation of REGNET at the ODOK’01, the Austrian conference for documentation, at Graz on the 25th of April.

ONB  Presentation of the Regnet activities in Budapest at the IST/Europrix Workshop in Budapest
(20th of april 2001)

SUL A short presentation of the project at Linköping University, Norrköping Campus by Ingrid Cantwell

## Web Sites

See section 2.3.3

## Other conventional and/or electronic printed matter

AIT Preparation of dissemination material (project information sheets, partner statements etc..) for the kick-off press conference. Design of REGNET logo, REGNET business letter.

## Contribution(s) to standardisation bodies and contributions to special interest groups

None.

## Contacts

IMAC Information and short presentation of the project in the context of other relevant projects (e. g. DSK - Datenbank Schweizerischer Kulturgüter) and related institutions with similar (research) focus.

SPAC Searches and contact of various kinds of informations channels.

TARX Contact with the Archives of Mechelen for participation in REGNET. Setting up a checklist of English museums with potential to be included into REGNET.

## Other

AIT  Interviews and article placement on REGNET for three local newspapers and radio.

# Organizing and collecting partners’contributions. Methodology and Template

A list of categories has been identified in order to collect and report the contributions of the partners according to the different types of dissemination channels used:

- publications (printed and electronic)

- presentations at conferences, meetings, seminars

- web sites

- other conventional and/or electronic printed matter

- contribution(s) to standardisation bodies and contributions to special interest groups

- contacts

- other

On the basis of this list, a form to be filled by the partners has been designed:

1. Publications (printed and electronic) Please list also not yet published papers Author(s). Title. Journal (review,magazine etc.) or Web Site. Number - Date. Abstract (max 1000 characters). 2. Presentations at conferences, meetings, seminars List the events you have attended and/or those you plan to attend Name and type of event (conference, meeting, seminar…). Date. Venue. Information about the event (objectives, topics discussed,target groups addressed, etc.). Author(s) of the presentation. Title. Abstract (max 1000 characters). 3. Web Sites Address. Short Description (content, main functionalities…). Links. Status (already on-line/not yet). 4. Other conventional and/or electronic printed matter List here brochures, flyers, CD-ROMs, etc. 5.Contribution(s) to standardisation bodies and contributions to special interest groups 6. Contacts Contacts and projects promoting and implementing REGNET Project idea (similar projects; policy makers; activities related to the EU’s Strctural Funds) 7. Other

The template has already been distributed to the partners who have been invited to attach to their filled forms a copy of the articles/presentations/brochures etc. they have listed in the template. All the information thus collected will be reported in the next IR6.1 update at month 6 (IR6.1 being a part of D13 REGNET - Information Dissemination Activities).

The reference period of the template correspond to the first year of the project: the partners will be asked to update the form quarterly.

# To do list

## IR6.1 updates schedule

IR6.1 will be quarterly updated on the basis of the inputs regularly supplied by the partners through the template. The updates will provide an overview, by categories, of carried out activities. Detailed descriptions of these activities will be supplied in annexes.

## Gantt chart

In the next page a Gantt chart shows carried out and planned activities in the first year of the project (1st April 2001-31 March 2002).