REGNET-IST-2000-26336

Task Brief

| WP Number and Title |  |  | WP 6 | Information Dissemination |  |
| --- | --- | --- | --- | --- | --- |
| Task Number and Title |  |  | T 6.1 | Information Dissemination |  |
| Sub-Task Number and Title |  |  |  |  |  |
| Task Leader and Contact |  |  | SPAC | <name@organisation> |  |
| Deliverable Number and Title |  |  | D 13 | Report: "REGNET - Information Dissemination Activities" |  |
| Interm. Report Number and Title |  |  | IR 6.1.1 | "Information Dissemination" (2001-06-30) |  |
| Start Date: |  | 2001.04.01 |  | End Date: | 2001.06.30 |
| Objectives: Information Dissemination |  |  |  |  |  |
| Description of Work: Information Dissemination will be done using different types of dissemination channels: Project WEB-Site (see attachment), conferences, seminars, printed and electronic publications. Special attention will be drawn to the participation of project members in relevant standardisation committees (e.g. CEN/ISS) and workshops. A special event will be a conference which will be held in Vienna in Autumn 2002 and organized by the Austrian National Library (see also attachment). REGNET will also provide input into the Cultivate Interactive journal. In close cooperation with the Austrian node of the Cultivate Network (CSC-Cultural Service Centre Austria) the project will be presented on several occasions and also be reported on the cultivate elist. The target groups addressed are coming from two domains: Cultural Heritage and New Economy. In the field of CH the addressees are professional at CH organizations as well as the relevant clientele and the organizations themselves. There will also be information dissemination to national and international organizations like ICOM, CIMI or ICA. The second domain covers the evolving new media industries and internet and application services providers. REGNET will seek the cooperation of these organizations for common workshops as well as for the organization of special seminars (digitisation, eBusiness, etc). All these activities might also rise the potential of having new customers to the REGNET network. A dedicated Time-Schedule (MS-Project) including events and publication dates has to be developed for the whole project and to be refined on a quarterly basis. This schedule has to include as well international as national/regional activities. |  |  |  |  |  |
| Description of expected results: A REGNET Conference is scheduled to be held in third quarter 2002. The Austrian National Library has offered their facilities to host such a conference. The theme will be: “Cultural Heritage and the new economy”. See: Attachments of the Technical Annex (Page A-21). REGNET Publications. The progress of the REGNET project, especially outcomes of current research work, will be published in international and national journals either in printed or electronic form. See: Attachments of the Technical Annex (Page A-22). |  |  |  |  |  |
| Methodology: Desk work, contacts. |  |  |  |  |  |
| Partner | PM | Contact (email) |  | Obligation |  |
| - AIT | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - CC | 2 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - IAT | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - ICCS | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - IMAC | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - MOT | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - MUS | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - ONB | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - SPAC | 1 | <name@organisation> |  | Baseline for this chapter of Interim Report IR 6.1.1 Task Management and Contribution to IR 6.1.1 Information Dissemination |  |
| - SR | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - SUL | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - TARX | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - TINC | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - VALT | 2 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| - ZEUS | 1 | <name@organisation> |  | Contribution to IR 6.1.1 |  |
| Total Effort | 17 | Comment |  |  |  |