## Person Months
Effort Breakdown per task (Person/Months) Month: 1 - 24
|  | WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | TOTAL
|  | Coord. | AIT | ONB | SR | IMAC | SUL | LMG | NRM | KVA | TARX | MECH | MUS | MOT | SPAC | ALI | CC | IAT | GRAN | ICCS | ZEUS | SI | CERTH | VALT | TINC | TASK | % | Del.
WP1 | Analysis of the State of the Art and Development of Concepts | ZEUS | 8 | 4 | 7 | 10 | 3 | 1 | 1 | 1 | 6 | 1 | 3 | 11 | 3 | 1 | 4 | 5 | 1 | 7 | 15 | 8 | 6 | 14 | 5 | 125 | 23.34%
T1.1 | Definition of content to be provided | IMAC | 1 | 1 |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 2 | 1 | 1 | 2 | 1 |  |  |  |  | 21 | 3.922% | D1
T1.2 | Development of a documentation and digitization plan for content creation and management | IMAC | 1 | 1 |  | 2 | 1 |  |  |  | 1 |  | 1 |  |  |  | 2 | 1 |  | 2 | 1 |  |  |  |  | 13 | 2.428% | D1
T1.3 | Identification of standards to be used | IAT |  |  | 1 | [8 empty] | 1 |  |  |  | 2 |  |  | 1 |  |  | 2 |  | 7 | 1.307% | D2
T1.4 | Development of the System Specifications | VALT | 4 | 1 | 6 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 6 | 10 | 0 | 65 | 12.14% | D2
T1.4.0 | ~ general | VALT | 1 |  | 1 | [5 empty] | 1 |  |  | 1 | [6 empty] | 1 | 1 | 1 | 1 |  | 8 | 1.494%
T1.4.1 | ~ Node-1: Portal | MOT | 1 |  |  | 1 | [7 empty] | 6 | 1 | [5 empty] | 1 |  |  | 2 |  | 12
T1.4.2 | ~ Node-2: CH Data Management | SPAC | 1 | 1 | [6 empty] | 3 |  |  |  | 1 | [7 empty] | 2 |  |  | 8
T1.4.3 | ~ Node-3: eBusines Data Management | ZEUS |  |  |  | 1 | [7 empty] | 3 | [6 empty] | 5 |  |  | 2 |  | 11
T1.4.4 | ~ Node-4: Ontology Checker | SI | 1 | [18 empty] | 4 | 3 |  |  | 8
T1.4.5 | ~ Node-5: Electronic Publisher | SR |  |  | 5 | [16 empty] | 3 |  |  |  | 8
T1.4.6 | ~ Core System | VALT | [18 empty] | 5 |  |  | 5 |  | 10
T1.5 | Setup of the Legal Framework and Partnership Model | AIT | 1 | [14 empty] | 1 |  | 1 |  |  |  |  | 1 | 4 | 0.747% | D3
T1.6 | Definition of supported Business Functions | VALT | 1 |  |  | 2 | [6 empty] | 1 | [6 empty] | 1 |  |  |  | 2 | 2 | 9 | 1.681% | D3
T1.7 | Identification of Market (Segments) and User Groups | TINC |  | 1 |  | 2 | [13 empty] | 1 |  |  |  |  | 2 | 6 | 1.12% | D3
WP2 | Implementation of the System and Preparation of Services and Product Generation | VALT | 10 | 4 | 6 | 9 | 3 | 2 | 2 | 2 | 6 | 2 | 2 | 10 | 6 | 2 | 5.5 | 3 | 4 | 12 | 12 | 6 | 6 | 14 | 8 | 136.5 | 25.49%
T2.1 | Preparation of Content & Products | IMAC | 1 | 4 |  | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 |  | 1 | 2 | 5.5 | 2 | 4 | 6 | [5 empty] | 42.5 | 7.937% | D4
T2.2 | System Implementation (1. Version) | ZEUS | 7 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 12 | 0 | 70 | 13.07% | D5
T2.2.0 | ~ general | ZEUS | 1 |  | 1 | [5 empty] | 1 |  |  | 1 | 1 | [5 empty] | 1 | 1 | 1 | 2 |  | 10
T1.4.1 | ~ Node-1: Portal | MOT | 1 |  |  | 1 | [7 empty] | 6 | 1 | [5 empty] | 1 |  |  | 2 |  | 12
T1.4.2 | ~ Node-2: CH Data Management | SPAC | 2 | [7 empty] | 3 |  |  |  | 3 | [7 empty] | 2 |  |  | 10
T1.4.3 | ~ Node-3: eBusines Data Management | ZEUS | 1 |  |  | 1 | [7 empty] | 3 | [6 empty] | 5 |  |  | 2 |  | 12
T1.4.4 | ~ Node-4: Ontology Checker | SI | 2 | [18 empty] | 2 | 3 |  |  | 7
T1.4.5 | ~ Node-5: Electronic Publisher | SR |  |  | 5 | [16 empty] | 3 |  |  |  | 8
T1.4.6 | ~ Core System | VALT | [18 empty] | 5 |  |  | 6 |  | 11
T2.3 | Setup of the legal framework | AIT | 1 | [14 empty] | 1 |  | 2 |  |  |  |  | 2 | 6 | 1.12% | D6
T2.4 | Business process (re-) engineering | VALT | 1 |  |  | 2 | [6 empty] | 1 | [6 empty] | 2 |  |  |  | 2 | 3 | 11 | 2.054% | D6
T2.5 | Market preparation | TINC |  |  |  | 2 | [13 empty] | 2 |  |  |  |  | 3 | 7 | 1.307% | D6
WP3 | Validation of the REGNET-Demonstrator and Preparation of the Demonstration Phase | IMAC | 5 | 2 | 3 | 5 | 4 | 2 | 2 | 2 | 6 | 2 | 2 | 3 | 6 | 2 | 0 | 4 | 2 | 4 | 9 | 3 | 3 | 14 | 0 | 85 | 15.87%
T3.1 | Validation of the REGNET-Demonstrator | IMAC |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 |  |  | 3 |  | 18 | 3.361% | D7
T3.2 | Preparation of the Demonstration Phase | VALT | 1 | 1 |  | 3 | 3 | 1 | 1 | 1 | 3 | 1 | 1 |  | 3 | 1 |  | 3 | 1 | 3 | 3 |  |  | 3 |  | 33 | 6.162% | D7
T3.3 | Implementation of the version 2 of the REGNET system | ZEUS | 4 |  | 3 | 1 |  |  |  |  | 2 |  |  | 3 | 2 | [5 empty] | 5 | 3 | 3 | 8 |  | 34 | 6.349% | D8
WP4 | Demonstration, Assessment and Evaluation | TARX | 1 | 5 | 1 | 4 | 6 | 3 | 3 | 3 | 5 | 3 | 3 | 1 | 5 | 3 | 0 | 4 | 3 | 6 | 5 | 1 | 1 | 14 | 1 | 81 | 15.13%
T4.1 | Execution of the demonstration phase (trial service) | TARX |  | 5 |  | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 |  | 3 | 3 | 6 | 3 |  |  | 3 |  | 55 | 10.27% | D9
T4.2 | Refinement of system and services where appropriate and necessary | VALT | 1 |  | 1 | [5 empty] | 1 |  |  | 1 | 1 | [5 empty] | 1 | 1 | 1 | 11 | 1 | 20 | 3.735% | D10
T4.3 | Analysis of the trial service, assessment and evaluation of the system | IAT |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 6 | 1.12% | D11
WP5 | Development of an exploitation plan | MOT | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 4 | 1 | 0 | 1 | 1 | 0 | 0 | 4 | 1 | 20 | 3.735%
T5.1 | Development of a Technology implementation plan (draft) | MOT | 1 | [10 empty] | 1 | 1 |  | 2 | 1 |  |  | 1 |  |  | 2 | 1 | 10 | 1.867% | D12
T5.2 | Development of a Technology implementation plan (final) |  |  | 1 |  | 1 |  |  |  |  | 1 |  | 1 | 1 |  |  | 2 |  |  | 1 |  |  |  | 2 |  | 10 | 1.867% | D12
WP6 | Information Dissemination | SPAC | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 2 | 1 | 17 | 3.175%
T6.1 | Information Dissemination | SPAC | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 | 1 |  | 2 | 1 |  | 1 | 1 |  |  | 2 | 1 | 17 | 3.175% | D13
WP7 | Project Management | AIT | 12 | 1 | 12 | 6 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 9 | 4 | 0 | 0 | 2 | 0 | 2 | 5 | 2 | 2 | 6 | 2 | 71 | 13.26%
T7.1 | Project Management | AIT | 12 | 1 | 12 | 6 | 2 |  |  |  | 4 |  |  | 3 | 4 |  |  | 2 |  | 2 | 5 | 2 | 2 | 6 | 2 | 65 | 12.14% | D15-17
T7.2 | Quality Assurance | MOT | [11 empty] | 6 | [11 empty] | 6 | 1.12% | D14
| Total Person Months |  | 38 | 18 | 30 | 36 | 19 | 8 | 8 | 8 | 29 | 8 | 12 | 37 | 26 | 8 | 15.5 | 20 | 10 | 33 | 48 | 20 | 18 | 68 | 18 | 535.5 | 100%
|  | % | 7.096% | 3.361% | 5.602% | 6.723% | 3.548% | 1.494% | 1.494% | 1.494% | 5.415% | 1.494% | 2.241% | 6.909% | 4.855% | 1.494% | 2.894% | 3.735% | 1.867% | 6.162% | 8.964% | 3.735% | 3.361% | 12.7% | 3.361% | 100%