REGNET-IST-2000-26336

Trimonthly Report

| Project acronym | REGNET | Contract nr. | IST-2000-26336 |
| --- | --- | --- | --- |
| Type and number | Trimonthly Report no. 01 |
| Covered period | From | 2001-10-01 | To | 2001-12-31 |
| Code name | RN_TR1v01_f | Version draft ( final ( |
| Date of issue | 2002-02-20 |
| Project Partner | W. Koch (AIT GmbH) Tel: +43-316-835359-0 Hans-Sachsgasse 14/3 Fax: +43-316-835359-75 A-8010 Graz Email: kochw@ait.co.at |
| Objective | Trimonthly Report |

Table of Contents

1	Identifications	2

2	Achievements	3

3	Effort	11

4	Deliverables Dates	13

5	Incidents	14

5.1	Issues	14

5.2	Red Flags	14

5.3	Deviations from Plan	14

5.4	Others	14

# Identifications

The list of active tasks in the reporting period, with the involved partners (the Task Leader in bold type) are detailed.

| Task | Task Description | Involved Partners | Start Date | End Date |
| --- | --- | --- | --- | --- |
| 2.1.1 | Cataloguing and Digitising | AIT ONB IMAC SUL LMG NRM KVA TARX MECH MUS SPAC ALI CC IAT GRAN ICCS | 2001-10-01 | 2002-03-31 |
| 2.1.2 | Thematic Content Production | AIT ONB IMAC SUL LMG NRM KVA TARX MECH MUS SPAC ALI CC IAT GRAN ICCS | 2001-10-01 | 2002-03-31 |
| 2.2.1 | System Implementation (Version 1) Node-1: Portal | AIT IMAC MOT SPAC ZEUS VALT | 2001-10-01 | 2002-03-31 |
| 2.2.2 | System Implementation (Version 1) Node-2: CH Data Management | AIT TARX SPAC CERT | 2001-10-01 | 2002-03-31 |
| 2.2.3 | System Implementation (Version 1) Node-3: e-Business Data Management | AIT IMAC MOT ZEUS VALT | 2001-10-01 | 2002-03-31 |
| 2.2.4 | System Implementation (Version 1) Node-4: Ontology Checker | AIT SI CERT | 2001-10-01 | 2002-03-31 |
| 2.2.5 | System Implementation (Version 1) Node-5: Electronic Publisher | SR SI | 2001-10-01 | 2002-03-31 |
| 2.2.6 | System Implementation (Version 1) Core System | ZEUS VALT | 2001-10-01 | 2002-03-31 |
| 2.2.7 | System Implementation (Version 1) Prototype Management | AIT VALT ZEUS | 2001-10-01 | 2002-03-31 |
| 2.3 | Set-up of the Legal Framework and Partnership Model | AIT IAT ICCS TINC | 2001-10-01 | 2002-03-31 |
| 2.4 | Business Process (Re-)engineering | AIT IMAC MUS ICCS VALT TINC | 2001-10-01 | 2002-03-31 |
| 2.5 | Market Preparation | IMAC ICCS TINC | 2001-10-01 | 2002-03-31 |
| 5.1 | Development of a Technology implementation plan (draft) | AIT MOT SPAC CC IAT ZEUS VALT TINC | 2001-04-01 | 2002-03-31 |
| 6.1 | Information Dissemination | AIT ONB SR IMAC SUL TARX MUS MOT SPAC CC IAT ICCS ZEUS VALT TINC | 2001-04-01 | 2003-03-31 |
| 7.1 | Project Management | AIT ONB SR IMAC SUL TARX MOT SPAC IAT ICCS ZEUS SI CERT VALT TINC | 2001-04-01 | 2003-03-31 |
| 7.2 | Quality Assurance | MOT | 2001-04-01 | 2003-03-31 |

# Achievements

| Task | Achievements |
| --- | --- |
| 2.1 | Preparation of Content and Products (IMAC) |
|  | AIT Conversion of sample data from the DSK database. Analysing metadata standards (AMICO, MDA, CDOC, CDWA, MARC21, Dublin Core). First draft of a crosswalk from AMICO to Dublin Core. IMAC Clarification of task, production of task brief WP 2.1. Definition of two sub tasks and production of separated task briefs for WP 2.1.1 Cataloguing & Digitising and WP 2.1.2 Thematic content production. General task management (information of partners, distribution of reminders, overview about the work done by the partners (collecting and merging of status reports), answering of questions regarding the practical work. Testing and set up of an environment in order to improve the handling of documents and to intensify the communication (project forum & document server on the project web site). Generation of a new version of templates for the content production. LMG Cataloguing and Digitising. Translating. ALI Digitisation of 73 images: file format JPEG; 480x480 pixel; watermarked Generation of 73 objects in Italian language (sent to IMAC) Reporting to IMAC of report on the state of content generation (RN_Report_fragments_v01ALI) Installation of 73 images into Alinari’s web server. CC Definition of the main features of the REGNET content and products in the Italian Regional Pole Collection of relevant material and information from Musei Capitolini and Museo degli Argenti IAT Contribution to task 2.1: “Cataloguing and Digitising” Contacts with Gran to digitize CH objects. GRAN Digitisation of the artworks in process. Elaboration of the document fieldlist-dsk-database. Agreement achieved among the different agents participating in the project (Art Galleries, Artists & Granollers City Council) about the legal framework ICCS Acquisition of digital data, domain Artists. Content providing of 100 art pictures Incorporating of the Art data in Z39.50 server. Demo connection to the Z39.50 server of AIT. Preparation work for connecting Content data from Russia region through Z39.50 protocol |
| 2.1.1 | Cataloguing and Digitising (IMAC) |
|  | ONB ONB has harvested information about high quality archival scanners and purchased a Homrich Imaging Technik (HIT) vario digital XL working with Sinarback 23 and Phase One Power Phase FX digital back, a product which represents the state of the art in archival digitisation, enabling the digitisation of objects of smallest formats up to A0-format and larger, in best quality. Experiences with scanning and data exchange were made. ONB staff was trained on the new scanner unit, which has been put into full use for digitising theme objects as well as archival and consumer services. ONB provided Sample data (“Empress Sissi”) for the Habsburg theme and field lists for object description. |
|  | IMAC Support of partners in cataloguing their objects (clarification of common problems, guidance in the usage of templates for data entry). Preparation of sample data (collection of sample data of partners, evaluation, coordination with technical group). Preparation of own database (Swiss cultural heritage) for demonstration within REGNET. Test of data entry tools (provided by AIT). Analysis of data structures in use at the side of the content providers. Mapping to domain-specific standards/Dublin Core. SUL Digitising and cataloguing of 30 objects. NRM NRM digitised 113 objects during the period. Object description in Swedish and English. KVA Digital cataloguing of scientific instruments collection. TARX Gathering and scanning of images of St Angela and St Ursula, located in the Ursulines convent in Tildonk (Belgium) and the museums and churches in Cologne (Germany). MECH 10 top ten pieces introduced in the ADLIB collection management system Gilt leather objects fully digitised into high resolution tiff-files. 28 SAINTS items introduced in the ADLIB collection management system Upgrade of ADLIB collection management system in order to export XML-files. MUS Several collections have been identified for digitisation. Main collections which still need photographing before digitisation have been identified A first 800 images have been digitised (although not all are suited for the REGNET project) Document RN_T211v01_MUS_screenshots was delivered. This document contains screen shots from our collection management system. It gives an idea of the object information used in the Museon. Document RN_T211_MUS_Objectrecord was delivered. This example from our database gives an indication of the fields used in our records Document RN_T211_MUS_Objectrecord_English was delivered. Examples of records with the English translation of the field names. SPAC Analysis of partners contributions (task brief) concerning Cataloguing and Digitising. |
| 2.1.2 | Thematic Content Production (IMAC) |
|  | ONB ONB has worked out Structures and Fragments according to ONB model digitisation plan (Target Collections / Themes) and ONB themes inventory – especially Habsburg (Empress Sissi and Habsburg Genealogy) and Linneaus. Exemplary topic maps are in preparation. IMAC Guidance in preparing thematic content: production and evaluation of "initial" documents and examples (produced mainly by TARX). Forming of an editorial board for thematic content. Evaluation of produced thematic content. Reporting of the status of individual themes. Clarifications in general (especially between IMAC and TARX). Working on themes: Tour d'Horizon. SUL Work on the Linnaean theme with KVA. KVA Thematic texts have been researched, prepared and written. Mostly on Linnaeus theme. TARX Production of thematic texts concerning St Angela and the Ursulines in Dutch and in English. Setting up of theme schemes for SAINTS, GILT LEATHER, TOUR D’HORIZON and ART GALLERY. MECH Initiation of a forum on the REGNET web site for the themes SAINTS and GILT LEATHER Production of more than 50 thematic texts Co-ordination of collaborations and contributions for SAINTS by other partners (especially with Gotland and Alinari). |
|  | Meeting and discussion with municipal archives of Mechelen about potential participation in REGNET (looking for thematic contribution). Study of contributions of MECH for the other themes. First results: possible contribution with Dodoens for BOTANY (LINNAEUS) and architecture for EARLY RENAISSANCE. MUS Several discussions and contributions made to the content examples and technical questions for the Technies and also to the guidelines for the thematic for the generation of thematic content within REGNET RN_T212v01_Themescheme_Leather_MUS.doc was produced. Illustrating the set-up of the theme leather. RN_T212v01_Fragments_English_MUS.doc was produced as an example of a fragments RN_T212v01_Themescheme_Masks&Amulets_MUS.doc was produced. Illustrating the set-up of the theme Masks & Amulets. RN_T212v01_Themescheme_Measuring_MUS.doc was produced. Illustrating the set-up of the theme Measuring. SPAC Analysis of partners contributions (task brief) concerning Thematic Content Production. |
| 2.2 | System Implementation (1st version) (ZEUS) |
|  | AIT Task Brief for Task 2.2.1.2 and Task 2.2.2.2. General technical project control and evaluation of new technologies (dbXML 1.0b4, EJB, SOAP, JAXP, Ant, Tomcat 4.0, Velocity). XForm (an open source project for generating self-validating web forms) was tested. A Java Applet prototype for supporting geographical selections (for query restrictions) was generated. A first version of a data entry component (including search and export options) has been implemented. Work with the topic map concept and tests with topic map servers and topic map viewers were done. First samples of data provided by content providers were used to elaborate a first draft of an internal data structure for the whole Regnet System. Simple tools for converting data into this structure were implemented and also available tools were tested. Design of a RMI-Interface to the Search & Retrieval component. Design and Prototyping of a Reference System (only search part) for one native XML database server (TextML Server). Evaluation of “interchange” as an electronic catalogue system. The functionalities and interfaces were checked to get ideas for integration with such catalogue systems. SR Preparation of Task brief· Architecture discussion· EDIT component specification for SI· Interface and component design SI During the first month the review results were analysed and the next step was to create a development plan with all the related technical partners. It was decided that the Ontology component for the first demo of Regnet should be integrated before the end of February 2002. SI had an informal meeting with CERT to prepare a work plan for the development of the Ontology node. The meeting took place in Greece-Thessaloniki in November 2001. The result of this meeting was that CERT will be mainly responsible for the development of the data entry and data manipulation, while SI will be responsible for the development of the Topic Maps interface. SI had communication with SR in order to discuss the requirements and technologies needed for the development of the Electronic Publisher node. Furthermore, SI started to work on the development of a SHOE system that will be able to retrieve results from distributed databases. During these months SI was more concentrated in the development of the Ontology node. SI tested in detail the Ontopia Omnigator server and also made a research on available Topic Map tools that could be used for Regnet. A first attempt to create valid Regnet Topic Map files took place. This attempt was mainly based on the AMICO DTD and the purpose was to transform this DTD to Topic Maps. The results were delivered to the Regnet Consortium. VALT Interim report template, development of technical prototypes, UML modelisation |

| 2.2.1 | Node-1: Portal (MOT) |
| --- | --- |
|  | IMAC General coordination with task leader (management issues). Preparation of an evaluation concept: preliminary desk research, definition/formulation of scenarios in order to assure a structured evaluation process of the portal functionality, navigation structure etc. Evaluation of first portal prototypes (documentation). MOT Preparation of Task Brief 2.2.1 and definition of milestones together with the subcomponents developers Definition of the Wap Portal Prototype architecture Development of the first version of the Wap Portal Prototype and related documentation Preparation of contributes for the Review Meeting SPAC End of architecture validation by the analysis of Deliverable D2. Component analysis of the overall system, keeping care to the Data Generation component and Cultural Heritage Data Management node. Task Brief 2.2.1.1 was finalized. |
| 2.2.2 | Node-2: CH Data Management (SPAC) |
|  | TARX Working out of a complete set of practical examples of an overall theme scheme with corresponding thematic texts, object descriptions and image descriptions (the SAINTS toolkit). SPAC The set up of development environment (CVS) was finalized. Start to analyse the source code of relevant component. Task Brief 2.2.2 was finalized. CERT CERT has set up a dbXML database and developed a data management tool for the Reference System prototype, supporting actions such as add, delete, list, etc. In the following, we have worked on developing the check data integrity and the external data entry modules of the Reference System. |
| 2.2.3 | Node-3: e-Business Data Management (ZEUS) |
|  | IMAC General coordination, evaluation of PCM system. ZEUS Task Brief regarding E-Business Data Management was prepared and distributed to the partners Development of the prototype for the e-commerce part of the E-Business subsystem the e-shop (http://epsilon.zeusnet.gr/test/) (* please note the / after test is compulsory) the administrative part of the databases (http://epsilon.zeusnet.gr/test/admzdb) with password 1234 administrative part of the targets databases (http://epsilon.zeusnet.gr/test/admin) with password 1234 Development of a report for Linux server configuration, that supports the e-shop. The report provides all the software tools that were used and all the necessary steps for the installation of these tools Development of a technical report for the e-shop Part of the B2B concept has been developed (the rest is still in progress) Task Brief regarding Node 3 - Catalogue Management was prepared and distributed to the partners Development of the basic functionalities of PCMa) First description of the interfaces in WSDLb) Research for CatXML specifications) Development of interconnections between the components of PCM |
| 2.2.4 | Node-4: Ontology Checker (SI) |
|  | TARX Construction of a topic map (.xtm) reflecting part of the theme of SAINTS. Study and test of a series of topic map engines: Empolis k42, Ontopia and TM4J. A JAVA client was developed for Empolis k42. CERT CERT has developed a prototype of the Knowledge Base (in dbXML) and developed a database management system for the Ontology data. We have also simulated the interfaces between the knowledge base and all other modules of the REGNET system (portal, electronic publisher, search system, etc.) and tested data transfer from the Knowledge Base to the clients based on the RMI protocol. |

| 2.2.5 | Node-5: Electronic Publisher (SR) |
| --- | --- |
|  | SR Discussion of the publishing components and infrastructure architecture· EP-Architecture set up and planning of further steps· Discussion and set-up of development plan· Infrastructure set-up (Cocoon)· Establishing of SOAP Communication· 1st iteration documentation EP-Description· EP description review 1st increment· Applicability of neural networks for categorising and sorting content· Preparation of demonstrator· Set-Up of EP demonstrator· Implementation of EP entry point· Implementation of stylesheet table pdf· Implementation of stylesheet table html· Implementation of stylesheet for generating SMIL presentation· UML documentation of EP-System· Description of Regnet EP-System· Investigation of covax system· Resource planning until 2.1.2002· Writing of EP description 2nd draft· Architecture description for IR 2.2· SI Edit component specification· Setup of EP Prototype for internal evaluation· Installing Prototype on Cocoon 2· Preparation of EP demonstrator and installation on a LINUX machine· Writing Installation Instruction for EP Prototype0_1· SI EDIT component specification, emails· SI EDIT component communication· RN Implementation· Discussion preparation and writing of Task brief· Preparation of review in Brussels |
| 2.2.7 | Prototype Management (VALT) |
| 2.2.7.3 | ZEUS Task Brief regarding Population of Database was prepared and distributed to the partners. |
| 2.3 | Set-up of the Legal Framework and Partnership Model (AIT) |
|  | AIT The Task Brief was generated and distributed to the contributing partners for comment. First research activities regarding the CSC Europe organizational structure were performed. IAT Contribution to task 2.3: “Set-up of the Legal Framework and Partnership Model” We are preparing our inputs to this task. Those inputs will be send soon. ICCS Establishing a two level legal framework : for internal and external relations. Elaborating a sample of contract for internal and external relations. Elaborating a sample contract for internal relation between players of artists’ domain. Adaptation of Amico Full membership agreement for external relations. TINC Definition of the main features of the REGNET legal entities and roadmap for incorporation of the service centres at central and national / regional level. Collection of relevant documents to model REGNET agreements, contracts, statutes, etc. |
| 2.4 | Business Process (Re-)Engineering (VALT) |
|  | IMAC Clarification of task/coordination with task leader. Modelling of use cases for the domains Archives and Libraries. MUS Document RN_T241v01_MUS was delivered. In this a first tryout for task 2.4 was made. Document Object entry use case description.doc was made in order to establish the right approach for the task. After response to the above mentioned tryouts further use cases have been worked out in detail. These will be delivered in the coming period. ICCS Development of the Artist studio functionalities Development of Gallery functionalities Access point to the RENET is under development. Inputs to the interim report is given. VALT Interim report template, business process representation TINC Internal preparatory work for company contributions to Interim Report 2.4. |

| 2.5 | Market Preparation (TINC) |
| --- | --- |
|  | IMAC Clarification of task. Conceptual work in business planning and market engineering. Development of a structure for a market plan, development of checklists, evaluation of software to enable collaborative working on business plans. Implementing and testing of software for collaborative working on business plans. ALI Alinari’s Reproduction copyright documentation sent to TINC (modulo_diritti_riproduzione_ALINARI.pdf) Alinari’s Business legal information sent to TINC (note_legali_business_Alinari.pdf) ICCS Address of the prospective users and user groups, domain Artists have been identified. Preparation of advertising material, which will be included in the newspaper “PC Week – Bulgaria” TINC Definition of objectives and partners roles of task 2.5. Preparation, and distribution of first version of Task Brief. Thorough discussion of Task Brief with Project Manager and involved partners. Revision and distribution of a second version of the Task Brief. Distribution of first version of Interim Report 2.5. |
| 5.1 | Development of a Technology Implementation Plan (draft) (MOT) |
|  | IAT Internal work in order to prepare the contribution to TIP document. Contacts with some firms/organizations to get information about social, scientific and commercial use of Regnet services. TINC Coordination with MOT to establish better coordination between TIP activities and T2.5. Revision of TIP template to make it more suitable to collect business indications from partners. |
| 6.1 | Information Dissemination (SPAC) |
|  | AIT Business Template for Medressa was filled in. Presentation and information dissemination on REGNET at: COVAX Meeting, Salzburg, Austria, 13-14 December 2001 CULTIVATE Regional Information Day, Innsbruck, Austria, 12 December 2001 Round Table of the Austria Ministry for economy and labour, Vienna, Austria, 20 November 2001 Eurocare Preparatory Meeting, Graz, Austria, 5 November 2001. Preparatory work on a REGNET flyer. Update on REGNET flyers in English and German for distribution purposes. SR Presentation of project in SNML-Roundtable· Knowledge transfer activities; dissemination of know-how in local research magazines (NOEO-Wissenschaftsmagazin, Salzburger Bildungs. und Forschungseinrichtungen, Salzburg, exposure 01/2001) IMAC Attendance of EVA 2001 (2001-11-14 to 2001-11-16): Presentation of the project on the Co-operation day (2001-11-16). Finalizing of a publication for the VMS Bulletin (Publication date: 2002). Preparation of an abstract for the call for papers "DGI-Online-Tagung 2002". Attendance of "Berliner Herbsttreffen zur Museumsdokumentation 2001-10-22 to 2002-10-24: Contacts, distribution of flyers and stickers. Presentation of the REGNET concept during the DSK-meeting (former Database of Swiss Cultural Heritage, 2001-18-12). Reporting for IR 6.1. TARX Several meetings with the archives of the cities of Mechelen and Brugge in order to establish further collaboration with REGNET. Edition of a new version of the thematic approach for the CULTIVATE publishing. |
|  | MUS In this reporting period no mayor steps were taken. Only bilateral dissemination was done. Museon commented on the Consortium Agreement and made suggestions for an additional paragraph. SPAC The first updated version of IR6.1 has been produced and presented during the 1st Review Meeting. CC Attendance at Culturalia, Rome December 2001 and dissemination of Regnet project Planning of participation to EVA Beijing and Euro-China 2002. IAT An article about REGNET was published in a regional Innovation Magazine. Some of those magazines have been sent to the Project Manager. Contacts with some cultural entities in order to organize a meeting about Regnet Services. ICCS Registration for the Conference “ComSysTech’2002”, 31.5-1.6.2002 and presentation of REGNET. TINC Planning of participation to EVA Beijing and Euro-China 2002. |
| 7.1 | Project Management (AIT) |
|  | AIT Formatting and partly proof reading of the deliverables D1, D2, D3 and the Appendixes. Organization and attending the Regnet Review Preparation Meeting in Brussels at the 24th of October 2001. Organization and attending the 1st Regnet Review Meeting in Brussels at the 25th of October 2001. Organization and attending of the RN-OH Cluster meeting at Brussels on 26 October 2001. Integration of the bimonthly reports from all partners and compilation of the Project Bimonthly Report no. 3. Integration of the progress reports from all partners and compilation of the Project Progress Report no. 1. Management of submission of REGNET 1st Cost Statement. Constant updates to the project internal web-site, and update of the public website (Deliverables are now available). For uploading and easy access to documents in addition to the existing web-based access a document management server based on XML has been introduced. Managing of the project internal Regnet list server. Organization of the REGNET Project Management Meeting at Barcelona January 2002. Coordination management of the first REGNET Contract amendment, which was then signed in December 2001. ONB 3. Bimonthly report & 1. Cost Statement written & delivered, status report to task leader SR Technical project-management:· Review of contributions to D2 and feedback· Development of glossary· Development of reference· Quality Assurance discussion MOT and Template development· Preparation and review of Task briefs· Task Briefs for 2nd Phase· Review of contributions to 1st iteration and feedback· Use Case discussion IMAC· Demo data template validation· Test data discussion with IMAC· Assembling of State of work 1st iteration· Endorsement for consumables CST, fax an Koch· Iteration 1 planning and status of work evaluation· Upload MOT contribution· Reading and evaluation of 1st iteration documentation· Coordination of CVS structuring and documentation· Documentation of CVS-Structure· E-Mail reminder SPAC· Structuring of proposal· Preparation of Review Meeting· Preparation and attendance of OH Clustering Meeting Administrative project-management:· Preparation of Cost Claim No.01· Preparation of Progress Report No.01· Preparation of BM No.03 IMAC Coordination of tasks in WP 2 (work contents, dissemination), especially coordination of content production and technical development. Various management issues. Finalizing first deliverable D1 (after Editorial Group Meeting). Preparation and attendance of Project Review Meeting Brussels (2001-10-25). Reporting PR 1 (progress report), BR 3 (Bimonthly report) and CST 1 (cost statement). |
|  | TARX Co-ordinating interventions towards several content partners for streamlining the thematic approach via guidelines, explanatory documents, etc. In collaboration with IMAC: support for the setting up of he task brief for content production. SPAC Participation to the pre-Review Meeting (Brussels 24 October 2001) and to 1st Review Meeting (Brussels 25 October 2001): presentation of WP6 achievements and planned activities. Participation to the 1st Cluster Meeting (Brussels 26 October 2001): drawing up of the minutes of the meeting. Internal management. IAT Coordination with different partners related to the elaboration of tasks 2.3. ICCS Work for the subcontractor SUSU and project management tasks. ZEUS Attendance at the review meeting in Brussels and presentation of Deliverable Report 2 to the EU reviewers· Preparation of Trimonthly Report No.1 VALT Technical management. TINC Preparation of and participation to review meeting in Brussels. Extraordinary meeting with MOT in Turin on 09/10 to discuss TIP - with special reference to the distributed template - and its relationship with T2.5. Extraordinary meeting with the Project Manager in Rome on 16/10 to discuss main features of the REGNET legal entities, business and marketing plan and other allied topics. Co-ordination of activities and involved partners in T2.5. |
| 7.2 | Quality Assurance (MOT) |
| 7.2 | MOT Preparation of contribute for the Review meeting Support on CVS structure definition QA Support & IR7.2 progress |

# Effort

| Period | 2001-10-01 – 2001-12-31 |
| --- | --- |

| Planned effort per active task (Person*Months) |
| --- |
| Partners | T2.1 | T2.2 | T2.3 | T2.4 | T2.5 | T5.1 | T6.1 | T7.1 | T7.2 | Tx.y | Tx.y | Planned |
| AIT | 0,5 | 3,5 | 0,5 | 0,5 |  | 0,25 | 0,125 | 1,5 |  |  |  | 6,875 |
| ONB | 2 |  |  |  |  |  | 0,125 | 0,125 |  |  |  | 2,25 |
| SR |  | 3 |  |  |  |  | 0,125 | 1,5 |  |  |  | 4,625 |
| IMAC | 1,5 | 1 |  | 1 | 1 |  | 0,125 | 0,75 |  |  |  | 5,375 |
| SUL | 1,5 |  |  |  |  |  | 0,125 | 0,25 |  |  |  | 1,875 |
| LMG | 1 |  |  |  |  |  |  |  |  |  |  | 1 |
| NRM | 1 |  |  |  |  |  |  |  |  |  |  | 1 |
| KVA | 1 |  |  |  |  |  |  |  |  |  |  | 1 |
| TARX | 1 | 2 |  |  |  |  | 0,125 | 0,5 |  |  |  | 3,625 |
| MECH | 1 |  |  |  |  |  |  |  |  |  |  | 1 |
| MUS | 0,5 |  |  | 0,5 |  |  | 0,125 |  |  |  |  | 1,125 |
| MOT |  | 5 |  |  |  | 0,25 | 0,125 | 0,375 | 0,75 |  |  | 6,5 |
| SPAC | 0,5 | 2,5 |  |  |  | 0,25 | 0,125 | 0,5 |  |  |  | 3,875 |
| ALI | 1 |  |  |  |  |  |  |  |  |  |  | 1 |
| CC | 2,75 |  |  |  |  | 0,5 | 0,25 |  |  |  |  | 3,5 |
| IAT | 1 |  | 0,5 |  |  | 0,25 | 0,125 | 0,25 |  |  |  | 2,125 |
| GRAN | 2 |  |  |  |  |  |  |  |  |  |  | 2 |
| ICCS | 3 |  | 1 | 1 | 1 |  | 0,125 | 0,25 |  |  |  | 6,375 |
| ZEUS |  | 6 |  |  |  | 0,25 | 0,125 | 0,625 |  |  |  | 7 |
| SI |  | 3 |  |  |  |  |  | 0,25 |  |  |  | 3,25 |
| CERT |  | 3 |  |  |  |  |  | 0,25 |  |  |  | 3,25 |
| VALT |  | 6 |  | 1 |  | 0,5 | 0,25 | 0,75 |  |  |  | 8,5 |
| TINC |  |  | 1 | 1,5 | 1,5 | 0,25 | 0,125 | 0,25 |  |  |  | 4,625 |
| Total | 21,25 | 35 | 3 | 5,5 | 3,5 | 2,5 | 2,125 | 8,125 | 0,75 |  |  | 81,75 |

| Effort resources used for the reporting period (Person*Months) |
| --- |
| Partners | T2.1 | T2.2 | T2.3 | T2.4 | T2.5 | T5.1 | T6.1 | T7.1 | T7.2 | Tx.y | Tx.y | Total |
| AIT | 0,18 | 4,5 | 0,06 |  |  |  | 0,02 | 2,11 |  |  |  | 6,87 |
| ONB | 1,34 |  |  |  |  |  |  | 0,05 |  |  |  | 1,39 |
| SR |  | 2,99 |  |  |  |  | 0,18 | 1,41 |  |  |  | 4,58 |
| IMAC | 1,85 | 0,7 |  | 0,6 | 1,4 |  | 0,3 | 1,1 |  |  |  | 5,95 |
| SUL | 0,7 | 0,3 |  |  |  |  |  |  |  |  |  | 1 |
| LMG | 0,56 |  |  |  |  |  |  |  |  |  |  | 0,56 |
| NRM | 2 |  |  |  |  |  |  |  |  |  |  | 2 |
| KVA | 2 |  |  |  |  |  |  |  |  |  |  | 2 |
| TARX | 1,09 | 2,11 |  |  |  |  | 0,1 | 0,4 |  |  |  | 3,7 |
| MECH | 0,93 |  |  |  |  |  |  |  |  |  |  | 0,93 |
| MUS | 0,75 |  |  | 0,25 |  |  |  |  |  |  |  | 1 |
| MOT |  | 4 |  |  |  |  |  |  | 0,5 |  |  | 4,5 |
| SPAC | 0,25 | 2 |  |  |  |  | 0,15 | 0,5 |  |  |  | 2,9 |
| ALI | 1,2 |  |  |  |  |  |  |  |  |  |  | 1,2 |
| CC | 2 |  |  |  |  |  | 0,25 |  |  |  |  | 2,25 |
| IAT | 0,2 |  | 0,4 |  |  | 0,1 | 0,2 | 0,4 |  |  |  | 1,3 |
| GRAN | 2 |  |  |  |  |  |  |  |  |  |  | 2 |
| ICCS | 3 |  | 1 | 1 | 1 |  | 0,125 | 0,25 |  |  |  | 6,375 |
| ZEUS |  | 6 |  |  |  |  |  | 0,625 |  |  |  | 6,625 |
| SI |  | 3 |  |  |  |  |  | 0,15 |  |  |  | 3,15 |
| CERT |  | 7 |  |  |  |  |  |  |  |  |  | 7 |
| VALT | 6 | 0,5 | 2 |  |  |  |  |  |  |  |  | 8,5 |
| TINC |  |  | 0,6 | 0,6 | 2,2 | 0,35 | 0,15 | 0,45 |  |  |  | 4,35 |
| Total | 26,05 | 33,1 | 4,06 | 2,45 | 4,6 | 0,45 | 1,475 | 7,445 | 0,5 |  |  | 80,13 |

| Cumulative Project effort in person-months |
| --- |
| Originally |  | Actually |
| Plan. | Cumul. | Period | Spent | Cumul. |
| 50,69 | 50,69 | 2001-04-01 – 2001-05-31 | 39,134 | 39,134 |
| 52,58 | 103,27 | 2001-06-01 – 2001-07-31 | 56,222 | 95,356 |
| 48,73 | 152 | 2001-08-01 – 2001-09-30 | 58,654 | 154,01 |
| 81,75 | 233,75 | 2001-10-01 – 2001-12-31 | 80,13 | 234,14 |

# Deliverables Dates

| Deliverables Code & Description | Originally planned | Current planned | Actual delivery | Partner Responsible |
| --- | --- | --- | --- | --- |
| D1 Content Creation and Content Management | 30.9.2001 | 30.9.2001 | 30.9.2001 | IMAC |
| D2 The REGNET-System: Specifications and State of the Art | 30.9.2001 | 30.9.2001 | 30.9.2001 | ZEUS |
| D3 REGNET-Enterprise Engineering and Market Analysis | 30.9.2001 | 30.9.2001 | 30.9.2001 | VALT |
| D4 Available Content and Products | 31.3.2002 | 31.3.2002 |  | IMAC |
| D5 The REGNET-System - Version 1 | 31.3.2002 | 31.3.2002 |  | ZEUS |
| D6 System Services and Business Processes | 31.3.2002 | 31.3.2002 |  | VALT |
| D12 Technological Implementation Plan | 31.3.2003 | 31.3.2003 |  | MOT |
| > Interim Report IR5.1v01 | 30.9.2001 | 30.9.2001 | 17.9.2001 | MOT |
| > Interim Report IR5.1v02 | 31.3.2002 | 31.3.2002 |  | MOT |
| D13 REGNET – Information Dissemination Activities | 31.8.2001 | 31.3.2003 |  | SPAC |
| > Interim Report IR6.1v01 | 30.9.2001 | 30.9.2001 | 17.10.2001 | SPAC |
| > Interim Report IR6.1v02 | 31.3.2002 | 31.3.2002 |  | SPAC |
| D14 REGNET – Quality Assurance System | 30.9.2001 | 31.3.2003 |  | MOT |
| > Interim Report IR7.2v01 | 30.9.2001 | 30.9.2001 | 21.9.2001 | MOT |
| > Interim Report IR7.2v02 | 31.3.2003 | 31.3.2003 |  | MOT |
| D16 Project Presentation (WEB Presence) | 30.6.2001 | 30.6.2001 | 30.6.2001 | AIT |
| > Updated Web Presence (new design) |  |  | 15.10.2001 | AIT |
| > Updated Web Presence |  | 31.3.2002 |  | AIT |
| D17 Project Presentation (Fact Sheet) | 30.6.2001 | 31.7.2001 | 27.7.2001 | AIT |
| > Updated Fact Sheet | 31.3.2003 | 31.3.2003 |  | AIT |

# Incidents

Summarise the mayor incidents if any in the reporting period.

## Issues

| Task | Issue description | Action Items |
| --- | --- | --- |
| Tx.y | Here describe the issues or problems that might affect achievements, delay activities, deliverables or milestones. | Corrective action envisaged by the project to overcome the issue. This includes the expected impact in terms of delays, quality and quantity of work. |

## Red Flags

| Task | Red Flag description | Recommended Solutions |
| --- | --- | --- |
| Tx.y | Here describe serious problems that cannot be addressed at the project level and require urgent attention from the Commission Services. | Describe possible solutions with pros and cons, and if possible recommend one of them. |

## Deviations from Plan

| Task | Deviation description | Recommended Solutions |
| --- | --- | --- |
| Tx.y | List any deviation from plan | Describe the action that will be taken: Which deliverables and Work packages are affected Why are deliverables not on schedule What is proposed Rationale for requested change. |

## Others

Report any item of interest, such as name or address changes, team changes, responsibilities reassignment, or other.

Footnote to Trimonthly report procedure:

Contributions of partners are integrated without any changes or evaluation.

The first project review took place at Brussels on the 25th of October. The overall evaluation of the project results so far led to a “green light” meaning continuation of the project without major corrections. The official review report was sent to the project coordinator on the 26th of November and consequently transferred to all partners and put onto the internal project web server.

The signing process of the consortium agreement to REGNET (RN_CAv03) has started already before the project review and is continuing. The document is brought to the extended project management meetings by AIT and partners have the possibility to sign there.

A request for an amendment to the Contract concerning SPAC change of legal address and of corporate status has been submitted and accepted

SPAC new legal address:

SPACE S.p.A.

Piazza del Carmine 22

09124 Cagliari

Italy

Tel.: +39 070 604741

Fax: +39 070 60474316

SPACE has also modified its corporate status, passing from a S.r.l. (Società a responsabilità limitata) to a S.p.A. (Società per Azioni).

Following these modifications the V.A.T number has changed, whereas the fiscal code is unchanged.

The new V.A.T. number is:

02658200924

The fiscal code is:

01728860972

The first amendment to the REGNET contract has been signed in December and distributed electronically to the partners, as well as published on the internal web site.

It contained in principal the following changes:

Changes of the addresses of the partners MOT, SPAC and IAT and a shift from consumables costs to travel costs for TARX.

# Text boxes

CULTURAL HERITAGE in REGIONAL NETWORKS