EUROPEAN COMMISSION -D.G. INFORMATION SOCIETY

IST  PROGRAMME

*********

2nd  PROJECT REVIEW REPORT

Period : October 1st 2001 – June 30th 2002

********************

- PROJECT TITLE		: Cultural Heritage in Regional Network

- ACRONYM			: REGNET

- PROJECT NUMBER		: IST-2000-26336

- DATE OF EVALUATION	: July 4, 2002

- VENUE				: Luxembourg

- PARTICIPANTS

- European Commission     : Jan Hoorens, Project Officer

- Project Partners		 : The list of participants is attached as annex 2 hereafter

- Reviewers		 : Jean-Louis Pascon

Jean-Pierre Bouillot

7. PROJECT COST			: 5 038 000 €

EC FUNDING			: 2 448 468 € (48,6 %)

MANPOWER			: 562,2 persons/month

The present review report has been drafted by Jean-Louis Pascon, acting as the coordinating reviewer/rapporteur and, Jean-Pierre Bouillot, acting as reviewer .

It represents therefore the opinion of the review team.

********************

Date : 	August 1st 2002

Place : 	Saint Quentin Fallavier			Senningerberg

Name :      	Jean-Louis Pascon				Jean-Pierre Bouillot

Signatures:

0. EXECUTIVE SUMMARY

The project was funded by the European Commission under a « cost-reimbursement contract for research and technological development/demonstration  projects », IST Program, Key Action 3, Action line 3-2-3 (contract Number IST-2000-26336).

The project has a contractual duration of 24 months.

The project review covered the period corresponding to the 2nd period of the project life (October 1st 2001 – June 30th 2002).

Previous review took place on October 25th 2001 (Brussels).

The review aimed at assessing the fulfilment of the project work plan, the achievement of the project objectives, the fulfilment of the deliverables, the reality of the resources employed, the use of reasonable endeavours and the likelihood of the achievement of the results and their use potential.

The review took place on July 4th, 2002, at the European Commission in Luxembourg, EUFO building, and was carried out as described hereafter under item 1 “Methodology”.

Due to the number of partners in this project, only 14 partners attended the meeting, but the balance between cultural organizations and technical companies attending has been appropriate. All present partners participated in the review and contributed to the presentation of the activity reports and/or of the deliverables as well as of the work programme for the following period.

The review team received from the partners a comprehensive report, both in writing and verbally, on the progress status of the project and the discussions, which followed the presentations, were open and constructive.

Key achievements during the review period include:

- Implementation of the system, preparation of the services and product generation included:

  - Preparation of the content;

  - Implementation of the first version of the prototype;

  - Set-up of the legal framework (especially the launching of the REGNET European Economic Interest Group);

  - Business process re-engineering;

  - Market study.

- First draft of the TIP (Technology Implementation plan);

- Dissemination activities.

No major deviations from the project objectives were observed. These objectives were to:

- Develop the first prototype of the service;

- Inventory of existing content in the electronic catalogues held locally;

- Integrate a distributed search and retrieval system to achieve interoperability  across the cultural organisations' catalogues;

- Define the “Information Products and Services” including the “supply chains”;

- Set-up of the legal framework of the business transactions (payment features, copyright management, authentication control, etc).

The project is considered to address the programme objectives fully.

In terms of provision of deliverables, the project is on schedule. Completeness and quality of deliverables was considered overall good.

The project is proceeding fully in line according to the "Description of work". No change with respect to the  "Description of work" has been observed.

Project performance with respect to the "Description of work" is as expected.

At this stage of the project, no results or success stories from the project merits publicity (e.g. for dissemination or to promote 3rd party exploitation).

Innovation enabled by the project can be qualified as at the forefront of the state of art for EbXml part of the project and as mainstream research for the other parts.

Reviewers identified no specific problems in terms of project management/co-ordination, apart those raised by the project co-ordinator.

The reviewers considered that there were overall no elements, which may give, rise to reasonable doubts as to the use of reasonable endeavours by the contractors to achieve the results aimed at by the project.

The reviewers considered that there were overall no elements which may give rise to reasonable doubts as to the likelihood of the achievement of the results aimed at by the project, or which can reasonably be expected to result in a considerable diminution of the use potential of such results.

Reviewers consider that the consortium has adequately taken account of developments outside the project in the state-of-the-art or the industry

Reviewers consider that the consortium has not fully taken account of potential synergies with other projects. Reviewers request project team to better coordinate their future developments with OpenHeritage project.

Reviewers consider that the consortium has adequately taken account of status and developments of standards.

The exploitation potential of project results is considered average.

Reviewers consider that  DUP/TIP provide a coherent plan for the exploitation of the project results.

The information dissemination reported is considered very good in respect of methods to be used, means, events, publications, media coverage and technology transfer activities.

The plan for information dissemination is considered average in respect of methods to be used, means, events, publications, media coverage and technology transfer activities.

On the basis of their findings and Art 2A4 of Annex III of the contract with the Commission, the reviewers recommend to the Commission to allow the project to continue, subject to due consideration of the recommendations in this report.

The following enclosures are attached to this report:

- Agenda of the meeting (annex 1);

- Attendance list (annex 2);,

- Updated project synopsis/fact sheet (annex 3);

- Progress indicators fiche provided by the project manager (annex 4);

- Progress indicators fiche by the review team (annex 5);

- Standard review documentation list (annex 6).

1.   METHODOLOGY

The technical verification aimed to objectively establish:

- The degree of fulfilment of the project work plan

- The degree of achievement of the project objectives as described in Annex I of the Contract

- The degree of fulfilment of the deliverables as described in Annex I

- Any elements which may give rise to reasonable doubts as to the reality of the resources that the contractors purport to have employed

- Any elements which may give rise to reasonable doubts as to the use of reasonable endeavours by the contractors to achieve the results aimed at by the project

- Any elements which may give rise to reasonable doubts as to the likelihood of the achievement of the results aimed at by the project, or which can reasonably be expected to result in a considerable diminution of the use potential of such results

The methodology and the rules provided in the contract concerning the "Technical verification" were respected, and in particular those provided in the Annex III, article 2A (Objectives of the technical verification) and article 2B (Organisation of the review) as summarised hereafter:

a) Annex III - Article 2A

The technical verification covered the provisions of the abovementioned article, but the reviewers considered also the potential for the longer-term exploitation of the project achievement and their recommendations expressed their opinion on how to enhance the chances of commercial success of the project outcome.

b)  Annex III - Article 2B

The contractors were informed by the Commission in due time of its intention to organise a review session and the names and CVs of the proposed experts were forwarded to the contractors according to the contractual provisions. The venue for the review was also agreed with the contractors (paragraph 1).

The co-ordinator approved the appointment of the experts (par. 2).

The meeting was chaired by Jan Hoorens, representing the European Commission, Information Society Directorate-General (par. 3).

On the occasion of the review, the contractors provided as much evidence as requested by the review team and a practical presentation  gave a fair idea of the possible end-products (par. 4). Reviewers received the review documentation 5 working days before the meeting. Review documentation was considered complete and timely with respect to the standard review documentation requirements provided in annex 6. Delivery mode was by website access, email, print, and CD-Rom.

The review was conducted according to the guidelines for project reviews (project monitoring in IST final, 10 September 2001) as communicated by note 2912 of 6 November 2001 to IST Directors. A copy of this document was forwarded to the reviewers and to the project co-ordinator.

This report refers to the deliverables produced by the contractors and to the verbal presentations made during the review.

2. APPROVAL OF DELIVERABLES

2.1. DELIVERABLES PRESENTED

The following  main deliverables were produced by the end of the review period:

- RN_D4v02 Available Content and products (With RN_D4v01_appendix);

- RN_D5v02 Development of a technological implementation plan (with RN_D5v02_appendix);

- RN_D6v02 System services and business processes (with RN_D6v01_appendix);

- The detailed list of deliverables is enclosed hereafter:

## Status and schedule of Deliverables – updated 14 June 2002

The following table indicates the deliverables initially scheduled for the actual and previous period and their current state. The deliverables D12, D13 and D14 have been included into the table although they are scheduled for the end of the project. The interim reports stated in relation to these deliverables show the progress of work in the respective areas.

| Deliverables Code & Description | Originally planned | Current planned | Actual delivery | Partner Responsible |
| --- | --- | --- | --- | --- |
| D1 Content Creation and Content Management | 30.9.2001 | 30.9.2001 | 30.9.2001 | IMAC |
| D2 The REGNET-System: Specifications and State of the Art | 30.9.2001 | 30.9.2001 | 30.9.2001 | ZEUS |
| D3 REGNET-Enterprise Engineering and Market Analysis | 30.9.2001 | 30.9.2001 | 30.9.2001 | VALT |
| D4 Status Report “Available Content and Products” | 31.3.2002 | 31.3.2002 | 15.4.2002 | IMAC |
| D4 Status Report “Available Content and Products” – Updated Version 2 |  |  | 12.6.2002 | IMAC |
| D5 Prototype: “The REGNET-System: Version 1” | 31.3.2002 | 31.3.2002 | 15.4.2002 | ZEUS |

| Deliverables Code & Description | Originally planned | Current planned | Actual delivery | Partner Responsible |
| --- | --- | --- | --- | --- |
| D5 Prototype: “The REGNET-System: Version 1” – Updated Version 2 |  |  | 12.6.2002 | ZEUS |
| D6 REGNET “System Services and Business Processes” – Version 1 | 31.3.2002 | 31.3.2002 | 15.4.2002 | VALT |
| D6 REGNET “System Services and Business Processes” – Version 2 |  |  | 14.6.2002 | VALT |
| D6 REGNET “System Services and Business Processes” – Final Version | 30.6.2002 | 30.6.2002 |  | VALT |
| D12 Technological Implementation Plan | 31.3.2001 | 31.3.2001 |  | MOT |
| > Interim Report IR5.1v01 | 30.9.2001 | 30.9.2001 | 17.9.2001 | MOT |
| > Interim Report IR5.1v08 | 31.3.2002 | 30.4.2002 | 2.5.2002 | MOT |
| D13 REGNET – Information Dissemination Activities | 31.8.2001 | 31.3.2003 |  | SPAC |
| > Interim Report IR6.1v01 | 30.9.2001 | 30.9.2001 | 17.10.2001 | SPAC |
| > Interim Report IR6.1v02 | 31.3.2002 | 30.4.2002 | 2.5.2002 | SPAC |
| > Interim Report IR6.1v04 | 31.3.2002 | 30.4.2002 | 12.6.2002 | SPAC |
| D14 REGNET – Quality Assurance System | 30.9.2001 | 31.3.2003 |  | MOT |
| > Interim Report IR7.2 | 30.9.2001 | 30.9.2001 | 21.9.2001 | MOT |
| > Interim Report IR7.2v03 | 31.3.2002 | 30.4.2002 | 2.5.2002 | MOT |
| > Interim Report IR7.2v04 | 31.3.2002 | 30.4.2002 | 14.6.2002 | MOT |

| Deliverables Code & Description | Originally planned | Current planned | Actual delivery | Partner Responsible |
| --- | --- | --- | --- | --- |
| D16 Project Presentation (WEB Presence) | 30.6.2001 | 30.6.2001 | 30.6.2001 | AIT |
| > Updated Web Presence (new design) |  |  | 15.10.2001 | AIT |
| > Updated Web Presence |  | continuous | continuous | AIT |
| D17 Project Presentation (Fact Sheet) | 30.6.2001 | 31.7.2001 | 27.7.2001 | AIT |
| > Updated Fact Sheet | Every 6 months | 30.6.2002 | 14.6.2002 | AIT |

In agreement with the European Commission Project Officer the tasks T2.3, T2.4 and T2.5 have been extended till end of June in order to execute emergency procedures due to non-in line contribution of the marketing plan. Within the time plan there has been delivered a first version of D6. A final version of D6 will then be produced till the end of June 2002

In terms of provision of deliverables, the project is on schedule.

2.2. REVIEWERS’ COMMENTS

In terms of completeness and quality of deliverables, performance was considered average.

The reviewers draw the attention on the following comments regarding completeness and quality of the deliverables:

- RN_ D3 REGNET-Enterprise Engineering and Market Analysis

The market description should quantify the potential in each targeted country;

In addition, a competition analysis should be carried out. This should address 5-6 more relevant products in Europe in this field;

The pricing policy for the services offered should be looked at more precisely.

Mr Donzella (TINC) raised several questions to IMAC concerning the man/months charged by IMAC for task 2.5 in the first contractual period. He questioned the validity of the time charge. The consortium was requested by the review team to  provide a written reply to that question.

On the other hand, the work delivered by TINC has been criticised by the project co-ordinator. TINC's contribution to the consortium ceased de facto with effect on April 1st, 2002. This resulted in the need to re-allocate resources and to redefine the tasks of some partners. The reviewers consider such reallocation reasonable in light of the required trust for future work and the need for a more comprehensive and focussed approach in a cost effective way. Reviewers consider 1st April as a reasonable cutoff date for such restructuring,  while costs up to end of March 2002 can be considered necessary on the basis of the documentation supplied, albeit high in relation to the quality of work performed.

- RN_D4v02 Available Content and products

The explanations about the multilingualism of content description could be more precise.

- RN_D5v02 Development of a technological implementation plan

The very long description of the wireless communication infrastructures is not necessary in the context of this project. Firstly, this market is under a very deep recession, no clear view of its development is available today. Secondly, this kind of technology is too expensive for the cultural organizations. A survey of the existing technical infrastructures in the museum world should be more useful for the project.

- RN_D6v02 System services and business processes

Firstly, agreements defined in this deliverable must be checked by lawyers (Expressions like “European Union intellectual property law” or “European law” seem not really applicable);

Secondly, the two different numberings in the part 2 (one for the paragraph, one for the case description) are confusing.

Finally, several case descriptions must be more deeply analysed. For example, in some cases, registrar marks cannot be put on the objects; exhibition  management is too simply described, etc.

The form for e-business should be revised. Questions like the billing address and VAT number, currency data,  for instance, should be included.

3. CONFORMITY TO THE WORKPLAN

3.1. ADHERENCE TO WORKPLAN

Work progress has been adequately reported in terms of specific objectives for the reporting period, progress by workpackage/task, deviations and corrective actions, follow up of previous reviews and work planned for the next reporting period as by the periodic progress report.

Reviewers consider that specific objectives for the reporting period are adequate in light of the description of work.

Reported progress by workpackage/tasks shows adherence to workplan in terms of resource investment, deliverables produced, work planned for the next reporting report and follow up of previous reviews.

Project performance with respect to the "Description of work" is as expected. However the clustering with OpenHeritage was not satisfactorily developed.

At this stage of the project, no result or success story from the project merits publicity.

Innovation enabled by the project can be qualified as:

- At the forefront of state-of-the-art for EbXml part of the project;

- Mainstream research for the other parts of the project.

The project is considered to address the programme objectives fully.

3.2. DEVIATION FROM WORKPLAN

No major deviation from the workplan was observed.  However deviations were observed as for market analysis and clustering activity.

3.3. CONTINGENCY PLAN

No contingency plan was put forward by the consortium. Proposals for corrective action on observed deviations were submitted by the project co-ordinator.

4. PROJECT MANAGEMENT AND CO-ORDINATION

The reviewers examined how the project is being managed, taking account of technical achievements, business development issues, information co-ordination and human and financial resources.

A clearer description of the activity of partners TINC, SPACE, CC, SR and IMAC (work results vs. manpower claimed ) was provided by the project co-ordinator following the request of the project officer.

The examination of this information allows to conclude the following in terms of eligibility of costs:

- detailed documentation supplied does not provide obvious signs of discrepancy between work results and manpower claimed for TINC, SPACE, SR and IMAC,

- complementary information on final manpower claimed is required for CC.

Reviewers identified no specific problems in terms of project management/co-ordination.

However, the final reallocation of manpower and associated task changes within RegNet partners as a result of the restructuring of market analysis and clustering activity must be rapidly send to the Project Officer, who will advise on the implementation modalities of this restructuring.

The reviewers considered that there were overall no elements which may give rise to reasonable doubts as to the use of reasonable endeavours by the contractors to achieve the results aimed at by the project.

The reviewers considered that there were overall no elements which may give rise to reasonable doubts as to the likelihood of the achievement of the results aimed at by the project, or which can reasonably be expected to result in a considerable diminution of the use potential of such results.

5. RELATION TO THE STATE-OF-THE-ART AND TO OTHER PROJECTS

### Reviewers consider that the consortium has adequately taken account of developments outside the project in the state-of-the-art or the industry.

Reviewers consider that it is not useful to develop products based on WAP technology.

### Reviewers consider that the consortium has not fully taken account of potential synergies with other projects. Reviewers suggest that the project may benefit from stronger links with OpenHeritage to better exploit potential synergy.

6. ACTIVITIES RELATED TO STANDARDS

### Reviewers consider that the consortium has adequately taken account of status and developments of standards.

7. PLANS FOR INDUSTRIAL EXPLOITATION OF RESULTS

Reviewers consider that the DUP/TIP were produced on schedule.

-. The dissemination and Use Plan shall be updated every 6 months. The project co-ordinator shall send the relevant updates to the Commission, as well as the TIP.

The exploitation potential of project results is considered average.

At this stage of the project, reviewers consider that DUP/TIP provide a coherent plan for the exploitation of the project results.

Reviewers draw the attention on following issues with regard to the exploitation of results:

- The positioning of the competitors must be based not only on the Internet technology products, but also on “old technologies” products like books, CD-ROM, etc.

- Cultural organisation budgets must be more deeply studied because this it is the key of the success of this project;

- The AMICO business plan cannot be imported directly in Europe: the USA is monolingual; Users/Providers are mainly autonomous organisations, it is not the case in Europe;

- A better view on the target customers/users is needed.

8. PLANS FOR DISSEMINATION OF RESULTS/ WEB SITE

Reviewers consider that the past reporting and plans for dissemination of results were produced on schedule.

Reporting on past information dissemination is considered complete. The information dissemination reported is considered very good in respect of methods to be used, means, events, publications, media coverage and technology transfer activities.

The plan for information dissemination is considered complete. The plan for information dissemination is considered average in respect of methods to be used, means, events, publications, media coverage and technology transfer activities.

9. SUMMARY OF REVIEWERS’ TECHNICAL COMMENTS

The following requests and recommendations were made by the review team.

9.1. DELIVERABLES

- RN_ D3 REGNET-Enterprise Engineering and Market Analysis

The market description should quantify the potential in each targeted country;

In addition, a competition analysis should be carried out. This should address 5-6 more relevant products in Europe in this field;

The pricing policy for the services offered should be looked at more precisely.

Mr Donzella (TINC) raised several questions to IMAC concerning the man/months charged by IMAC for task 2.5 in the first contractual period. He questioned the validity of the time charge. The consortium was requested by the review team to  provide a written reply to that question.

On the other hand, the work delivered by TINC has been criticised by the project co-ordinator. TINC's contribution to the consortium ceased de facto with effect on April 1st, 2002. This resulted in the need to re-allocate resources and to redefine the tasks of some partners. The reviewers consider such reallocation reasonable in light of the required trust for future work and the need for a more comprehensive and focussed approach in a cost effective way. Reviewers consider 1st April as a reasonable cutoff date for such restructuring,  while costs up to end of March 2002 can be considered necessary on the basis of the documentation supplied, albeit high in relation to the quality of work performed.

- RN_D4v02 Available Content and products

The explanations about the multilingualism of content description could be more precise.

- RN_D5v02 Development of a technological implementation plan

The very long description of the wireless communication infrastructures is not necessary in the context of this project. Firstly, this market is under a very deep recession, no clear view of its development is available today. Secondly, this kind of technology is too expensive for the cultural organizations. A survey of the existing technical infrastructures in the museum world should be more useful for the project.

- RN_D6v02 System services and business processes

Firstly, agreements defined in this deliverable must be checked by lawyers (Expressions like “European Union intellectual property law” or “European law” seem not really applicable);

Secondly, the two different numberings in the part 2 (one for the paragraph, one for the case description) are confusing;

Finally, several case descriptions must be deeply analysed. For example, in some cases, registrar marks cannot be put on the objects; exhibition management is too simply described, etc.

9.2. WORKPLAN

No special request

9.3. PROJECT MANAGEMENT

- Issues with Consorzio Civita and Terra Incognita must be rapidly solved;

- Final decision must be send to the Project Officers as soon as it is possible;

- The performance of SPACE, versus their cost statement should be clarified by the project co-ordinator.

9.4. STATE-OF-THE-ART AND OTHER PROJECTS

Links with OpenHeritage must be stronger during the next year.

9.5. STANDARDS

No specific request.

9.6. EXPLOITATION

- The positioning of the competitors must be based not only on the Internet technology products, but also on “old technologies” products like books, CD-ROM, etc.

- Cultural organizations budgets must be more deeply studied;,

- AMICO business plan transferability to be checked;

- The market segments must be more clearly identified.

9.7. INFORMATION DISSEMINATION

No specific request.

10. CONCLUSIONS

On the basis of their findings and Art 2A4 of Annex III of the contract with the Commission, the reviewers recommend to the Commission to allow the project to continue subject to due consideration of the recommendations in this report.

The evaluation elements have been formulated at the end of the executive summary.

ANNEXES:

1.   Agenda of the review meeting (Annex 1);

- Participants list (Annex 2) ;

- Project synopsis/fact sheet (Annex 3);

- Progress indicators fiche by project manager (Annex 4);

- Progress indicators fiche by review team (Annex 5);

- Review documentation (Annex 6).

Annex 1

Agenda of Review Meeting

| Time | Issue (rapporteur) |
| --- | --- |
| 10:00 | Opening and Approval of the Agenda (EC, review chair, project partners) |
| 10:01 | Introduction, content and purpose of the review (Commission – review chair) (+ formal verification of Review Documentation) |
| 10:05 | Objectives and Progress, Follow up of REV-01 (AIT) |
| 10:20 | WP2 – Structure and Deliverables (AIT/VALT) |
| 10:50 | Detailed presentation of progress by workpackage: - WP2 - Task 2.1 Preparation of Content and Products / D4 (IMAC) |
| 11:40 | Coffee Break |
| 11:50 | Detailed presentation of progress by workpackage: WP2 - Task 2.1 Preparation of Content and Products Presentations of content cases |
| 12:15 | Detailed presentation of progress by workpackage: - WP2 - Task 2.2 System Implementation (1. Version) / D5 (ZEUS, VALT) |
| 12:45 | Detailed presentation of progress by workpackage - WP2 - Task 2.3 Setup of the Legal Framework / D6 (AIT) - WP2 - Task 2.4 Business process (re-)engineering / D6 (VALT) - WP2 - Task 2.5 Market preparation / D6 (IMAC) |
| 11:55 | Detailed presentation of progress by workpackage: Status of WP5 - Development of a technological implementation plan / D12 (MOT) Status of WP6 - Information Dissemination / D13 (SPAC) Status of WP7 - Project Management / D14/D16/D17 (AIT) |
| 13:15 | Lunch Break |
| 14:15 | Demonstration of System: Online Presentation of the REGNET System (Version one) |
| 16:15 | Coffee Break |
| 16:30 | Workplan adherence: Presentation based on Progress Reports (AIT) Q&A (reviewers) Contingency plans (reviewers) |
| 16:45 | Project Management and Co-ordination: Presentation based on Progress Reports (AIT) Q&A (reviewers) First impression (reviewers) |
| 17:00 | Relation to State of the Art and other projects: Presentation based on Progress Reports, Cluster issues (AIT) Q&A (reviewers) First impression (reviewers) |
| 17:15 | Standards: Presentation based on Progress Reports (AIT) Q&A (reviewers) First impression (reviewers) |

| Time | Issue (rapporteur) |
| --- | --- |
| 17:30 | Exploitation of results: Presentation based on Progress TIP (AIT) Q&A (reviewers) First impression (reviewers) |
| 17:45 | Information dissemination: Presentation based on IR61v04 (AIT) Q&A (reviewers) First impression (reviewers) |
| 17:50 | Meeting of the review team to discuss: - Initial impressions regarding assessment - Formulate preliminary recommendations |
| 17:55 | Presentation of the initial comments and recommendations: - presentation of initial impressions (review team) - reply from consortium (AIT) |
| 18:00 | Closing of the meeting (review chair) |

Annex 2

PARTICIPANTS LIST

Attendance List in Alphabetical Order of Partner Acronyms

AIT

AIT-Angewandte Informationstechnik GmbH

Klosterwiesgasse 32/I

A-8010 Graz

AUSTRIA

Phone: (43-316) 835359-0

Fax:(43-316) 835359-75

URL: http://www.ait.co.at/

- Gerda Koch		e-mail: kochg@ait.co.at

- Walter Koch	e-mail: kochw@ait.co.at

URL: http://www.cscaustria.at/members/koch

ICCS

Institute of Computer and Communication Systems

Bulgarian Academy of Sciences

Acad.G.Bonchev str. bl.2

1113 Sofia

BULGARIA

Phone: (359 2) 71 68 52; (359 2) 979 27 74
Fax:(359 2) 72 39 05

- Zlatka Ivanova

- Krasimira Stoilova		e-mail: k.stoilova@hsh.iccs.bas.bg

- Todor Stoilov		e-mail: tstoilov@hsh.iccs.bas.bg

IMAC

Information & Management Consulting

Weidenweg 60

D-10437 Berlin

GERMANY

Phone: (49-30) 42018684

Fax: (49-30) 42018685

URL: http://www.imac.de

- Josef Herget	e-mail: herget@imac.de

MUS

Museon

Stadhouderslaan 41

3823 CJ Den Haag

NETHERLANDS

Phone: (31-70) 3381 411

Fax: (31-70) 3381 339

URL: http://www.museon.nl

- Hub Kockelkorn	e-mail: hkockelkorn@museon.nl

- Rob Schouten	e-mail: rschouten@museon.nl

SPACE

SPACE S.p.A

Piazza del Carmine 22

09124 Cagliari

Italy

Phone: (39-0574) 27256

Fax:(39-0574) 404782

- Paolo Alongi	e-mail: paolo.alongi@spacespa.it

SR

Salzburg Research

Forschungsgesellschaft m.b.H.

Jakob Haringer Strasse 5/III

A-5020 Salzburg

AUSTRIA

Phone: (43-662) 2288-401

Fax: (43-662) 2288-222

URL: http://www.salzburgresearch.at

- Erich Gams	e-mail: erich.gams@salzburgresearch.at

SUL

Stockholm University Library

Universitatsvägen 10

10691 Stockholm

SWEDEN

Phone: (46-8) 162786

Fax:(46-8) 162786

- Ingrid Cantwell	e-mail: ingrid.cantwell@sub.su.se

TARX

TARX nv

Bordekensstraat 30

1981 Hofstade

BELGIUM

Phone: (32 015) 62 14 05

Fax: (32 015) 62 03 35

- Vic Haesaerts	e-mail: vh@tarx.be

TINC

Terra Incognita Ltd.

Alameda House, 90-100 Sydney Street

London SW3 6NJ

UNITED KINGDOM

Phone: (39-347) 7770725

Fax: (39-02) 700405187

GSM UK: (44-776) 9506737

FAX UK: (44-870) 0881516

- MM Carlo Donzella and Eriskat		e-mail: donzella@abrltd.co.uk

VALT

ValTech

Tersud, 5 Avenue Marcel Dassault

F-31500 Toulouse

FRANCE

Phone: (33 5) 62 47 52 00

Fax: (33 5) 62 47 52 01

URL: http://www.valtech.com

- Jean-Pierre Lorre		e-mail: jean-pierre.lorre@valtech.fr

ZEUS Kostas Giotopoulos

ZEUS Consulting S.A.

Trade Center - Riga Ferraiou 93 st.

26221 Patras

GREECE

Phone: (30 61) 622655

Fax:(30 61) 272425

URL: http://www.zeusconsult.gr/

- Kostas Giotopoulos	e-mail: kgiotop@zeusnet.gr

Annex 3

Project synopsys/fact sheet

REGNET

## Cultural Heritage in Regional Networks

Project URL: http://www.regnet.org/

| # Coordinator |  |
| --- | --- |
| Contact Person: Name: KOCH, Walter Tel: +43.316.835359-0 Fax: +43.316.835359-75 Email: kochw@ait.co.at | # Organisation: AIT Angewandte Informationstechnik Forschungsgesellschaft mbH Klosterwiesgasse 32/1 8010 Graz Austria |

REGNET aims to set up a functional network of service centres in Europe which provides IT-services dedicated to Cultural Heritage organisations and will be an enabler of eBusiness activities for CH organizations. Multi media industries enabling the production of electronic publications will be integrated. It will provide access and use of digital data (scientific and cultural) as well as of physical goods as provided by museum shops. The four players within the network are the content providers, the service centre operators, the system developers and end users. The content providers (museums, libraries, archives etc.) will provide access (via wired and wireless communication) to their digital contents, services and products and offer them to their clients (B2C). In return they can use the REGNET facilities for multimedia productions and data base management, or cooperate with other REGNET partners during the creation of data bases, generation of multimedia products or creation of a virtual exhibition (B2B). The service centre operators will generate income by providing the technical infrastructure (software/hardware) to content providers and other partners within the REGNET network. They offer additional IT-services and consultancies. And the system developers are selling the REGNET system to other cultural service centres and content providers. They implement additional components for the REGNET software system (additional ‘nodes’ like an ‘exhibition creator’, etc), and will generate income via licence fees for the REGNET system. For the end user the system will offer easy and wide access to cultural heritage data information and the purchase of CH related goods and services at one point, with stress on the production of personalized goods (e.g. CDROM) and services.

Main objectives of REGNET are:

- Development of a service infrastructure which enables business to business (B2B) transactions as well as business to consumer (B2C) transactions

- Development and use of existing - locally held - electronic catalogues (OPACS: Online Public Access Catalogues) referring to cultural & scientific objects contained in libraries, museums, archives, and galleries, as well as to goods and services.

- Integration of a distributed search and retrieval system to achieve a 'virtual union' catalogue of all OPACS and product/service catalogues held locally

- Definition of Information Products and Services including necessary 'supply chains' and the connected business processes and functions to deliver digital and physical goods (to provide high quality services an editorial committee will be installed)

- Setup of a legal framework necessary for all business transaction on the B2B and B2C level (containing payment features, copyright systems, authentication control, etc)

- Integration and test of existing components, standards, and methods in the field of distributed search and retrieval and e-commerce

- Access to the REGNET-WEB services with mobile devices via de facto standard protocols (such as wireless application protocol, WAP etc).

- Run a trial service (demonstration phase) which should be followed by a regular service.

The technical (research and development) objectives of REGNET are:

- Development of the ‘REGNET building blocks (nodes)’ which are necessary to build up an appropriate infrastructure to access to catalogues (containing cultural & scientific data, product & service descriptions, etc) in the Cultural Heritage domain.

Access to the ‘REGNET System’ via wired communication lines as well as via wireless mode (e.g. using the wireless application protocol WAP).

The building blocks (nodes) of the REGNET system consist of:

- REGNET – Portal (access to remote data entry, distributed search, e-business)

- REGNET – Cultural Heritage Data Management (search over distributed meta data repositories connected to stores containing digital content)

- REGNET – eBusiness Data Management (e-commerce system allowing access to distributed product/service catalogues)

- REGNET – Ontology (Metadata) Subsystem (containing the specifications of all metadata needed in the Cultural Heritage domain as well as in the e-business domain; this subsystem also stores specifications of workflows and process related metadata)

- REGNET  –  Electronic Publishing Subsystem (allowing the production of personalised digital products based on standardised meta data and workflows)

The demonstration objectives of REGNET are:

- Test the technical (hardware/software) infrastructure of the REGNET system

- Validate the developed services offered to end users and content providers

- Test the operation of at least three Cultural Service Centres

Milestones:

M1: State of the Art, Results: documentation plans (preparation of content); infrastructure to run the trial service; legal framework

M2: System implementation, Results: Content and products ready; System is tested; contracts and agreements are signed; start of market activities; Training of REGNET administrators

M3: End of system validation, Results: infrastructure at service centres ready

M4: Trial Service ends, Results: Regular service network

M5: REGNET established

Project details:

Project Reference: IST-2000-26336	Contract Type: Cost-sharing contracts

Start Date: 2001-04-01			End Date: 2003-03-31

Duration: 24 months			Project Status: Execution

| ### Participants |  |
| --- | --- |
| Angewandte Informationstechnik Forschungsgesellschaft mbH | AUSTRIA |
| Österreichische Nationalbibliothek | AUSTRIA |
| Salzburg Research Forschungsgesellschaft m.b.H. | AUSTRIA |
| IMAC Information & Management Consulting e.K. | GERMANY |
| Stockholms universitet | SWEDEN |
| Länsmuseet pa Gotland | SWEDEN |
| Naturhistoriska riksmuseet | SWEDEN |
| Kungl. Vetenskapsakademien | SWEDEN |
| TARX nv | BELGIUM |
| Stad Mechelen | BELGIUM |
| Stichting Museon (Museum vorr het Onderwijs) | NETHERLANDS |
| Motorola S.p.A. | ITALY |
| SPACE S.r.l. | ITALY |
| Fratelli Alinari I.D.E.A. S.P.A. | ITALY |
| Consorzio Civita | ITALY |
| Instituto Andaluz de Tecnologia | SPAIN |
| Ajuntament de Granollers | SPAIN |
| Zeus Consulting SA | GREECE |
| Systema Informatics S.A. | GREECE |
| Centre for Research and Technology Hellas | GREECE |
| Institute of Computer and Communication Systems, Bulgarian Acadamy of Sciences | BULGARIA |
| VALTECH | FRANCE |
| Terra Incognita Europa Limited | UNITED KINGDOM |

Annex 4

Progress indicators fiche BY PROJECT MANAGER

| IST Project Review : Progress Indicators Fiche (to be aggregated as Programme statistics) | Programme Area: IST-00-3-1.a. Date of Review : 4 July 2002 Project Number : IST-2000-26336 Project Acronym :REGNET |
| --- | --- |

| Part A – To be completed by the Project Manager and submitted to the Commission prior to the project review |  |  |  |
| --- | --- | --- | --- |
| A | Project’s view of IST Programme | State, select, or score as necessary | Comments |
| 1 | How do you value participation in the IST programme – beyond the funding of your project? | Score 0-1-2-3-4-5 0 = no value, to 5 = very high value | 5 |
| 2 | How frequent are contacts between this project and other IST project(s) ? (Eg arising from Clusters or from own-initiatives) (If “no contacts”, please do not answer the next two questions A3 & A4) |  Weekly - Monthly - Quarterly - Less frequently than quarterly - No contacts… |  |
| 3 | Which aspect(s) of your project’s work do you aim to develop or improve by having contact with other projects? (Multiple selection permitted) | - Expertise/technical knowledge sharing - Critical Mass - Consensus building - Access market / exploit results - Promotion / Reputation - Other… |      |
| 4 | How are these contacts considered by the Consortium? | - Strategic - Useful / productive - Have no effect on the project | useful/ productive |

| A | Project’s own dissemination activities, and needs | Select, or score as necessary | Comments |
| --- | --- | --- | --- |
| 5 | Is the project actively “targeting” technical or policy contributions towards: - industry guidelines / defacto “standards” - technical standards bodies | Yes / No Yes / No | Industry guidelines / defacto standards |
| 6 | Cumulative number of general purpose information products produced by the project :  Printed brochures, leaflets, facts sheets etc  Referenced S&T Publications  Conference papers - CD-ROMs DVDs Does the project have a public Web site ? | State number of different publications in each case: 1 facts sheet, 1 poster, several project leaflets in different languages 10 publications (online and in paper) 32 presentations at conferences 1 official project public website with description in 8 languages 3 partner project web sites, various link references on partner sites | Several contacts with standardisation bodies. Several contacts with cultural heritage organization on national basis. |
| 7 | Are there any results or success stories from or related to the project that merit publicity on the ISTweb? Eg to promote wider dissemination or to promote 3rd party exploitation If YES, the project manager will be contacted and support offered to prepare the in formation for publication | Yes / No | The Cultural Service Centre Europe EEIG has been applied for registration. First REGNET public demonstrator will be available online soon. |

Name:	Signature:

Organisation:	Date:

Annex 5

Progress indicators fiche BY review team

| IST Project Review : Progress Indicators Fiche (to be aggregated as Programme statistics) | Programme Area: KA- 3 –323 Date of Review :July 3, 2002 Project Number : 2000-26336 Project Acronym : REGNET |
| --- | --- |

| For completion by the Project Officer, with the Reviewers |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Results of Review meeting | State, or select one, as necessary | Comments |  |
| 1 | Is the project proceeding according to its “Description of work”? | - Fully in line X Minor changes - Major changes | The clustering with OpenHeritage must be improved |  |
| 2 | Is the project on schedule ? If NO state delay in Months | Yes |  |  |
| 3 | What is the performance of the project? (with respect to the “Description of work”) | - Higher than expected X As expected - Lower than expected |  |  |
| 4 | How many times has the project been reviewed? (Include present review) | Twice |  |  |
| 5 | Are there any results or success stories from or related to the project that merit publicity? E.g. for dissemination or to promote 3rd party exploitation | No | Not yet |  |
| 6 | Final Result of the present review | - Successful project completion (if final review) X Continue (minor changes) - Significant modifications required - Termination of Partner’s contract - Termination of overall contract | Take into account the recommendations of the review report |  |

|  | Project plans and progress made | State, or select one, as necessary (with comments if changed with respect to previous assessment) | Comments |
| --- | --- | --- | --- |
| 7 | Which of the following best describes the focus of the project? (Select one only) | - Basic scientific / technical knowledge - Guidelines, methodologies - Prototype service / software code - Prototype hardware / product X Technology demonstrator - Study (survey etc) - Take-up / technology transfer - Network of excellence - Other … |  |
| 8 | Which of the following best describes the innovation of the project ? (Select one only) | - Breakthrough X At the forefront of state-of-the-art - Mainstream research - None (Eg certain Accompanying Measures) |  |
| 9 | To what extent does the project still address the Programme objectives? | X Fully - In part - No longer relevant |  |
| 10 | Which of the following best describes the exploitation potential of project results? (in terms of commercial success, market acceptance, take-up as a standard etc) | - Very good X Average - Poor - Not Applicable (certain Accompanying Measures) | - Market segfments and target groups to be better identified - Competition analysis to be carried out. |

PO: HOORENS	Date and Signature:		Date:

Reviewers: PASCON AND BOUILLOT	Dates and Signatures:

Annex 6

review DOCUMENTATION

| 0 | List of Documents | RN_REV2_documentation |
| --- | --- | --- |
| 1 | Agenda | RN_REVA02v01 |
| 2 | Participant List | RN_REV2_att list |
| 3 | Project synopsis/fact sheet | RN_D17v02_factsheet_long, RN_D17v02_factsheet_short |
| 4 | Progress indicators fiche | RN_IST project result indicatorsJULY02_draft |
| 5 | List of Deliverables planned/actual | RN_REV2_dev list |
| 6 | Deliverables | RN_D4v02 RN_D4v01_appendix RN_D5v02 RN_D5v02_appendix RN_D6v02 RN_D6v01_appendix |
| 7 | Periodic Progress Report | RN_PR2v01_f |
| 8 | Dissemination | RN_IR61v04 |
| 9 | Quality Assurance | RN_IR72v04 |
| 10 | TIP | RN_IR51v08 |
| 11 | Summary of Cost Statements | RN_CST2_summary |
| 12 | Previous Review Report | REGNET-1st-review-JointReport-V 01MODJHV16111sendout |
| 13 | Follow-up to Previous Review Report | RN_REV2_rev1followup |
| 14 | Short Description of Demo | RN_REV2_DescrOfDemov01 |
| 15 | REGNET Technical Annex | RN_Annex1_DOW RN_Annex1_attachments |
| 16 | RN REV2 CD-ROM |  |