Attachment - PMG-01-01 / 012:

Technical Annex:  9.4 Deliverables list

Deliverables list

| Del. no. | Deliverable name | WP no. | Lead particip-ant | Estimated person-months | Del. type* | Security** | Delivery (proj. month) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D1 | Content Creation and Content Management | WP1 | IMAC | 34 | - report | - Rest. | - 6 |
| D2 | The REGNET – System: Specifications and State of the Art | WP1 | ZEUS | 72 | - report | - Pub. | - 6 |
| D3 | REGNET - Enterprise Engineering and Market Analysis | WP1 | VALT | 19 | - report | - Pub. | - 6 |
| D4 | Available Content and Products | WP2 | IMAC | 42,5 | - report | - Rest. | - 12 |
| D5 | REGNET-System: Version-1 | WP2 | ZEUS | 70 | - prototype | - Rest. | - 12 |
| D6 | System Services and Business Processes | WP2 | VALT | 24 | - report | - Pub. | - 12 |
| D7 | Validation of the REGNET System operation & Preparation of the REGNET - Demonstration Phase | WP3 | IMAC | 51 | - report | - FP5 | - 15 |
| D8 | The REGNET-System: Version-2 | WP3 | VALT | 34 | - prototype | - Rest. | - 15 |
| D9 | REGNET System operation | WP4 | TARX | 55 | - report | - Rest. | - 24 |
| D10 | REGNET – Demonstration (Trial Service) | WP4 | VALT | 20 | - prototype | - Rest. | - 24 |
| D11 | REGNET trial service and recommendations | WP4 | IAT | 6 | - report | - Pub. | - 24 |
| D12 | Technology Implementation Plan | WP5 | MOT | 20 | - report | - Rest. | - 24 |
| D13 | REGNET – Information Dissemination Activities | WP6 | SPAC | 17 | - report | - Pub. | - 5 |
| D14 | REGNET - Quality Assurance System | WP7 | MOT | 6 | - report | - Rest. | - 6 |
| D15 | - Final Report | WP7 | AIT | 6 | - report | - Pub. | - 24 |
| D16 | - Project Presentation (WEB Presence) | WP7 | AIT | 6 | - WEB-Site | - Pub | - 3 |
| D17 | - Project Presentation (Fact Sheet) | WP7 | AIT | 3 | - Fact sheet | - Pub | - 3 |

* A short, self-evident description e.g. report, demonstration, conference, specification, prototype…

**Int.	Internal circulation within project (and Commission Project Officer if requested)

Rest.	Restricted circulation list (specify in footnote) and Commission PO only

IST	Circulation within IST Programme participants

FP5	Circulation within Framework Programme participants

Pub.	Public document

Technical Annex - Attachments:  15. Deliverable Specifications

| Del. no. | Deliverable name | WP no. | Lead participant |
| --- | --- | --- | --- |
| D1 | Content Creation and Content Management | 1 | IMAC |
| Estimated person-months | Del. type | Security | Delivery (proj.-month) |
| 34 | report | Pub. | 6 |
| Specification: This deliverable contains the results of Work Area A (Content Creation and Content Management) related to Work Package 1. It refers to the contents provided by the content providers to the REGNET demonstration phase. The content providers are: Region-1: ONB, SUL, LMG, NRM, KVA, (AIT, IMAC) Region-2: MECH, MUS Region-3: ALI, (CC) Region-4: GRAN In region-1 AIT and IMAC can also provide content (AIT: Basler Plakatsammlung, IMAC: Datenbank Schweizer Kulturgüter). CC will nominate content providers located in Latium and Umbria (Italian regions). The deliverable is divided in two main chapters related to two tasks of work package 1: Task 1.1: Definition of content to be provided. This chapter describes the content available for the demonstration and will be subdivided according to the domains covered by REGNET, mainly: libraries, museums, archives. All collections and their objects will be described according to a unique scheme which will be compatible to standard meta data schemes: x-MARC (library), ICOM/AMICO/CIMI (Museum), ISAD(G) (archives). A mapping to of these different schemas to DublinCore Metadata will be provided. Task 1.2: Development of a documentation and digitization plan for content creation and management. The deliverable will include a plan who to prepare the content of the different content holders in that way that it can be used by the REGNET demonstrator. This plan will be structured according to the different formats and material type and define how metadata will be generated. In addition this deliverable will include tools (conversion programs, date entry programs) necessary to enter metadata into the REGNET repositories and product catalogues. An exchange format based on XML will be generated. For the technical work (selection and implementation of tools) as well as for the necessary training of staff at the content provider’s side the technical partner(s) in a region will be responsible: Region-1: AIT, IMAC Region-2: TARX Region-3: SPAC Region-4: IAT, ZEUS, ICCS/SUSU The deliverable will include test samples form all content provider’s data relevant to REGNET. |  |  |  |

| Del. no. | Deliverable name | WP no. | Lead participant |
| --- | --- | --- | --- |
| D2 | The REGNET – System: Specifications and State of the Art | 1 | ZEUS |
| Estimated person-months | Del. type | Security | Delivery (proj.-month) |
| 72 | report | Pub. | 6 |
| Specification: This deliverable contains the results of Work Area B (Platform Engineering) related to Work Package 1. It refers to the design work to be done for the REGNET demonstrator and a study work related to standards, methods, and tools necessary for the REGNET implementation. The deliverable will include the basic design principles used for the design process and the baseline design as well as the detailed design for all of its components as outlined in the attachment. The tasks covered by this deliverables are: Task 1.3: Identification of standards to be used. This section is divided in two main paragraphs: - Ontology (metadata) related standards, bibliographic rules, workflow management, … - technical standards (ebusiness, protocol, formats, architectures, etc). There will also be a short outline about standards committees active in the REGNET related domains. Task 1.4: Development of the System Specifications. This task contains the majority of this deliverables. An introductory section related to this task contains the design methodology (eventual “OPEN – Object-oriented Process, Environment and Notation”) and all design documents (including interface and architectural specifications) related to the five REGNET – “nodes”: - REGNET-Portal, - REGNET-Cultural Heritage Data Management, - REGNET-eBusiness Data Management, - REGNET-Ontology Checker, - REGNET-Electronic Publisher. The deliverable also contains the class tree used for the implementation (as far as available at this stage). There will be a special section dedicated to application servers, eventually having “enhydra” as reference model for REGNET. The potential of the whole “infrastructure” will be evaluated based on the assumption that the REGNET-Publishing component can be considered as a kernel of a “media production centre”. 8 PMs will be dedicated to a research report which will be included in this deliverable and titled: “Cultural Heritage and eBusiness: A Standards Framework”. The work is carried out within task 1.3. |  |  |  |

| Del. no. | Deliverable name | WP no. | Lead participant |
| --- | --- | --- | --- |
| D3 | REGNET - Enterprise Engineering and Market Analysis | 1 | VALT |
| Estimated person-months | Del. type | Security | Delivery (proj.-month) |
| 19 | report | Pub. | 6 |
| Specification: This deliverable contains the results of Work Area C (Enterprise Engineering) related to Work Package 1. It has three different chapters related to task 1.5-7 of WP1. The first chapter will describe and elaborate the legal framework on which the operation of the REGNET network of service centres is based on. The second chapter provides input to the development activities and will describe the business layer of the REGNET system, and the last chapter is related to markets and user groups. The tasks covered by this deliverables are: Task 1.5: Set up of the Legal Framework and Partnership Model. This section is divided in two main paragraphs: - Legal framework (E.g. Copyright, etc) - Partnership Model (Based mainly on actual experiences like AMICO, MOSAIC, etc). The deliverable will include a set of agreements on international level and recommendations for national implementations thereof. Task 1.6: Definition of Supported Business Functions. This chapter contains a general overview of business processes and functions relevant to the Cultural Heritage sector. But it is also structured according the different domains (libraries, museum, archives, …) relevant to REGNET. The business processes will be grouped into blocks related to the REGNET concept: data entry, data management, media production, etc. As input to work area B “business objects” will be defined. Any processes and/or functions specific to a region will be described separately. Task 1.7: Identification of Market (Segments) and User Groups. This chapter of deliverable D3 includes an outline about market engineering relevant to REGNET and what methodology will be applied to market research. This will be based on practical experiences eventually made within other projects (e.g. COVAX). The chapter is divided into paragraphs related to different domains, especially what user groups, services and products are important within a domain. This might also affect the instantiation of a service centre dedicated to a domain. Specific issues relevant to a region will also be addressed. |  |  |  |

| Del. no. | Deliverable name | WP no. | Lead participant |
| --- | --- | --- | --- |
| D13 | REGNET – Information Dissemination Activities | 6 | SPAC |
| Estimated person-months | Del. type | Security | Delivery (proj.-month) |
| 17 | report | Pub. | 5 |
| Specification: This deliverable includes the description of the information dissemination activities of the REGNET project. Different activities like publication, attendance and organization of events (conferences, workshops, seminars, symposia, etc) are described and outlined in the attachment part. It refers to task 6.1 of work package 6. Task 6.1: Information Dissemination. The deliverable is structured according to the type (publication, event) of dissemination activities and work area (A-E) to which an activity belongs. |  |  |  |

| Del. no. | Deliverable name | WP no. | Lead participant |
| --- | --- | --- | --- |
| D14 | REGNET - Quality Assurance System | 7 | MOT |
| Estimated person-months | Del. type | Security | Delivery (proj.-month) |
| 6 | report | Rest. | 6 |
| Specification: This deliverable includes the description of all activities related to Quality Assurance (QA). It refers to task 7.2 of work package 7. Task 7.2: Quality Assurance. The deliverable contains two chapters. One describes the QA Plan and the procedures on which it is based on, the other how the QA-Activities are carried out within the REGNET project. It includes the form sheets used during the QA-process. QA-activities will be reported as attachment to bimonthly reports as appropriate. |  |  |  |

| Del. no. | Deliverable name | WP no. | Lead participant |
| --- | --- | --- | --- |
| D15 | Final Report | 7 | AIT |
| Estimated person-months | Del. type | Security | Delivery (proj.-month) |
| 6 | report | Pub. | 24 |
| Specification: This deliverable includes the description of all activities related to the REGNET project. It includes the activities related to the project management (task 7.1) as well as activities to project related information management and project presentation activities. Task 7.1: Project Management. One chapter of the report is dedicated to all management activities within the project. Other chapters are dedicated to work areas and will be subdivided according to the work plan of REGNET. A special chapter will be dedicated to the cluster activities especially to the relation with the Open Heritage Project. |  |  |  |

| Del. no. | Deliverable name | WP no. | Lead participant |
| --- | --- | --- | --- |
| D16 | Project Presentation (WEB Presence) | 7 | AIT |
| Estimated person-months | Del. type | Security | Delivery (proj.-month) |
| 6 | WEB-Site | Pub. | 3 |
| Specification: This deliverable includes the project presentation in the internet. It consists of the WEB-site which is located at http://www.regnet.org . The pages will be delivered as html-files. Connected services like a discussion list will be described and the usage and participants will be documented. |  |  |  |

| Del. no. | Deliverable name | WP no. | Lead participant |
| --- | --- | --- | --- |
| D17 | Project Presentation (Fact Sheet) | 7 | AIT |
| Estimated person-months | Del. type | Security | Delivery (proj.-month) |
| 3 | Fact sheet | Pub. | 3 |
| Specification: This deliverable includes the “project fact sheet”. It is of high quality and dedicated for distribution via different channels (events, mail, personal). Updates of the fact sheets will be attached to bimonthly reports. |  |  |  |