Attachment - PMG-01-01 / 013:

Working Plan for the first three months

| Task | Task/WP Description | Deliverables and milestones | Start Date | Coordinator |
| --- | --- | --- | --- | --- |
| WP 1 | Analysis of the State of the Art and Development of Concepts | D1, D2, D3 -> 2001-09-30 (1.Milestone) | 2000-04-01 | ZEUS |
| T 1.1 | Definition of content to be provided | IR 1.1 Interim Report -> 2001-06-30 (D1) | 2000-04-01 | IMAC |
| T 1.3 | Identification of standards to be used | IR 1.3 Interim Report -> 2001-05-31 (D2) | 2000-04-01 | IAT |
| T 1.4 | Development of the Systems Specifications | IR 1.4.1 Interim Report -> 2001-06-30 (D2) | 2000-05-01 | VALT |
| T 1.6 | Definition of Supported Business Functions | IR 1.6 Interim Report -> 2001-06-30 (D3) | 2000-04-01 | VALT |
| T1.7 | Identification of Market (Segments) and User Groups | IR 1.7.1 Interim Report -> 2001-06-30 (D3) | 2000-04-01 | TINC |
| WP 5 | Development of a technolo-gical implementation plan (TIP) | D12 -> 2003-03-31 (5. Milestone) | 2000-04-01 | MOT |
| T 5.1 | TIP - 1. Version | IR 5.1.1 Interim Report -> 2001-06-30 (D12) | 2000-04-01 | MOT |
| WP 6 | Dissemination and Use Plan | D13 -> 2003-03-31 (5. Milestone) | 2000-04-01 | SPACE |
| T 6.1 | Information Dissemination | IR 6.1.1 Interim Report -> 2001-06-30 (D13) | 2000-04-01 | SPACE |
| WP 7 | Project Management | D15 -> 2003-03-31 (5. Milestone) D16, D17 -> 2001-06-30 | 2000-04-01 | AIT |
| T 7.1 | Co-ordination | Bimonthly Report -> 2001-05-31 | 2000-04-01 | AIT |
| T 7.2 | Quality Assurance | IR 7.2 Interim Report -> 2001-06-30 (D14) | 2000-04-01 | MOT |

Technical Annex:  9.5 Project planning and timetable

9.6 Graphical presentation of project components

REGNET-IST-2000-26336

Task Brief

| WP Number and Title |  | WP x |  |  |
| --- | --- | --- | --- | --- |
| Task Number and Title |  | T x.y |  |  |
| Task Leader and Contact |  |  |  |  |
| Deliverable Number and Title |  | D z |  |  |
| Interm. Report Number and Title |  | IR x.y<.n> |  |  |
| Start Date: | yyyy.mm.dd |  | End Date: | yyyy.mm.dd |
| Methodology: |  |  |  |  |
| Partner | Contact (email) |  | Obligation |  |
| - AIT |  |  |  |  |
| - ONB |  |  |  |  |
| - SR (UniVie) |  |  |  |  |
| - IMAC |  |  |  |  |
| - SUL |  |  |  |  |
| - LMG |  |  |  |  |
| - NRM |  |  |  |  |
| - KVA |  |  |  |  |
| - TARX |  |  |  |  |
| - MECH |  |  |  |  |
| - MUS |  |  |  |  |
| - MOT |  |  |  |  |
| - SPAC |  |  |  |  |
| - ALI |  |  |  |  |
| - CC |  |  |  |  |
| - IAT |  |  |  |  |
| - GRAN |  |  |  |  |
| - ICCS(SUSU) |  |  |  |  |
| - ZEUS |  |  |  |  |
| - SI |  |  |  |  |
| - CERT |  |  |  |  |
| - VALT |  |  |  |  |
| - TINC |  |  |  |  |