7

REGNET-IST-2000-26336

Project Meeting Minutes

| Type and Name of Meeting | Extended Project Management Group Meeting PMG-01-02 |
| --- | --- |
| Dates of Meeting | 2001-09-12 – 2001-09-14 |
| Place of Meeting | Florence, Italy |
|  | CLUB EUROSTAR Railway Station of Florence Piazza Stazione 50100 Florence |
| Code Name | RN_PMGM02v02.doc |
| Version | V03 | draft ( final ( |
| Attendants | AIT: Mr. Walter Koch, Ms. Gerda Koch, Mr. Martin Bogensperger ONB: Mr. Hans Petschar, Mr. Christian Recht SR: Mr. Christian Eichinger, Mr. Erich Gams, UniVie: <represented by SR> IMAC: Mr. Josef Herget, Ms. Silke Grossmann SUL: Ms. Ingrid Cantwell, Mr Christer Wijkström, Mr. Clas-Ove Strandberg LMG: Ms. Katarina Stenius NRM: <represented by SUL> KVA: Mr. Carl Grandin, Mr. Christer Karlsson TARX: Mr. Vic Haesaerts MECH: Ms. Heidi De Nijn MUS: Mr. Hub Kockelkorn, Mr. Rob Schouten MOT: Mr. Davide Varvello SPAC: Mr. Stefano Cuomo, Ms. Flavia Saettone, Mr. Paolo Alongi ALI: Mr. Andrea de Polo, Mr. Sam Minelli CC: Ms. Michaela Michilli IAT: <represented by AIT> GRAN: Ms. Airí Masgrau ICCS: Ms. Krasimira Stoilova, Mr. Todor Stoilov SUSU: <represented by ICCS> ZEUS: Mr. Kostas Giotopoulos SI: Mr. Nikos Karatzoulis CERT: Mr. Dimitrios Tzovaras, Mr. Ioannis Tsampoulatidis VALT: Mr. Jean-Pierre Lorre TINC : Mr. Carlo Donzella |
| Contact Person | Christian Eichinger, christian.eichinger@salzburgresearch.at Gerda Koch, kochg@ait.co.at |
| Version Log | Version 01 (2001-09-16): initial meeting minutes composed from SR with open contributions of content group represented by IMAC Version 02 (2001-09-19): edited version with contribution from AIT |

Table of Contents

1	General Minutes	3

2	General Action List	9

2.1	Upcoming Events	9

2.2	Actions	9

# General Minutes

Wednesday, 2001-09-12

| Time | Partner | Description |
| --- | --- | --- |
| 13:40 | ALI | Opening Andrea de Polo |
| 13:55 | AIT | Walter Koch: Overview: Content Engineering, Platform Engineering, Business Engineering End of Sept. Deliverables should be finished ! |
| 15:15 | AIT | Gerda Koch: Reporting: The first two bimonthly reports have been sent to the Commission. There will be a switch to 3 monthly reports from the 1st of October onto the end of the project. Some changes in partner details will make a contract amendment necessary. These changes are: AIT changed name, SR scientific person in charge change, MOT address change AIT developed a poster for presentations of the project (First usage at ICHIM01). This poster can be downloaded from the web site, and reproduced by the partners. Poster demonstration A new public website design for the REGNET project has been developed and will be published soon. Partners were asked to comment on the new design. The first cost statement will be due end of September. The template contains two pages: overall Cost statement (in EURO and local currency) detailed Cost statement (only in EURO) (should reflect first bimonthly reports, the person months have to be the same) only net amounts can be charged to the Commission! Copies of the invoices for subcontractors have to be added to the cost statement Submission in first week of Oct. All partners should read Consortium agreement and send comments to it ASAP. The annexes to the consortium agreement will contain a list of the knowledge the partners have before starting the project. They will also contain the models for license agreements. A model for copyright statement has already been worked out and can be found in Annex 3. Licensing: Every partner should be able to use the REGNET framework and has copyright on the own modules. This issue has to be worked out for the CA within the next few days. It should be possible to bring the consortium agreement with the signatures of already some partners to the Review. REGNET has been invited to give a presentation at the MEDRESSA conference in Kairo, 8th of October. MEDRESSA os an IST accompanied measure supporting the commercial cooperation in the southern Mediterranean area. The conference in Kairo will focus on cultural heritage. The RN partner CC was asked to present REGNET at KAIRO, and agreed to do so. |
| 15:55 | SPAC | Interim report 6.1 – Information dissemination Report on template till end of Sept. All partners involved in T6.1 are asked to contribute ASAP: |
| 16:05 | MOT | Quality management plan should be provided till end of Sept. |
| 16:15 | ZEUS | WP1: IR 1.2/1.4/1.6 still to be finished |
| 16:20 | IMAC | WP1.1/1.2 The first version of IR1.1 is done in coordination with T1.4 and T1.6, use cases and requirements. IR1.2 is worked out in coordination with IR1.3 The themes define the type if priorisation in order to find out what should be digitized first. The edited version of IR1.1 and the results of IR1.2 will then constitute the D1. The outcome of T1.2 is to provide for every partner a customized digitization plan. As a first inputs the models are described. The next steps will be: Coordination with technical development, the impacts of the themes approach, the decision about standards and formats to be used, the merging of the work done. |
| 16:50 | TARX | Report on Themes, (~10 themes identified) A change to fragment data set fields has been performed. Additions and split of keywords. According to clustering it has been perceived that both OH and RN use the thematic approach, OH within the Narration’s module, while RN is applying the fragments into themes concept throughout all functionalities. An explicit reference to the usage in each project should be made in the future! |
| 17:30 | VALT | Report on Task 1.4: The main parts to be merged are: 1) the requirements, 2) the use case descriptions, 3) the functional technical architecture. Main aspects for the future are: a detailed description for each component a decision on which option to use - the definition of the software development plan Report on Task 1.6 The newest version has been put onto the server on 11.9. The domains modeled so far are: museums, art galleries and international supply chain. Further input from libraries and archives is needed! T1.6 defines the core processes within the REGNET business model, which is crucial for the revenue infrastructure. |
| 18:00 | AIT | Report on IR1.5 A first version of IR1.5 was distributed to the partners involved. It identified the work to be done by each partner and the dates for delivery of the contributions. A new table on status has been developed for this IR and it should be used at the beginning of each IR. This table shows the effort of each partner and the combined work structure of the different WP. For example, the analysis work of T1.5 will constitute the basis of the REGNET framework for T2.3. |
| 18:20 | TINC | Report on Task 1.7 T1.7 analyses the identified solutions and already existing services on the web. Still, national surveys of users, potential new products and services, and existing EU studies remain to be integrated. The Analysis of User Profiles might be shifted to WP2.? |
| 18:50 | AIT | AIT & SPAC will do the Clustering with Open Heritage OH is perceived as concentrating on the collection management systems, while REGNET concentrates on the integration of existing tools. Therefore OH could offer their collection management system to REGNET, but REGNET can not integrate this on a code level, but only via interface. OH will benefit from the outcome of T1.5 of REGNET. OH specially focuses on the modeling of a socio-economic prototype, and the simulations of these socio-economic model should give an input on how to adjust the economy. OH will develop a TSC, and provide a requirements report and TSC subsystem to REGNET. A prototype global portal OpenHeritage.com will be also developed. |
| 19:00 |  | Closing of first day |

Thursday, 2001-09-13

| Time | Partner | Description |
| --- | --- | --- |
| 09:15 | TARX | Report on Themes (cont.) Fragments in Theme Approach, the REGNET triangle. Guidelines for the contribution of themes by the partners have been developed. Content Providers are asked to prepare some examples for the TopicMap server. The REGNET data view divides between themes, fragments, and object images. Scenarios are needed There are already different demos on the RN web site (K42..) The latest standard of TopicMap is May2001, some samples are available on the server, and based on this application the client should be developed. Only some examples should be shown in REGNET. Very important for the fragment description are the primary keywords used for Search and Retrieval. |
| 09:50 | AIT | Report on IR 1.3 |
| 10:15 |  | Splitting up into two groups Content Provider and Technical Partners See RN_PTGM05v01_todo and RN_PTGM06v01 respectively |
| 13:00 |  | Lunch |
| 15:00 |  | Group splitting cont. See RN_PTGM05v01_todo and RN_PTGM06v01 respectively |
| 18:00 | IMAC | Report on Themes and Topic Maps More technical issues are still open, but a report should be ready within 2 weeks. Digitisation plan will not start at the beginning of Oct. |
|  | VALT | Report on IR 1.4, identification of open issues Regarding the functionalities the tech group agreed on the already established list. The REGNET system will provide a REGENT network with Master node (manages the ontology) and other Nodes (technical framework and copy of ontology). The different CSCs might provide diverse functionalities. Focus of the work on T1.4 now lies in the interfaces between the different functionalities |
|  | IMAC/ICCS/TINC | Report on IR 1.7 Will work together on the adaption of the existing IR1.7 A benchmarking concept, results of already existing studies, and a roadmap of how to achieve a business plan within the project should be added to the IR! |
|  | AIT | For IR 1.6 pages have to be doubled (32->75) For the User Interface contributions are welcome ! Studies like IFLA and the outcome of IMPRIMATUR should be integrated. AIT will deliver contributions on archives and libraries to T1.6. ONB can contribute some material on libraries processes. |
| 20:15 |  | Closing of second day |

Friday, 2001-09-14

| Time | Partner | Description |
| --- | --- | --- |
| 09:00 | AIT | Together with the cost statement an official progress report has to be sent to the Commission which states in a more detailed description the work that has been done during the first 6 months. A template for the periodic progress report will be distributed together with the cost statement template by AIT during next week. All partners are required to keep detailed work sheets of their effort charged to the project. Templates for Time Sheets and Work Sheets available if needed Next Meetings: Editorial Board: Editorial Board meeting end of September. The meeting will take place in Toulouse from the 27th to the 30th of September. Partners attending will be: IMAC, TARX, SUL, AIT, VALT, ZEUS, SR The work plan will be: Thu 27.9. D2 Fri 28.9. D1, D2, D3 Sat 29.9. D1, D3 Sun 30.9. D1, D3 All the other partners: please be available (for email, tel. etc.. contact) during this time !! The submission date for partner contributions to the Deliverables is Thu 20.9. 24:00!!! The final submission date for the end versions of the deliverables will be Wed 26.9. 24:00 !!! Minor corrections will be possible till Fri 28.9. 12:00. D1: IMAC, TARX, SUL, SR D2: AIT, VALT, ZEUS, TARX, SR D3: AIT, VALT, IMAC, SUL, SR SR will prepare a draft of a short CDROM presentation of REGNET (project and partners), appr. 10-15 min for the Review introduction. Review Meeting: AIT, VALT, IMAC, SR, ZEUS, MOT, TARX, SUL, IAT, TINC, SPAC, (ONB?) Correction to Florence!!!! The approved dates by Mr. Hoorens are: 24.9. OH Review 25.9. RN Review 26.9. OH Clustering The partners who were identified as participants to the Review at Florence are asked to be prepared to be available at Brussels on the 24.9. in the afternoon !! |
| 10:30 |  | Splitting up See RN_PTGM05v01_todo and RN_PTGM06v01 respectively |
| 12:30 |  | Lunch |
| 14:30 | AIT | WP 2: D4/D5/D6 must be provided at the end of month 12 of the project. Middle of Oct. Task Briefs ready IMAC will do the first version The technical management should make a detailed planning of T2.2. The content providers should start digitizing and give their material ASAP to the technicians.( deadline mid of WP2) Between the 28.6.02 and 31.3.03 the REGNET business should be prepared to go into operation! There might be the need to employ other economic professionals or consultants for REGNET. Also the marketing plan could be an outsourcing issue?! While OH will operate as a .com commercial organization, REGNET could focus on developing a non-profit organization. In the consortium agreement the usage of the regent system should be clarified, and also the maintenance after project end. The maintenance might be carried out by a maintenance agency or the partners should be able to apply for the source code and change/use the programs themselves Middle of January next Project Management meeting (Decision of location until end of Oct. Greece, Bulgaria or Barcelona?) The meeting will also be a three day event, with internet connection etc (partners should be prepared for doing some organization work!) After review meeting the project should agree on a conference preparation for September 2002 as outlined already in Page A-21 of the Attachments to the contract. (ONB has offered to provide the rooms) |
| 15:20 |  | Closing of third day |

# General Action List

## Upcoming Events

| Date | Description | Partner(s) |
| --- | --- | --- |
| 27.09.2001 - 30.09.2001 | Editorial Board Meeting (EBM) | see attachment for EBM |
| 24.10.2001 - 26.10.2001 | 24.10: Review Preparatory meeting 25.10: Review REGNET 26.10: RN-OH Clustering meeting | see attachement for review meeting |
| 8.10.2001 | Short CDROM introduction to REGNET for Review | SR |
| 01/2001 | Extended Project Management Group Meeting | All partners |
| 04/2001 | Extended Project Management Group Meeting | All partners |
| ? | CH Conference, September 2002 | SPAC, ONB |

## Actions

For detailed actions of the content group and technical group we refer to RN_PTGM05v01_todo and RN_PTGM06v01 respectively.

| Number* | Action / To Do | Task/WP | Responsible | Date+ |
| --- | --- | --- | --- | --- |
| GA 001 | Submission of updated Irxx and upload to REGNET web - all major changes need to be incorporated, minor changes allowed until the evening of 26.09.2001 Submission of the updated Quality Assurance Plan (T7.2) | T1.1 to T1.7 T7.2 | Task leaders, IMAC, VALT, ZEUS, SR | 20.09.2001 |
| GA 002 | 16:00 GMT: Submission of final IRxx documents with minor changes to the updated version of 20.09.2001 - the same is valid for T7.2 | T1.1 to T1.7 T7.2 | Task leaders, IMAC, VALT, ZEUS, SR | 26.09.2001 |
| GA 003 | Preparation and sending of cost claims for EC to AIT | n/a | all partners | 09.10.2001 |
| GA 004 | Guidelines for Structuring WP2 | WP2 | Task leaders | 08.10.2001 |
| GA 005 | Delivery of task briefs for WP2: 2.1 IMAC 2.2 ZEUS 2.3 AIT 2.4 VALT 2.5 TINC | WP2 | SR, Task leaders, MOT (quality assurance) | 15.10.2001 |
| GA 006 | Decision about next PMG Meeting in January Possible Hosts: ZEUS, ICCS, GRAN | - | PMG | 11/2001 |
| GA 007 | Planning of CH Conference SPAC as leader of dissemination activities ONB hosting | WP6 | SPAC | 11/2001 |
| GA 008 | User interface, 1st design |  | MOT | 12/2001 |

* GA 001 means "general action 1".

+ If not otherwise stated, delivery of action results (documents) to AIT have to take place until 07:00 a.m. GMT of the next working day, e.g. date is 20.09.2001, then results are due at 21.09.2001 07:00 a.m. GMT.